## Preparation
Pematang | Pematang P11 | Pematang 00108 | S1-E1-43B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210093DR | 2021-07-26 21:00 | 2021-07-26 21:00 | 2021-08-23 21:30 | Complete
Pematang | Pematang P11 | Pematang 00108 | S1-E1-43B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ABI-88 | GRK2/402/2210093DR | 2021-08-23 21:30 | 2021-07-26 21:00 | 2021-08-26 15:00 | Complete
Petani | Petani P01 | Petani 00130 | O-O-76B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210139DR | 2021-08-26 15:00 | 2021-09-04 04:00 | 2021-09-22 22:30 | Complete
Petani | Petani P03 | Petani 00131 | O-O-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210140DR | 2021-09-21 22:30 | 2021-09-26 02:30 | 2021-10-13 04:00 | Complete
Petani | PTN-P3 | Petani 00132 | O-O-77B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210143DR | 2021-10-13 04:00 | 2021-10-18 09:00 | 2021-11-05 21:30 | Complete
Petani | PTN-P4 | Petani 00133 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210144DR | 2021-11-05 21:30 | 2021-11-10 21:30 | 2021-11-30 | Complete
Petani | PTN-P1 | Petani 00134 | N1-W1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210141DR | 2021-11-30 | 2021-12-05 | 2021-12-25 09:00 | Complete
Petani | PTN-X10 | Petani 00135 | S1-O-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210142DR | 2021-12-25 09:00 | 2021-12-31 | 2022-02-02 13:00 | Complete
Petani | PTN-P2 | Petani 00137 | S1-O-14D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220243DR | 2022-02-02 13:00 | 2022-02-07 21:00 | 2022-02-25 14:00 | Complete
Petani | PTN-X09 | Petani 00139 | O-O-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220245DR | 2022-02-25 14:00 | 2022-03-02 18:00 | 2022-03-21 03:00 | Release
Petani | PTN-X08 | Petani 00140 | O-O-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220247DR | 2022-03-21 03:00 | 2022-03-27 11:30 | 2022-04-11 | Complete
Petani | PTN-X12 | Petani 00143 | O-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220248DR | 2022-04-11 | 2022-04-15 14:00 | 2022-04-30 | Complete
Petani | PTN-X13 | Petani 00146 | O-O-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220252DR | 2022-04-30 | 2022-05-05 | 2022-05-20 16:00 | Complete
Petani | PETA22-P23 | Petani 00147 | O-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220255DR | 2022-05-20 16:00 | 2022-05-30 03:00 | 2022-06-14 21:30 | Complete
Petani | PETA22-P04 | Petani 00150 | O-O-32D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220256DR | 2022-06-14 21:30 | 2022-06-20 21:00 | 2022-07-16 05:00 | Complete
Petani | PETA22-P06 | Petani 00152 | O-O-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220254DR | 2022-07-16 05:00 | 2022-07-22 07:00 | 2022-08-12 | Complete
Petani | PETA22-INJ4 | Petani 00156 | N1-W1-25A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220505DR | 2022-08-12 | 2022-08-17 12:00 | 2022-09-04 03:30 | Complete
Pematang | PMT-P02 | Pematang 00110 | O-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220520DR | 2022-09-04 03:30 | 2022-09-14 00:30 | 2022-11-08 22:00 | Complete
Pematang | PMT-P17 | Pematang 00113 | O-O-52E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220344DR | 2022-11-08 22:00 | 2022-11-21 12:00 | 2022-12-14 02:00 | Release
Petani | PETA22-P28 | Petani 00165 | O-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTK2/402/3220811DR | 2022-12-14 02:00 | 2022-12-24 14:00 | 2023-01-14 19:00 | Complete
Petani | PETA23-P32 | Petani 00166 | O-O-54D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTL2/402/3220812DR | 2023-01-14 19:00 | 2023-01-21 01:30 | 2023-02-09 12:00 | Complete
Petani | PETA23_P14 | Petani 00167 | O-O-85G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220903DR | 2023-02-09 12:00 | 2023-02-24 | 2023-03-18 | Complete
Petani | PETA22-P19 | Petani 00168 | O-O-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220913DR | 2023-03-18 | 2023-04-09 08:00 | 2023-04-30 19:00 | Complete
Petani | PETA23-P34 | Petani 00173 | O-O-85D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220914DR | 2023-04-30 19:00 | 2023-05-04 14:30 | 2023-05-28 05:00 | Complete
Petani | PETA23-P30 | Petani 00174 | O-O-85E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220912DR | 2023-05-28 05:00 | 2023-05-31 18:00 | 2023-06-20 | Complete
Petani | PETA23_P12 | Petani 00178 | O-O-85F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230291DR | 2023-06-20 | 2023-06-23 10:00 | 2023-07-10 16:00 | Complete
Petani | PETA23-P33 | Petani 00181 | O-O-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230298DR | 2023-07-10 16:00 | 2023-07-15 14:00 | 2023-08-01 | Complete
Petani | PETA23_P10 | Petani 00182 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTH2/402/3220808DR | 2023-08-01 | 2023-08-04 22:00 | 2023-08-22 07:00 | Complete
Petani | PT22_P21 | Petani 00187 | O-O-63D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230300DR | 2023-08-22 07:00 | 2023-08-25 12:30 | 2023-09-12 14:00 | Complete
Petani | PETA22-INJ3 | Petani 00189 | S1-O-15C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220917DR | 2023-09-12 14:00 | 2023-09-17 21:00 | 2023-10-12 | Complete
Petani | PETA23B-P03 | Petani 00192 | O-O-63E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230301DR | 2023-10-12 | 2023-10-16 14:00 | 2023-10-30 19:00 | Complete
Petani | PETA23_P07 | Petani 00196 | O-O63F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230302DR | 2023-10-30 19:00 | 2023-11-04 01:00 | 2023-11-20 13:30 | Complete
Kopar | KPR-X20 | Kopar 00040 | O-O-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220622DR | 2023-11-20 13:30 | 2023-11-28 13:30 | 2023-12-22 10:30 | Release
Kopar | KPR-X18 | Kopar 00042 | Kopar O-O-86A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220621DR | 2023-12-22 10:30 | 2024-03-26 05:30 | 2024-04-21 22:00 | Complete
Pudu | PDU23_P02 | Pudu 00021 | O-O-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSN2/402/3230693DR | 2024-01-31 17:00 | 2024-02-15 04:00 | 2024-03-13 15:00 | Complete
Kopar | KPR-X09 | Kopar 00044 | O-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220618DR | 2024-04-21 22:00 | 2024-04-29 06:00 | 2024-05-19 13:00 | Complete
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210093DR | 2021-11-04 16:00 | 2021-11-08 03:00 | 2021-11-13 20:00 | Complete
Bangko | BNK-P25 | Bangko 00353 | N1-W1-11A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210053DR | 2021-12-02 22:00 | 2021-12-04 02:00 | 2021-12-10 17:00 | Complete
Bangko | BNK-P32 | Bangko 00352 | N1-W3-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210061DR | 2021-12-18 02:30 | 2021-12-21 22:00 | 2021-12-27 16:00 | Complete
Bangko | BNK-P1 | Bangko 00382 | N1-W2-17C | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | ACS-005 | GRK2/402/2220060DR | 2022-05-08 05:00 | 2022-05-09 21:00 | 2022-05-10 07:00 | Complete
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ACS-005 | GRK2/402/2210123DR | 2022-05-27 22:00 | 2022-05-28 16:00 | 2022-06-05 11:00 | Complete
Minas | MINAHW23_P08 | Minas 02124 | 6C-19A | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | ACS-006 | SSM2/402/3230251DR | 2024-07-07 | 2024-07-07 22:00 | 2024-07-09 12:00 | Complete
Pematang | Pematang P05 | Pematang 00107 | O-O-32B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210093DR | 2021-07-18 22:30 | 2021-07-18 22:30 | 2021-08-15 21:30 | Complete
Pematang | Pematang P05 | Pematang 00107 | O-O-32B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210093DR | 2021-08-15 21:30 | 2021-07-18 22:30 | 2021-08-19 01:00 | Complete
Pemburu | PEMB21-P04 | Pemburu 00034 | S1-W1-38B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210121DR | 2021-08-16 | 2021-09-05 05:00 | 2021-09-06 17:00 | Complete
Pemburu | PEMB21-P04 | Pemburu 00034 | S1-W1-38B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210121DR | 2021-08-19 01:00 | 2021-08-28 14:00 | 2021-09-06 17:00 | Complete
Pemburu | PEMB21-P05 | Pemburu 00035 | S1-W1-37E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210122DR | 2021-09-06 17:00 | 2021-09-13 13:00 | 2021-09-23 | Complete
Pemburu | PEMB21-P05 | Pemburu 00035 | S1-W1-37E | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210122DR | 2021-09-21 | 2021-09-21 | 2021-09-23 | Complete
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210123DR | 2021-09-23 | 2021-09-27 05:00 | 2021-10-05 18:00 | Complete
Pemburu | PEMB21-P01 | Pemburu 00037 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210124DR | 2021-10-05 18:00 | 2021-10-09 15:00 | 2021-10-19 | Complete
Pemburu | PEMB21-P03 | Pemburu 00038 | O-O-65D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210125DR | 2021-10-19 | 2021-10-24 16:00 | 2021-11-02 | Complete
Bangko | BNK-P38 | Bangko 00366 | N1-W2-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210062DR | 2021-11-02 | 2021-11-13 20:00 | 2021-11-25 22:00 | Complete
Bangko | BNK-P24 | Bangko 00362 | N2-W1-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210052DR | 2021-11-25 22:00 | 2021-11-30 15:00 | 2021-12-10 22:00 | Complete
Bangko | BNK-P35 | Bangko 00370 | N1-W1-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210064DR | 2021-12-10 22:00 | 2021-12-29 19:00 | 2022-01-17 15:00 | Complete
Bangko | BNK-P13 | Bangko 00358 | N1-W2-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210041DR | 2022-01-17 15:00 | 2022-01-29 19:00 | 2022-02-10 10:30 | Complete
Duri | 6R-88B | Duri 10913 | 6R-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220098DR | 2022-02-10 10:30 | 2022-02-24 23:30 | 2022-03-13 10:00 | Complete
Duri | 3H-53C | Duri 10925 | 3H-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220105DR | 2022-03-13 10:00 | 2022-03-23 23:30 | 2022-04-06 16:00 | Complete
Duri | 3G-0502B | Duri 10932 | 3G-0502B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220110DR | 2022-04-06 16:00 | 2022-04-10 23:00 | 2022-05-02 19:00 | Complete
Duri | 3G-1002C | Duri 10938 | 3G-1002C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220117DR | 2022-05-02 19:00 | 2022-05-08 06:00 | 2022-05-20 19:00 | Complete
Duri | 5L-74D | Duri 10945 | 5L-74D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220123DR | 2022-05-20 19:00 | 2022-05-25 21:00 | 2022-06-05 07:00 | Complete
Duri | 4N-11C | Duri 10951 | 4N-11C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220127DR | 2022-06-05 07:00 | 2022-06-09 11:00 | 2022-06-20 21:00 | Complete
Duri | 3N-26B | Duri 10954 | 3N-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220132DR | 2022-06-20 21:00 | 2022-06-28 13:00 | 2022-07-09 04:00 | Complete
Duri | 3N-35G | Duri 10958 | 3N-35G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220137DR | 2022-07-09 04:00 | 2022-07-11 19:00 | 2022-07-30 21:00 | Complete
Duri | 6N-62D | Duri 10964 | 6N-62D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220142DR | 2022-07-30 21:00 | 2022-08-03 07:00 | 2022-08-13 08:30 | Complete
Pager | PG22-P16 | Pager 00051 | O-O-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220322DR | 2022-08-13 08:30 | 2022-08-29 16:00 | 2022-09-13 19:00 | Release
Pager | PG22-P06 | Pager 00052 | O-O-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220331DR | 2022-09-13 19:00 | 2022-09-19 07:00 | 2022-10-06 12:00 | Release
Sintong | SIN-P06 | Sintong 00052 | O-W1-67A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220661DR | 2022-10-06 12:00 | 2022-10-26 20:00 | 2022-11-09 17:30 | Complete
Sintong | SIN-P03 | Sintong 00053 | S1-O-13B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220421DR | 2022-11-09 17:30 | 2022-11-16 18:00 | 2022-11-28 16:00 | Complete
Sintong | SIN-P04 | Sintong 00054 | O-O-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220375DR | 2022-11-28 16:00 | 2022-12-05 10:00 | 2022-12-25 05:30 | Complete
Sintong | SIN-P02 | Sintong 00055 | O-O-71B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220395DR | 2022-12-25 05:30 | 2022-12-28 10:00 | 2023-01-14 | Complete
Sintong | SIN-P01 | Sintong 00056 | S1-O-34A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220444DR | 2023-01-14 | 2023-01-20 | 2023-02-09 | Complete
Sintong | SIN-P05 | Sintong 00057 | O-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220349DR | 2023-02-09 | 2023-02-28 | 2023-03-16 10:00 | Complete
Benar | BNR-X17 | Benar 00067 | O-O-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220846DR | 2023-03-16 10:00 | 2023-03-27 18:00 | 2023-04-07 14:00 | Complete
Benar | BNR-X18 | Benar 00069 | O-O-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220847DR | 2023-04-07 14:00 | 2023-04-13 21:00 | 2023-04-24 | Complete
Benar | BNR-X24 | Benar 00070 | O-O-46D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220848DR | 2023-04-24 | 2023-05-01 | 2023-05-11 05:00 | Complete
Bekasap | BKS-X02 | Bekasap 00228 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220452DR | 2023-05-11 05:00 | 2023-05-27 10:00 | 2023-06-06 02:00 | Complete
Bekasap | BKS-X06 | Bekasap 00229 | S1-O-27D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220614DR | 2023-06-06 02:00 | 2023-06-11 03:00 | 2023-06-23 09:00 | Complete
Bekasap | BKS-X03 | Bekasap 00230 | S1-O-27C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230153DR | 2023-06-23 09:00 | 2023-06-27 07:00 | 2023-07-08 12:30 | Complete
Bekasap | BKS-X04 | Bekasap 00231 | S1-O-27E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3220886DR | 2023-07-08 12:30 | 2023-07-13 | 2023-07-23 13:00 | Complete
Pungut | PUNG23_D01 | Pungut 00050 | S2-E1-11B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230199DR | 2023-07-23 13:00 | 2023-08-03 10:00 | 2023-08-14 15:30 | Complete
Pungut | PUNG23_P16 | Pungut 00051 | S2-E1-23A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230202DR | 2023-08-14 15:30 | 2023-08-20 08:30 | 2023-09-02 | Complete
Pungut | PUNG23_D02A | Pungut 00052 | S1-E1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230197DR | 2023-09-02 | 2023-09-07 | 2023-09-17 22:00 | Complete
Duri | 3H-65C | Duri 11118 | 3H-65C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230106DR | 2023-09-17 22:00 | 2023-09-28 11:00 | 2023-11-05 13:00 | Complete
Duri | 3L-18D | Duri 11131 | 3L-18D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230110DR | 2023-11-05 13:00 | 2023-11-13 16:00 | 2023-11-29 19:00 | Complete
Duri | 5G-1101A | Duri 11155 | 5G-1101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230108DR | 2023-11-29 19:00 | 2023-12-25 10:30 | 2024-03-11 10:30 | Complete
Duri | 5S-88B | Duri 11163 | 5S-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230111DR | 2023-12-31 10:00 | 2024-01-23 16:00 | 2024-02-04 10:30 | Complete
Duri | 7S-22B | Duri 11176 | 7S-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230109DR | 2024-02-04 10:30 | 2024-02-11 01:15 | 2024-02-27 09:30 | Complete
Duri | 4G-70D | Duri 11190 | 4G-70D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230107DR | 2024-03-11 10:30 | 2024-03-16 22:00 | 2024-03-28 22:30 | Complete
Duri | 3J-33B | Duri 11195 | 3J-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230105DR | 2024-03-28 22:30 | 2024-04-02 07:30 | 2024-04-18 05:00 | Complete
Duri | 4H-54C | Duri 11200 | 4H-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2240033DR | 2024-04-18 05:00 | 2024-04-22 18:00 | 2024-05-05 20:00 | Complete
Bekasap So | P_BESO24_03 | Bekasap So 00017 | S3-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSN2/402/3230683DR | 2024-05-05 20:00 | 2024-05-14 13:00 | 2024-05-30 13:00 | Complete
Pematang | P_PEMA24_10 | Pematang 00137 | O-O-52M | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230159DR | 2024-05-30 13:00 | 2024-06-04 17:00 | 2024-06-22 06:00 | Complete
Pematang | P_PEMA24_08 | Pematang 00138 | O-O-52L | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230157DR | 2024-06-22 06:00 | 2024-06-25 12:00 | 2024-07-11 07:00 | Complete
Pematang | P_PEMA24_07 | Pematang 00140 | O-O-52K | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230156DR | 2024-07-11 07:00 |  |  | In Progress
Minas | MNA-P3 | Minas 01988 | 8D-67N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220197DR | 2022-01-01 | 2022-01-01 | 2022-01-17 | Complete
Minas | MNA-P8 | Minas 01990 | 8D-66N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220199DR | 2022-01-17 | 2022-01-19 20:00 | 2022-02-01 13:00 | Complete
Minas | MNS-P16 | Minas 01991 | 8E-53E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3210109DR | 2022-02-01 13:00 | 2022-02-08 05:00 | 2022-02-27 | Complete
Minas | MNA-P7 | Minas 01993 | 8E-61N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220202DR | 2022-02-27 | 2022-03-05 | 2022-03-15 12:00 | Release
Minas | MNS-P4 | Minas 01994 | 8E-51E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220205DR | 2022-03-15 12:00 | 2022-03-19 13:00 | 2022-03-30 17:00 | Complete
Minas | MNA-P9 | Minas 01996 | 8E-41N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220207DR | 2022-03-30 17:00 | 2022-04-04 17:00 | 2022-04-18 01:00 | Complete
Minas | MNA-P15 | Minas 01999 | 8E-36E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220206DR | 2022-04-18 01:00 | 2022-05-03 05:00 | 2022-05-14 19:30 | Complete
Minas | MNS-P23 | Minas 02001 | 7E-88E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220203DR | 2022-05-14 19:30 | 2022-05-19 19:00 | 2022-05-30 08:00 | Complete
Minas | P_5D-92E | Minas 02004 | 5D-92E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220215DR | 2022-05-30 08:00 | 2022-06-04 | 2022-06-15 06:30 | Complete
Minas | P_7D-17S | Minas 02006 | 7D-17S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220219DR | 2022-06-15 06:30 | 2022-06-19 03:30 | 2022-06-29 05:00 | Complete
Minas | P_6C-28E | Minas 02008 | 6C-28E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220230DR | 2022-06-29 05:00 | 2022-07-09 03:00 | 2022-07-17 19:30 | Release
Minas | P_10D-24N | Minas 02012 | 10D-24N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220220DR | 2022-07-17 19:30 | 2022-07-23 17:00 | 2022-08-05 05:00 | Complete
Minas | P_8E-54E | Minas 02015 | 8E-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220222DR | 2022-08-05 05:00 | 2022-08-09 10:30 | 2022-08-21 22:00 | Complete
Minas | P_6C-21N | Minas 02018 | 6C-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220514DR | 2022-08-21 22:00 | 2022-08-29 | 2022-09-05 18:30 | Release
Minas | MNS-P08 | Minas 02021 | 9C-38 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220326DR | 2022-09-05 18:30 | 2022-09-14 02:00 | 2022-09-25 | Complete
Minas | P_3D-74E | Minas 02023 | 3D-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220333DR | 2022-09-25 | 2022-10-03 02:15 | 2022-10-14 17:00 | Complete
Minas | P_3D-73E | Minas 02026 | 3D-73E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220368DR | 2022-10-14 17:00 | 2022-10-18 19:00 | 2022-10-28 15:30 | Complete
Minas | P_3D-64E | Minas 02027 | 3D-64E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220347DR | 2022-10-28 15:30 | 2022-11-01 01:00 | 2022-11-12 03:00 | Complete
Minas | P_3D-34E1 | Minas 02030 | 3D-34E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220409DR | 2022-11-12 03:00 | 2022-11-23 10:00 | 2022-12-15 22:00 | Complete
Minas | P_6C-89E | Minas 02034 | 6C-89E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220387DR | 2022-12-15 21:00 | 2022-12-31 23:00 | 2023-01-14 02:00 | Release
Minas | P_4D-71E | Minas 02042 | 4D-71E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220448DR | 2023-01-14 02:00 | 2023-01-24 16:30 | 2023-02-06 19:00 | Complete
Minas | P_3A-26N | Minas 02046 | 3A-26N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220633DR | 2023-02-06 19:00 | 2023-02-24 14:00 | 2023-03-13 15:45 | Complete
Minas | P_10C-26 | Minas 02050 | 10C-26 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220646DR | 2023-03-13 15:45 | 2023-03-25 10:00 | 2023-04-06 05:00 | Complete
Minas | P_7C-16N | Minas 02055 | 7C-16N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220644DR | 2023-04-06 05:00 | 2023-04-14 15:00 | 2023-04-23 05:00 | Complete
Minas | P_7C-17S | Minas 02060 | 7C-17S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220650DR | 2023-04-23 05:00 | 2023-05-01 | 2023-05-11 03:00 | Complete
Minas | P_5C-63 | Minas 02065 | 5C-63 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220647DR | 2023-05-11 03:00 | 2023-05-17 | 2023-05-28 22:00 | Complete
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230246DR | 2023-05-28 22:00 | 2023-06-03 08:00 | 2023-06-16 10:00 | Complete
Minas | P_8E-46N | Minas 02073 | 8E-46N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230239DR | 2023-06-16 10:00 | 2023-06-23 02:30 | 2023-07-04 16:30 | Complete
Minas | MNS-P21 | Minas 02075 | 9D-48E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230216DR | 2023-07-04 16:30 | 2023-07-10 05:30 | 2023-07-20 03:00 | Release
Minas | MNS-P20 | Minas 02081 | 9D-28N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230214DR | 2023-07-20 03:00 | 2023-07-24 07:00 | 2023-08-03 04:30 | Complete
Minas | P_7D-32E | Minas 02085 | 7D-32E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230224DR | 2023-08-03 04:30 | 2023-08-08 | 2023-08-19 03:30 | Complete
Minas | P_7D-42E | Minas 02089 | 7D-42E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230218DR | 2023-08-19 03:30 | 2023-08-21 21:30 | 2023-08-31 09:30 | Complete
Minas | P_7D-43N | Minas 02093 | 7D-43N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230221DR | 2023-08-31 09:30 | 2023-09-02 22:00 | 2023-09-11 12:00 | Complete
Minas | P_MINA24_7E-93E | Minas 02094 | 7E-93E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230510DR | 2023-09-11 12:00 | 2023-09-16 11:30 | 2023-09-24 09:00 | Complete
Minas | P_MINA24_3D-13N | Minas 02096 | 3D-13N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230512DR | 2023-09-24 09:00 | 2023-09-30 10:00 | 2023-10-07 21:00 | Complete
Minas | P_3D-12N | Minas 02099 | 3D-12N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230229DR | 2023-10-07 21:00 | 2023-10-11 00:30 | 2023-10-18 05:00 | Complete
Minas | P_2D-85N | Minas 02103 | 2D-85N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230241DR | 2023-10-18 05:00 | 2023-10-22 14:30 | 2023-10-30 15:00 | Complete
Minas | P_MINA24_8E-44E | Minas 02106 | 8E-44E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230506DR | 2023-10-30 15:00 | 2023-11-06 16:30 | 2023-11-16 05:00 | Complete
Minas | P_3A-92E | Minas 02109 | 3A-92E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230219DR | 2023-11-16 05:00 | 2023-11-23 10:00 | 2023-12-04 10:00 | Release
Minas | P_MINA24_3D-55N | Minas 02112 | 3D-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230491DR | 2023-12-04 10:00 | 2023-12-12 14:00 | 2023-12-22 21:30 | Complete
Minas | P_MINA24_6B-29N | Minas 02116 | 6B-29N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230514DR | 2023-12-22 21:30 | 2024-02-06 00:30 | 2024-02-14 19:00 | Complete
Minas | P_MINA24_8C-77E | Minas 02120 | 8C-77E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230500DR | 2024-02-14 19:00 | 2024-02-28 15:00 | 2024-03-09 | Complete
Balam So | BLSO-P28 | Balam So 00449 | N1-W1-46B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | ACS-015 | GRK2/402/2220012DR | 2022-06-07 21:30 | 2022-06-09 19:00 | 2022-06-11 | Complete
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210065DR | 2021-11-18 12:00 | 2021-11-18 12:00 | 2021-12-12 16:00 | Release
Bangko | BNK-P37 | Bangko 00371 | N1-W1-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210068DR | 2021-12-12 16:00 | 2021-12-16 04:00 | 2021-12-29 16:30 | Complete
Balam So | BLSO-P14 | Balam So 00448 | O-O-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210003DR | 2021-12-29 16:30 | 2022-01-19 05:00 | 2022-01-28 17:00 | Complete
Duri | 5G-0812B | Duri 10916 | 5G-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220108DR | 2022-01-28 17:00 | 2022-02-08 | 2022-02-14 | Complete
Duri | 4H-1113B | Duri 10915 | 4H-1113B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220100DR | 2022-02-14 | 2022-02-17 09:00 | 2022-02-23 08:00 | Complete
Duri | 5F-1012B | Duri 10914 | 5F-1012B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220104DR | 2022-02-23 08:00 | 2022-02-26 05:00 | 2022-03-03 17:00 | Complete
Duri | 5F-1212B | Duri 10918 | 5F-1212B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220107DR | 2022-03-03 17:00 | 2022-03-05 20:00 | 2022-03-11 12:00 | Complete
Duri | 5H-0704B | Duri 10921 | 5H-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220115DR | 2022-03-11 12:00 | 2022-03-14 11:00 | 2022-03-20 02:00 | Complete
Duri | 6G-0703B | Duri 10924 | 6G-0703B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220118DR | 2022-03-20 02:00 | 2022-03-22 18:00 | 2022-03-28 05:00 | Complete
Duri | 6G-0101B | Duri 10928 | 6G-0101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220113DR | 2022-03-28 05:00 | 2022-03-30 17:00 | 2022-04-04 18:00 | Complete
Duri | 5E-1007B | Duri 10933 | 5E-1007B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220119DR | 2022-04-04 18:00 | 2022-04-06 15:00 | 2022-04-11 09:00 | Complete
Duri | 5E-0809B | Duri 10935 | 5E-0809B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220150DR | 2022-04-11 09:00 | 2022-04-18 12:00 | 2022-04-27 16:00 | Complete
Balam So | BLSO-P06 | Balam So 00466 | O-O-35F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220007DR | 2022-04-27 15:00 | 2022-05-05 16:00 | 2022-05-14 07:00 | Complete
Balam So | BLSO-P17 | Balam So 00472 | O-O-35G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220025DR | 2022-05-14 17:00 | 2022-05-17 04:00 | 2022-05-24 11:00 | Release
Balam So | BLSO-P20 | Balam So 00478 | O-O-16C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220020DR | 2022-05-24 11:00 | 2022-05-28 21:30 | 2022-06-05 17:00 | Complete
Balam So | BLSO-P18 | Balam So 00475 | O-O-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220014DR | 2022-06-05 17:00 | 2022-06-07 16:00 | 2022-06-14 13:00 | Complete
Balam So | LQR-TE195_BLSO_39 | Balam So 00488 | N1-W1-78A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220050DR | 2022-06-14 13:00 | 2022-06-19 06:00 | 2022-06-27 03:00 | Complete
Balam So | LQR-TE017_BLSO_38 | Balam So 00484 | N1-W1-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220033DR | 2022-06-27 03:00 | 2022-06-29 06:00 | 2022-07-06 10:00 | Complete
Balam So | LQR-TE073_BLSO_1 | Balam So 00492 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220034DR | 2022-07-06 10:00 | 2022-07-09 03:00 | 2022-07-16 09:30 | Complete
Balam So | LQR-TE031_BLSO_6 | Balam So 00506 | O-O-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220052DR | 2022-07-16 09:30 | 2022-07-18 14:00 | 2022-07-26 17:00 | Complete
Balam So | LQR-TE041_BLSO_3 | Balam So 00496 | O-O-44G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220042DR | 2022-07-26 17:00 | 2022-07-28 17:00 | 2022-08-05 | Complete
Balam So | BLSO-P48 | Balam So 00503 | BLSO O-O-44H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/3220221DR | 2022-08-05 | 2022-08-07 12:00 | 2022-08-14 06:45 | Complete
Balam So | BLSO-P43 | Balam So 00509 | O-O-44I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220318DR | 2022-08-14 06:45 | 2022-08-16 06:45 | 2022-08-24 05:00 | Complete
Balam So | LQR-TE197_BLSO_40 | Balam So 00486 | N1-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220324DR | 2022-08-24 05:00 | 2022-08-28 19:00 | 2022-09-06 08:30 | Complete
Balam So | BLSO-P47 | Balam So 00489 | O-O-44M | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220328DR | 2022-09-06 08:30 | 2022-09-11 01:30 | 2022-09-20 07:30 | Complete
Balam So | BLSO-P36 | Balam So 00491 | O-O-44N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220529DR | 2022-09-20 07:30 | 2022-09-22 05:00 | 2022-10-01 09:30 | Complete
Balam So | BLSO-P42 | Balam So 00499 | N1-W1-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220329DR | 2022-10-01 09:30 | 2022-10-07 03:00 | 2022-10-16 18:00 | Complete
Balam So | BLSO-P40 | Balam So 00507 | N1-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220404DR | 2022-10-16 18:00 | 2022-10-21 01:00 | 2022-11-01 19:00 | Complete
Balam So | LQR-TE142_BLSO_4 | Balam So 00508 | N1-O-76D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220540DR | 2022-11-01 19:00 | 2022-11-05 06:00 | 2022-11-15 | Complete
Balam So | LQR-TE081_BLSO_14 | Balam So 00510 | O-O-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220543DR | 2022-11-15 | 2022-11-19 21:00 | 2022-11-30 04:00 | Complete
Balam So | LQR-TE002_BLSO_42 | Balam So 00512 | N1-W1-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220362DR | 2022-11-30 04:00 | 2022-12-04 02:00 | 2022-12-11 05:00 | Complete
Balam So | BLSO23-P11 | Balam So 00513 | N1-O-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220590DR | 2022-12-11 05:00 | 2022-12-21 05:00 | 2023-01-01 03:00 | Complete
Balam So | BLSO23-P06 | Balam So 00515 | O-O-44L | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220592DR | 2023-01-01 03:00 | 2023-01-07 02:00 | 2023-01-16 08:00 | Complete
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220554DR | 2023-01-16 08:00 | 2023-01-19 14:00 | 2023-01-24 21:00 | Complete
Balam So | BLSO23-LQR-TE015 | Balam So 00519 | O-O-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220399DR | 2023-01-24 21:00 | 2023-01-30 09:00 | 2023-02-08 | Complete
Duri | 6G-0903B | Duri 11035 | 6G-0903B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220574DR | 2023-02-08 | 2023-02-25 01:00 | 2023-03-03 08:00 | Complete
Duri | 6L-87B | Duri 11036 | 6L-87B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220492DR | 2023-03-03 08:00 | 2023-03-08 23:30 | 2023-03-16 18:00 | Complete
Duri | 7M-59D | Duri 11037 | 7M-59D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220575DR | 2023-03-16 18:00 | 2023-03-20 16:30 | 2023-03-28 12:00 | Complete
Duri | 6G-1001B | Duri 11049 | 6G-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220856DR | 2023-03-28 12:00 | 2023-04-01 19:00 | 2023-04-07 09:00 | Complete
Duri | 6G-1003C | Duri 11041 | 6G-1003C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220875DR | 2023-04-07 09:00 | 2023-04-09 16:00 | 2023-04-15 18:00 | Complete
Duri | 5G-0704B | Duri 11054 | 5G-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220854DR | 2023-04-15 18:00 | 2023-04-18 09:00 | 2023-04-24 17:00 | Complete
Duri | 6G-0702B | Duri 11025 | 6G-0702B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230057DR | 2023-04-24 17:00 | 2023-04-26 21:00 | 2023-05-03 21:00 | Complete
Duri | 5H-0306B | Duri 11056 | 5H-0306B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220859DR | 2023-05-03 21:00 | 2023-05-07 02:30 | 2023-05-12 09:00 | Complete
Duri | 6G-0502B | Duri 11065 | 6G-0502B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220860DR | 2023-05-12 09:00 | 2023-05-14 17:00 | 2023-05-20 10:30 | Complete
Duri | 6G-0502C | Duri 11066 | 6G-0502C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230112DR | 2023-05-20 10:30 | 2023-05-22 15:00 | 2023-05-28 06:00 | Complete
Duri | 6G-0203B | Duri 11032 | 6G-0203B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | DRI2/402/3220827DR | 2023-05-28 06:00 | 2023-05-31 02:00 | 2023-06-06 14:00 | Complete
Duri | 6G-0203C | Duri 11058 | 6G-0203C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230069DR | 2023-06-06 14:00 | 2023-06-08 13:00 | 2023-06-15 03:00 | Complete
Duri | 2J-0911A | Duri 11081 | 2J-0911A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220739DR | 2023-06-15 03:00 | 2023-06-19 03:00 | 2023-06-26 19:00 | Complete
Duri | 2H-0507B | Duri 11074 | 2H-0507B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220734DR | 2023-06-26 19:00 | 2023-07-01 10:00 | 2023-07-13 06:00 | Complete
Duri | 2J-0411B | Duri 11082 | 2J-0411B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220766DR | 2023-07-13 06:00 | 2023-07-16 02:30 | 2023-07-22 10:00 | Complete
Duri | 5G-0213B | Duri 11088 | 5G-0213B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230062DR | 2023-07-22 10:00 | 2023-07-25 03:30 | 2023-08-01 07:00 | Complete
Duri | 5F-0210C | Duri 11089 | 5F-0210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230063DR | 2023-08-01 07:00 | 2023-08-02 22:30 | 2023-08-08 20:00 | Complete
Duri | 5F-0208B | Duri 11098 | 5F-0208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230064DR | 2023-08-08 20:00 | 2023-08-10 22:30 | 2023-08-17 17:00 | Complete
Duri | 5E-1107D | Duri 11099 | 5E-1107D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230065DR | 2023-08-17 17:00 | 2023-08-20 04:00 | 2023-08-26 11:00 | Complete
Duri | 5F-0810B | Duri 11101 | 5F-0810B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230081DR | 2023-08-26 11:00 | 2023-08-29 12:00 | 2023-09-04 18:00 | Complete
Duri | 5G-0210B | Duri 11102 | 5G-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230082DR | 2023-09-04 18:00 | 2023-09-07 07:00 | 2023-09-13 12:00 | Complete
Duri | 2J-0711A | Duri 11115 | 2J-0711A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220744DR | 2023-09-13 12:00 | 2023-09-16 02:00 | 2023-09-21 18:00 | Complete
Duri | 2J-0111A | Duri 11116 | 2J-0111A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220770DR | 2023-09-21 18:00 | 2023-09-23 22:00 | 2023-09-30 | Complete
Duri | 2H-1111A | Duri 11117 | 2H-1111A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220792DR | 2023-09-30 | 2023-10-01 10:00 | 2023-10-07 14:00 | Complete
Duri | 2J-0612A | Duri 11124 | 2J-0612A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220752DR | 2023-10-07 14:00 | 2023-10-08 22:00 | 2023-10-14 14:30 | Complete
Duri | 2J-0712B | Duri 11127 | 2J-0712B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220746DR | 2023-10-14 14:30 | 2023-10-15 20:00 | 2023-10-23 13:30 | Complete
Duri | 2J-0812A | Duri 11133 | 2J-0812A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220747DR | 2023-10-23 13:30 | 2023-10-25 00:30 | 2023-10-31 18:00 | Complete
Duri | 2J-0413B | Duri 11134 | 2J-0413B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220765DR | 2023-10-31 18:00 | 2023-11-03 12:00 | 2023-11-09 05:00 | Complete
Duri | 2H-1212A | Duri 11135 | 2H-1212A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220798DR | 2023-11-09 05:00 | 2023-11-11 08:30 | 2023-11-18 18:00 | Complete
Duri | 2J-0511A | Duri 11144 | 2J-0511A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220760DR | 2023-11-18 18:00 | 2023-11-21 03:00 | 2023-11-27 17:00 | Complete
Duri | 3J-0501A | Duri 11145 | 3J-0501A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220755DR | 2023-11-27 17:00 | 2023-11-29 12:00 | 2023-12-06 18:00 | Complete
Duri | 3H-1101A | Duri 11159 | 3H-1101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220785DR | 2023-12-06 18:00 | 2023-12-10 09:00 | 2023-12-16 | Complete
Duri | 3J-0301A | Duri 11160 | 3J-0301A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220774DR | 2023-12-16 | 2023-12-24 20:00 | 2023-12-31 12:00 | Complete
Duri | 2J-0212A | Duri 11166 | 2J-0212A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220780DR | 2023-12-31 12:00 | 2024-01-14 10:00 | 2024-01-24 06:00 | Complete
Duri | 2J-0610A | Duri 11173 | 2J-0610A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220749DR | 2024-01-24 06:00 | 2024-01-30 05:00 | 2024-02-06 05:00 | Complete
Duri | 2J-0210B | Duri 11174 | 2J-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220781DR | 2024-02-06 05:00 | 2024-02-10 13:00 | 2024-02-19 21:00 | Complete
Duri | 2J-0311A | Duri 11178 | 2J-0311A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220772DR | 2024-02-19 21:00 | 2024-02-21 13:00 | 2024-02-28 06:00 | Complete
Duri | 3J-0101A | Duri 11167 | 3J-0101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220790DR | 2024-02-28 06:00 | 2024-03-01 17:00 | 2024-03-07 08:00 | Complete
Duri | 2J-0412A | Duri 11179 | 2J-0412A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220759DR | 2024-03-07 08:00 | 2024-03-12 22:30 | 2024-03-19 15:00 | Complete
Duri | 4H-0912C | Duri 11193 | 4H-0912C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240066DR | 2024-03-19 15:00 | 2024-03-22 06:00 | 2024-03-28 22:00 | Complete
Duri | 6G-0504B | Duri 11194 | 6G-0504B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240068DR | 2024-03-28 22:00 | 2024-03-31 | 2024-04-06 22:00 | Complete
Duri | 3F-0402A | Duri 11203 | 3F-0402A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240069DR | 2024-04-06 22:00 | 2024-04-10 21:00 | 2024-04-18 19:00 | Complete
Duri | 4K-20F | Duri 11204 | 4K-20F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240070DR | 2024-04-18 19:00 | 2024-04-21 02:00 | 2024-04-28 20:00 | Complete
Duri | 5K-48F | Duri 11205 | 5K-48F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240071DR | 2024-04-28 20:00 | 2024-04-30 23:30 | 2024-05-07 18:00 | Complete
Duri | 5G-1012C | Duri 11213 | 5G-1012C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240075DR | 2024-05-07 18:00 | 2024-05-09 15:00 | 2024-05-16 06:00 | Complete
Duri | 5G-1012D | Duri 11217 | 5G-1012D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240072DR | 2024-05-16 06:00 | 2024-05-17 14:30 | 2024-05-26 | Complete
Duri | 6F-1203C | Duri 11220 | 6F-1203C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240073DR | 2024-05-26 | 2024-05-28 21:00 | 2024-06-04 10:00 | Complete
Duri | 5F-0606C | Duri 11221 | 5F-0606C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240074DR | 2024-06-04 10:00 | 2024-06-06 18:00 | 2024-06-13 12:00 | Complete
Duri | 9M-102A | Duri 11235 | 9M-102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230734DR | 2024-06-13 12:00 | 2024-06-16 02:00 | 2024-06-20 19:30 | Complete
Duri | 8L-54A | Duri 11237 | 8L-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230733DR | 2024-06-20 19:30 | 2024-06-23 13:00 | 2024-06-27 21:00 | Complete
Duri | 5E-1209C | Duri 11247 | 5E-1209C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240883DR | 2024-06-27 21:00 | 2024-06-30 18:00 | 2024-07-06 21:00 | Complete
Duri | 5E-0810B | Duri 11251 | 5E-0810B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240041DR | 2024-07-06 21:00 | 2024-07-08 03:30 | 2024-07-14 18:00 | Complete
Duri | 5F-0407B | Duri 11257 | 5F-0407B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240042DR | 2024-07-14 18:00 |  |  | In Progress
Duri | P_3Q39C | Duri 10855 | 3Q-39C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210093DR | 2021-08-03 21:00 | 2021-08-05 20:00 | 2021-08-09 16:00 | Complete
Duri | P_3R33E | Duri 10856 | 3R-33E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210025DR | 2021-08-09 16:00 | 2021-08-11 02:30 | 2021-08-14 22:00 | Complete
Duri | P_3R52B | Duri 10857 | 3R-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210026DR | 2021-08-14 22:00 | 2021-08-16 04:00 | 2021-08-20 03:30 | Complete
Duri | P_6M53C | Duri 10861 | 6M-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210028DR | 2021-08-20 03:30 | 2021-08-21 21:30 | 2021-08-25 05:00 | Complete
Duri | P_3P61E | Duri 10862 | 3P-61E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210027DR | 2021-08-25 05:00 | 2021-08-26 13:00 | 2021-08-31 06:00 | Complete
Duri | 6G-1004B | Duri 10863 | 6G-1004B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210153DR | 2021-08-31 06:00 | 2021-09-02 | 2021-09-06 06:00 | Complete
Duri | 5H-0504B | Duri 10864 | 5H-0504B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210092DR | 2021-09-06 06:00 | 2021-09-07 21:30 | 2021-09-11 16:30 | Complete
Duri | 5K-19B | Duri 10867 | 5K-19B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210090DR | 2021-09-11 16:30 | 2021-09-13 03:00 | 2021-09-17 11:30 | Complete
Duri | 5J-88C | Duri 10868 | 5J-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210091DR | 2021-09-17 11:30 | 2021-09-18 12:00 | 2021-09-23 10:00 | Complete
Duri | 5G-0212B | Duri 10869 | 5G-0212B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210089DR | 2021-09-23 10:00 | 2021-09-26 14:00 | 2021-09-30 20:00 | Complete
Duri | 6G-0201B | Duri 10872 | 6G-0201B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210079DR | 2021-09-30 20:00 | 2021-10-02 08:00 | 2021-10-06 07:00 | Complete
Duri | 6G-0404B | Duri 10873 | 6G-0404B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210080DR | 2021-10-06 07:00 | 2021-10-07 08:00 | 2021-10-11 05:00 | Complete
Duri | 6G-0401B | Duri 10876 | 6G-0401B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210081DR | 2021-10-11 05:00 | 2021-10-12 05:00 | 2021-10-16 | Complete
Duri | 6G-0401C | Duri 10877 | 6G-0401C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210073DR | 2021-10-16 | 2021-10-17 12:00 | 2021-10-21 20:00 | Complete
Duri | 5H-0507B | Duri 10880 | 5H-0507B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210088DR | 2021-10-21 20:00 | 2021-10-24 19:00 | 2021-10-29 08:00 | Complete
Duri | 5K-65D | Duri 10881 | 5K-65D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210106DR | 2021-10-29 08:00 | 2021-10-31 | 2021-11-04 19:30 | Complete
Duri | 7Q-25B | Duri 10884 | 7Q-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210107DR | 2021-11-04 19:30 | 2021-11-06 16:00 | 2021-11-12 | Complete
Duri | 4K-27D | Duri 10885 | 4K-27D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210115DR | 2021-11-12 | 2021-11-15 03:30 | 2021-11-20 05:15 | Complete
Duri | 4K-21D | Duri 10886 | 4K-21D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210110DR | 2021-11-20 05:15 | 2021-11-21 23:30 | 2021-11-27 16:00 | Complete
Duri | 7Q-16B | Duri 10889 | 7Q-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210113DR | 2021-11-27 16:00 | 2021-11-29 18:30 | 2021-12-06 03:30 | Complete
Duri | 7Q-13D | Duri 10890 | 7Q-13D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210111DR | 2021-12-06 03:30 | 2021-12-08 03:00 | 2021-12-13 17:30 | Complete
Duri | 6S-62B | Duri 10893 | 6S-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210116DR | 2021-12-13 17:30 | 2021-12-16 19:30 | 2021-12-21 16:30 | Complete
Duri | 6T-34D | Duri 10894 | 6T-34D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210117DR | 2021-12-21 16:30 | 2021-12-24 06:00 | 2021-12-29 | Complete
Duri | 3N-29F | Duri 10897 | 3N-29F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210120DR | 2021-12-29 | 2022-01-02 02:00 | 2022-01-11 20:00 | Complete
Duri | 3S-78D | Duri 10898 | 3S-78D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220088DR | 2022-01-11 20:00 | 2022-01-14 17:00 | 2022-01-19 13:00 | Complete
Duri | 4K-32C | Duri 10901 | 4K-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220090DR | 2022-01-19 13:00 | 2022-01-23 23:00 | 2022-01-29 10:00 | Complete
Duri | 5K-25C | Duri 10902 | 5K-25C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220092DR | 2022-01-29 10:00 | 2022-01-31 16:00 | 2022-02-05 16:30 | Complete
Duri | 5K-26D | Duri 10906 | 5K-26D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220094DR | 2022-02-05 16:30 | 2022-02-08 18:00 | 2022-02-18 | Complete
Duri | 5H-0604B | Duri 10909 | 5H-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220099DR | 2022-02-18 | 2022-02-20 10:00 | 2022-02-24 12:00 | Complete
Duri | 5H-0405B | Duri 10910 | 5H-0405B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220101DR | 2022-02-24 12:00 | 2022-02-26 13:30 | 2022-03-02 19:30 | Complete
Duri | 5G-0613B | Duri 10917 | 5G-0613B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220111DR | 2022-03-20 20:00 | 2022-03-20 20:00 | 2022-03-26 02:00 | Complete
Duri | 5G-0604B | Duri 10922 | 5G-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220106DR | 2022-03-26 02:00 | 2022-03-28 03:00 | 2022-04-01 20:30 | Complete
Duri | 5F-0410C | Duri 10920 | 5F-0410C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220109DR | 2022-04-01 20:30 | 2022-04-04 | 2022-04-08 11:00 | Complete
Duri | 5J-86B | Duri 10926 | 5J-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220120DR | 2022-04-08 11:00 | 2022-04-12 18:00 | 2022-04-18 10:00 | Complete
Duri | 6K-20F | Duri 10936 | 6K-20F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220138DR | 2022-04-18 11:00 | 2022-04-22 09:00 | 2022-04-27 10:00 | Complete
Duri | 5K-24E | Duri 10929 | 5K-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220122DR | 2022-04-27 10:00 | 2022-04-28 20:30 | 2022-05-04 13:00 | Complete
Duri | 6K-11C | Duri 10944 | 6K-11C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220140DR | 2022-05-04 13:00 | 2022-05-09 04:15 | 2022-05-14 05:00 | Complete
Duri | 5J-88D | Duri 10943 | 5J-88D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220133DR | 2022-05-14 05:00 | 2022-05-16 12:30 | 2022-05-21 22:15 | Complete
Duri | 5K-17C | Duri 10934 | 5K-17C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220135DR | 2022-05-21 22:15 | 2022-05-23 07:00 | 2022-05-28 05:00 | Complete
Duri | 6J-82C | Duri 10948 | 6J-82C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220143DR | 2022-05-28 05:00 | 2022-05-29 14:00 | 2022-06-05 03:00 | Complete
Duri | 5K-37B | Duri 10931 | 5K-37B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220125DR | 2022-06-05 03:00 | 2022-06-06 13:30 | 2022-06-11 06:00 | Complete
Duri | 6K-20E | Duri 10946 | 6K-20E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220145DR | 2022-06-11 06:00 | 2022-06-13 15:30 | 2022-06-18 09:00 | Complete
Duri | 5J-75C | Duri 10953 | 5J-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220128DR | 2022-06-18 09:00 | 2022-06-19 22:00 | 2022-06-24 21:00 | Complete
Duri | 4Q-12C | Duri 10957 | 4Q-12C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220155DR | 2022-06-24 21:00 | 2022-06-28 03:00 | 2022-07-01 23:00 | Complete
Duri | 5J-77C | Duri 10955 | 5J-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220130DR | 2022-07-01 23:00 | 2022-07-04 18:00 | 2022-07-09 10:30 | Complete
Duri | 6M-72D | Duri 10959 | 6M-72D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220153DR | 2022-07-09 10:30 | 2022-07-12 | 2022-07-15 20:00 | Complete
Duri | 7M-27B | Duri 10961 | 7M-27B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220149DR | 2022-07-15 20:00 | 2022-07-17 22:00 | 2022-07-23 05:00 | Complete
Duri | 6M-16B | Duri 10963 | 6M-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220151DR | 2022-07-23 05:00 | 2022-07-24 19:00 | 2022-07-28 14:30 | Complete
Duri | 6G-0603C | Duri 10966 | 6G-0603C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220147DR | 2022-07-28 14:30 | 2022-07-31 06:00 | 2022-08-04 06:00 | Complete
Duri | 4H-1011C | Duri 10974 | 4H-1011C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220131DR | 2022-08-04 06:00 | 2022-08-06 06:00 | 2022-08-10 11:00 | Complete
Duri | 4H-1111C | Duri 10970 | 4H-1111C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220563DR | 2022-08-10 11:00 | 2022-08-12 18:00 | 2022-08-16 21:00 | Complete
Duri | 5H-1001B | Duri 10973 | 5H-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220477DR | 2022-08-16 21:00 | 2022-08-19 02:30 | 2022-08-23 22:00 | Complete
Duri | 6F-0702C | Duri 10976 | 6F-0702C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220564DR | 2022-08-23 22:00 | 2022-08-26 01:00 | 2022-08-30 18:00 | Complete
Duri | 4H-1111B | Duri 10972 | 4H-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220565DR | 2022-08-30 18:00 | 2022-09-06 09:00 | 2022-09-06 09:00 | Complete
Duri | 5H-1005B | Duri 10977 | 5H-1005B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220479DR | 2022-09-06 09:00 | 2022-09-09 04:30 | 2022-09-13 16:00 | Complete
Duri | 5H-0903B | Duri 10979 | 5H-0903B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220480DR | 2022-09-13 16:00 | 2022-09-16 05:00 | 2022-09-21 09:00 | Complete
Duri | 5F-0907B | Duri 10981 | 5F-0907B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220465DR | 2022-09-21 09:00 | 2022-09-24 02:30 | 2022-09-29 12:15 | Complete
Duri | 5F-0910C | Duri 10984 | 5F-0910C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220466DR | 2022-09-29 12:15 | 2022-10-01 06:00 | 2022-10-05 20:00 | Complete
Duri | 5H-0307B | Duri 10986 | 5H-0307B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220484DR | 2022-10-05 20:00 | 2022-10-07 22:00 | 2022-10-12 23:00 | Complete
Duri | 5H-0303B | Duri 10989 | 5H-0303B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220483DR | 2022-10-12 23:00 | 2022-10-15 16:00 | 2022-10-20 | Complete
Duri | 5H-0310B | Duri 10990 | 5H-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220485DR | 2022-10-20 | 2022-10-22 02:00 | 2022-10-26 12:30 | Complete
Duri | 5F-1110B | Duri 10992 | 5F-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220472DR | 2022-10-26 12:30 | 2022-10-28 21:00 | 2022-11-02 13:30 | Complete
Duri | 6F-1002B | Duri 10988 | 6F-1002B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220469DR | 2022-11-02 01:30 | 2022-11-05 02:00 | 2022-11-09 19:00 | Complete
Duri | 5G-1110B | Duri 10997 | 5G-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220488DR | 2022-11-09 19:00 | 2022-11-15 22:00 | 2022-11-20 13:00 | Complete
Duri | 5G-1113C | Duri 11001 | 5G-1113C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220489DR | 2022-11-20 13:00 | 2022-11-22 19:30 | 2022-11-27 20:00 | Complete
Duri | 6G-1103B | Duri 11003 | 6G-1103B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220490DR | 2022-11-27 20:00 | 2022-11-30 18:00 | 2022-12-05 17:00 | Complete
Duri | 5G-1012B | Duri 11006 | 5G-1012B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220491DR | 2022-12-05 17:00 | 2022-12-07 17:00 | 2022-12-12 06:30 | Complete
Duri | 5G-0913B | Duri 11002 | 5G-0913B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220566DR | 2022-12-12 06:30 | 2022-12-19 18:00 | 2022-12-26 | Complete
Duri | 5G-0804B | Duri 11007 | 5G-0804B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220567DR | 2022-12-26 | 2023-01-01 | 2023-01-06 | Complete
Duri | 6G-0604B | Duri 11010 | 6G-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220568DR | 2023-01-06 | 2023-01-08 | 2023-01-12 21:00 | Complete
Duri | 5F-0512C | Duri 11013 | 5F-0512C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220569DR | 2023-01-12 21:00 | 2023-01-14 23:00 | 2023-01-20 18:30 | Complete
Duri | 6F-0602C | Duri 11018 | 6F-0602C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220570DR | 2023-01-20 18:30 | 2023-01-22 10:00 | 2023-01-27 19:15 | Complete
Duri | 5H-0202B | Duri 11020 | 5H-0202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220571DR | 2023-01-27 19:15 | 2023-01-30 02:30 | 2023-02-03 11:00 | Complete
Duri | 5H-0401B | Duri 11021 | 5H-0401B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220572DR | 2023-02-03 11:00 | 2023-02-05 | 2023-02-09 11:00 | Complete
Duri | 5I-0101B | Duri 11023 | 5I-0101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | DRI2/402/3220824DR | 2023-02-09 11:00 | 2023-02-19 | 2023-02-25 | Complete
Duri | 6G-0803B | Duri 11024 | 6G-0803B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220852DR | 2023-02-25 | 2023-02-27 06:00 | 2023-03-04 05:00 | Complete
Duri | 5G-0713C | Duri 11026 | 5G-0713C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220853DR | 2023-03-04 05:00 | 2023-03-23 | 2023-03-28 02:30 | Complete
Duri | 4H-1112B | Duri 11043 | 4H-1112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220861DR | 2023-03-28 02:30 | 2023-03-30 | 2023-04-04 04:00 | Complete
Duri | 5G-0811B | Duri 11044 | 5G-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220865DR | 2023-04-04 04:00 | 2023-04-06 | 2023-04-10 21:00 | Complete
Duri | 6G-0701C | Duri 11046 | 6G-0701C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230094DR | 2023-04-10 21:00 | 2023-04-12 16:00 | 2023-04-18 03:00 | Complete
Duri | 5G-0908B | Duri 11048 | 5G-0908B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220867DR | 2023-04-18 03:00 | 2023-04-20 02:00 | 2023-04-26 18:00 | Complete
Duri | 6G-0902B | Duri 11061 | 6G-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220855DR | 2023-04-26 18:00 | 2023-04-28 21:00 | 2023-05-04 02:30 | Complete
Duri | 5H-0802B | Duri 11062 | 5H-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230093DR | 2023-05-03 03:00 | 2023-05-05 10:00 | 2023-05-10 12:00 | Complete
Duri | 6F-1101C | Duri 11063 | 6F-1101C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230060DR | 2023-05-10 12:00 | 2023-05-13 05:00 | 2023-05-17 06:00 | Complete
Duri | 6F-1101D | Duri 11064 | 6F-1101D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230114DR | 2023-05-17 06:00 | 2023-05-18 15:00 | 2023-05-23 09:00 | Complete
Duri | 5F-0107B | Duri 11068 | 5F-0107B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230119DR | 2023-05-23 09:00 | 2023-05-25 09:00 | 2023-05-30 09:00 | Complete
Duri | 5F-0912B | Duri 11070 | 5F-0912B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230099DR | 2023-05-30 09:00 | 2023-05-31 23:30 | 2023-06-06 23:00 | Complete
Duri | 6F-0801C | Duri 11069 | 6F-0801C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230098DR | 2023-06-06 23:00 | 2023-06-08 14:30 | 2023-06-14 04:00 | Complete
Duri | 6F-0701C | Duri 11071 | 6F-0701C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230100DR | 2023-06-14 04:00 | 2023-06-16 02:00 | 2023-06-22 06:00 | Complete
Duri | 5F-0411B | Duri 11079 | 5F-0411B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230086DR | 2023-06-22 06:00 | 2023-06-24 06:00 | 2023-06-30 02:30 | Complete
Duri | 5F-1210B | Duri 11080 | 5F-1210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230075DR | 2023-06-30 02:30 | 2023-07-02 08:30 | 2023-07-07 20:00 | Complete
Duri | 5F-1210C | Duri 11083 | 5F-1210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230079DR | 2023-07-07 20:00 | 2023-07-09 00:30 | 2023-07-15 15:00 | Complete
Duri | 5F-0909B | Duri 11084 | 5F-0909B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230074DR | 2023-07-15 15:00 | 2023-07-17 03:00 | 2023-07-24 | Complete
Duri | 5H-0209B | Duri 11095 | 5H-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220858DR | 2023-07-24 | 2023-07-25 16:00 | 2023-07-30 14:00 | Complete
Duri | 5G-0512C | Duri 11096 | 5G-0512C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220874DR | 2023-07-30 14:00 | 2023-08-01 06:00 | 2023-08-06 06:00 | Complete
Duri | 5K-36B | Duri 11085 | 5K-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230125DR | 2023-08-06 06:00 | 2023-08-07 20:15 | 2023-08-16 12:30 | Complete
Duri | 4K-62E | Duri 11097 | 4K-62E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230122DR | 2023-08-16 12:30 | 2023-08-18 09:00 | 2023-08-25 | Complete
Duri | 5F-0811B | Duri 11105 | 5F-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230078DR | 2023-08-25 | 2023-08-27 12:00 | 2023-09-02 | Complete
Duri | 5F-0811C | Duri 11106 | 5F-0811C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230072DR | 2023-09-02 | 2023-09-03 09:30 | 2023-09-09 05:00 | Complete
Duri | 5F-0610B | Duri 11112 | 5F-0610B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230080DR | 2023-09-09 05:00 | 2023-09-10 14:00 | 2023-09-16 02:00 | Complete
Duri | 5F-0508C | Duri 11120 | 5F-0508C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230087DR | 2023-09-16 02:00 | 2023-09-17 06:00 | 2023-09-22 08:00 | Complete
Duri | 5F-0410D | Duri 11114 | 5F-0410D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230088DR | 2023-09-22 08:00 | 2023-09-23 18:00 | 2023-09-29 03:00 | Complete
Duri | 5F-1108C | Duri 11123 | 5F-1108C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230089DR | 2023-09-29 03:00 | 2023-09-30 12:00 | 2023-10-05 18:00 | Complete
Duri | 5F-0206B | Duri 11125 | 5F-0206B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230090DR | 2023-10-05 18:00 | 2023-10-07 06:00 | 2023-10-12 12:00 | Complete
Duri | 5F-0908B | Duri 11130 | 5F-0908B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230104DR | 2023-10-12 12:00 | 2023-10-14 | 2023-10-20 10:00 | Complete
Duri | 5E-1206B | Duri 11113 | 5E-1206B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230129DR | 2023-10-20 10:00 | 2023-10-22 20:00 | 2023-10-29 | Complete
Duri | 5E-0910C | Duri 11141 | 5E-0910C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230101DR | 2023-10-29 | 2023-10-30 16:00 | 2023-11-05 | Complete
Duri | 3F-0104B | Duri 11142 | 3F-0104B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230066DR | 2023-11-05 | 2023-11-07 12:00 | 2023-11-12 20:00 | Complete
Duri | 8L-25A | Duri 11143 | 8L-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230127DR | 2023-11-12 20:00 | 2023-11-16 | 2023-11-20 13:00 | Complete
Duri | 2J-0611A | Duri 11152 | 2J-0611A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220751DR | 2023-11-20 13:00 | 2023-11-22 22:00 | 2023-11-28 16:00 | Complete
Duri | 2J-0712A | Duri 11153 | 2J-0712A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220748DR | 2023-11-28 16:00 | 2023-11-29 19:00 | 2023-12-06 | Complete
Duri | 2J-0713A | Duri 11154 | 2J-0713A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220750DR | 2023-12-06 | 2023-12-07 10:00 | 2023-12-16 02:00 | Complete
Duri | 5F-0311B | Duri 11161 | 5F-0311B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230084DR | 2023-12-16 02:00 | 2023-12-22 01:30 | 2023-12-28 19:30 | Complete
Duri | 9M-126A | Duri 11151 | 9M-126A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230128DR | 2023-12-28 19:30 | 2024-01-28 22:00 | 2024-02-02 13:00 | Complete
Duri | 5F-0211B | Duri 11162 | 5F-0211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230085DR | 2023-12-30 13:30 | 2024-01-03 07:00 | 2024-01-09 03:00 | Complete
Duri | 5H-0902B | Duri 11177 | 5H-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240053DR | 2024-01-12 13:00 | 2024-01-19 22:00 | 2024-01-25 12:00 | Complete
Duri | 5F-0109C | Duri 11170 | 5F-0109C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240054DR | 2024-02-02 13:00 | 2024-02-07 10:30 | 2024-02-13 | Complete
Duri | 6G-0104B | Duri 11180 | 6G-0104B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240037DR | 2024-02-13 | 2024-02-15 02:30 | 2024-02-21 05:00 | Complete
Duri | 2J-0313A | Duri 11184 | 2J-0313A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220771DR | 2024-02-21 05:00 | 2024-02-24 16:00 | 2024-02-29 19:00 | Complete
Duri | 2J-0710A | Duri 11186 | 2J-0710A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220742DR | 2024-02-29 19:00 | 2024-03-02 21:00 | 2024-03-09 09:00 | Complete
Duri | 3J-0102B | Duri 11197 | 3J-0102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220793DR | 2024-03-09 09:00 | 2024-03-12 17:00 | 2024-03-18 23:00 | Complete
Duri | 6G-0704B | Duri 11198 | 6G-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240057DR | 2024-03-18 23:00 | 2024-03-21 11:00 | 2024-03-27 15:00 | Complete
Duri | 5G-0813B | Duri 11199 | 5G-0813B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240058DR | 2024-03-27 15:00 | 2024-03-29 09:00 | 2024-04-03 23:00 | Complete
Duri | 5G-0911B | Duri 11201 | 5G-0911B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240059DR | 2024-04-03 03:00 | 2024-04-05 23:00 | 2024-04-16 22:00 | Complete
Duri | 4V-46B | Duri 11208 | 4V-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240060DR | 2024-04-16 22:00 | 2024-04-19 11:00 | 2024-04-26 06:00 | Complete
Duri | 4K-11D | Duri 11211 | 4K-11D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240064DR | 2024-04-26 06:00 | 2024-04-28 05:00 | 2024-05-07 12:00 | Complete
Duri | 4K-22E | Duri 11214 | 4K-22E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240062DR | 2024-05-07 12:00 | 2024-05-09 | 2024-05-17 12:00 | Complete
Duri | 6F-1003B | Duri 11222 | 6F-1003B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240079DR | 2024-05-17 12:00 | 2024-05-19 16:00 | 2024-05-25 07:30 | Complete
Duri | 5F-0706B | Duri 11224 | 5F-0706B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240080DR | 2024-05-25 07:30 | 2024-05-26 19:00 | 2024-06-01 14:00 | Complete
Duri | 5G-0808B | Duri 11227 | 5G-0808B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240077DR | 2024-06-01 14:00 | 2024-06-03 02:00 | 2024-06-08 10:00 | Complete
Duri | 5F-0306B | Duri 11230 | 5F-0306B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240056DR | 2024-06-08 10:00 | 2024-06-11 10:30 | 2024-06-18 | Complete
Duri | 5F-0406B | Duri 11233 | 5F-0406B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240842DR | 2024-06-18 | 2024-06-19 03:00 | 2024-06-25 22:00 | Complete
Duri | 5E-1207B | Duri 11239 | 5E-1207B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240837DR | 2024-06-25 22:00 | 2024-06-27 04:00 | 2024-07-02 16:00 | Complete
Duri | 5G-0311B | Duri 11242 | 5G-0311B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240886DR | 2024-07-02 16:00 | 2024-07-04 03:00 | 2024-07-09 11:00 | Complete
Duri | 5G-0912C | Duri 11250 | 5G-0912C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240884DR | 2024-07-09 11:00 | 2024-07-10 22:00 |  | In Progress
Duri | P_7M37C | Duri 10850 | 7M-37C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210093DR | 2021-08-02 08:00 | 2021-08-06 14:15 | 2021-08-11 21:00 | Complete
Duri | P_8M75B | Duri 10851 | 8M-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210029DR | 2021-08-11 21:00 | 2021-08-15 08:00 | 2021-08-20 | Complete
Duri | P_8M20C | Duri 10858 | 8M-20C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3210154DR | 2021-08-20 | 2021-08-22 08:00 | 2021-08-31 12:00 | Complete
Bekasap | P02_BK21 | Bekasap 00197 | O-O-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210002DR | 2021-08-31 12:00 | 2021-09-07 06:00 | 2021-09-18 07:00 | Complete
Bekasap | BKS-P2 | Bekasap 00198 | O-E1-51C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210014DR | 2021-09-18 07:00 | 2021-09-22 16:00 | 2021-10-02 06:30 | Complete
Pematang | Pematang P02 | Pematang 00109 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210126DR | 2021-10-02 06:30 | 2021-10-05 21:00 | 2021-10-21 19:00 | Complete
Bekasap | BKS-P3 | Bekasap 00200 | O-E1-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210015DR | 2021-10-21 19:00 | 2021-10-27 | 2021-11-05 08:00 | Complete
Bekasap | BKS-P7 | Bekasap 00201 | O-E1-43C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210019DR | 2021-11-05 08:00 | 2021-11-07 15:00 | 2021-11-15 14:00 | Complete
Bekasap | BKS-P10 | Bekasap 00203 | S1-O-16J | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210004DR | 2021-11-15 14:00 | 2021-11-19 04:00 | 2021-11-26 11:00 | Complete
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210018DR | 2021-11-26 11:00 | 2021-11-29 05:00 | 2021-12-07 19:00 | Release
Bekasap | BKS-P12 | Bekasap 00207 | O-O-66B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210006DR | 2021-12-07 19:00 | 2021-12-11 16:30 | 2021-12-21 05:00 | Complete
Bekasap | BKS-P16 | Bekasap 00208 | O-O-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210017DR | 2021-12-21 05:00 | 2021-12-27 09:00 | 2022-01-04 07:30 | Release
Bekasap | BKS-P18 | Bekasap 00209 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210012DR | 2022-01-04 07:30 | 2022-01-08 18:00 | 2022-01-19 18:00 | Complete
Bekasap | BKS-P5 | Bekasap 00211 | S1-O-16G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220082DR | 2022-01-19 18:00 | 2022-01-23 19:00 | 2022-02-01 18:00 | Complete
Duri | 4H-0811B | Duri 10908 | 4H-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220095DR | 2022-02-01 18:00 | 2022-02-14 | 2022-02-20 09:30 | Complete
Duri | 5J-85C | Duri 10905 | 5J-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220096DR | 2022-02-20 09:30 | 2022-02-23 17:00 | 2022-03-01 03:00 | Complete
Bekasap | BKS-P9 | Bekasap 00214 | O-E1-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220083DR | 2022-03-01 03:00 | 2022-03-07 21:00 | 2022-03-18 | Complete
Bekasap | BKS-P13 | Bekasap 00216 | S1-O-36C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220086DR | 2022-03-18 | 2022-03-23 11:30 | 2022-04-04 | Complete
Bekasap | BKS-X10 | Bekasap 00218 | O-E1-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220286DR | 2022-04-04 | 2022-04-07 22:00 | 2022-04-20 | Complete
Bekasap | BKS-X11 | Bekasap 00219 | O-E1-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220284DR | 2022-04-26 | 2022-04-26 | 2022-05-05 20:00 | Complete
Menggala No | MNO-P05 | Menggala No 00048 | N3-W1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220196DR | 2022-05-05 20:00 | 2022-05-22 15:00 | 2022-06-05 09:30 | Complete
Menggala No | MNO-P13 | Menggala No 00050 | N3-W1-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220236DR | 2022-06-05 09:30 | 2022-06-09 | 2022-06-21 05:00 | Complete
Menggala No | MNO-P16 | Menggala No 00052 | N3-W1-36E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220239DR | 2022-06-21 05:00 | 2022-06-25 18:00 | 2022-07-08 | Complete
Menggala No | MNO-P14 | Menggala No 00054 | N3-W1-36D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220208DR | 2022-07-08 | 2022-07-10 20:00 | 2022-07-22 22:00 | Complete
Menggala No | MNO-P20 | Menggala No 00056 | N4-W1-83A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220212DR | 2022-07-22 22:00 | 2022-07-27 18:00 | 2022-08-09 19:00 | Complete
Menggala No | MNO-P21 | Menggala No 00058 | N4-W1-83B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220316DR | 2022-08-09 19:00 | 2022-08-14 11:00 | 2022-08-29 11:00 | Complete
Menggala No | MNO-P19 | Menggala No 00059 | N4-W1-83C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220518DR | 2022-08-29 11:00 | 2022-09-06 02:00 | 2022-09-19 16:00 | Complete
Balam So | LQR-TE049_BLSO_57 | Balam So 00494 | S1-O-74A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220528DR | 2022-09-19 16:00 | 2022-10-04 14:00 | 2022-10-13 06:00 | Complete
Balam So | LQR-TE180_BLSO_56 | Balam So 00498 | S1-O-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220536DR | 2022-10-13 06:00 | 2022-10-20 04:00 | 2022-10-30 18:00 | Complete
Balam So | BLSO-P44 | Balam So 00501 | N1-W1-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220342DR | 2022-10-30 18:00 | 2022-11-07 03:00 | 2022-11-15 20:00 | Complete
Balam So | LQR-TE016_BLSO_35 | Balam So 00504 | N1-W1-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220340DR | 2022-11-15 20:00 | 2022-11-24 | 2022-12-01 21:00 | Complete
Minas | P_4C-24E | Minas 02032 | 4C-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220553DR | 2022-12-01 21:00 | 2023-01-06 06:00 | 2023-01-19 08:00 | Complete
Minas | P_4C-25N1 | Minas 02036 | 4C-25N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220542DR | 2023-01-19 08:00 | 2023-01-28 17:45 | 2023-02-26 18:00 | Complete
Minas | P_4C-25N2 | Minas 02047 | 4C-25N2 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220430DR | 2023-02-26 18:00 | 2023-03-23 20:00 | 2023-04-04 12:00 | Complete
Minas | P_5C-95N | Minas 02054 | 5C-95N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220651DR | 2023-04-04 12:00 | 2023-04-11 13:30 | 2023-04-21 10:00 | Complete
Minas | P_4A-22 | Minas 02059 | 4A-22 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230211DR | 2023-04-21 10:00 | 2023-04-29 | 2023-05-10 15:00 | Complete
Minas | P_4A-23E | Minas 02062 | 4A-23E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220655DR | 2023-05-10 15:00 | 2023-05-14 05:00 | 2023-05-23 18:00 | Complete
Minas | P_7D-12N | Minas 02069 | 7D-12N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230244DR | 2023-05-23 18:00 | 2023-05-30 16:00 | 2023-06-09 08:30 | Complete
Minas | P_3D-33E | Minas 02072 | 3D-33E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220638DR | 2023-06-09 08:30 | 2023-06-19 18:00 | 2023-06-26 20:00 | Complete
Minas | P_5B-87E | Minas 02076 | 5B-87E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230227DR | 2023-06-26 20:00 | 2023-07-06 16:00 | 2023-07-15 07:00 | Complete
Minas | P_3B-34 | Minas 02082 | 3B-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220433DR | 2023-07-15 07:00 | 2023-07-20 21:00 | 2023-07-27 05:00 | Complete
Minas | P_6D-84E | Minas 02084 | 6D-84E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230238DR | 2023-07-27 05:00 | 2023-08-02 20:00 | 2023-08-10 17:00 | Complete
Minas | P_6D-96N | Minas 02088 | 6D-96N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230234DR | 2023-08-10 17:00 | 2023-08-13 10:30 | 2023-08-23 06:00 | Complete
Minas | P_4A-29 | Minas 02090 | 4A-29 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230249DR | 2023-08-22 06:00 | 2023-08-26 12:00 | 2023-09-13 22:00 | Complete
Minas | MNS-P11 | Minas 02095 | 8D-31E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230217DR | 2023-09-13 22:00 | 2023-09-20 12:00 | 2023-10-01 | Complete
Minas | Minas P03 | Minas 02097 | 8D-43N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220458DR | 2023-10-01 | 2023-10-04 10:00 | 2023-10-11 10:00 | Release
Minas | P_MINA24_8D-42N | Minas 02100 | 8D-42N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230503DR | 2023-10-11 10:00 | 2023-10-13 12:00 | 2023-10-21 18:30 | Complete
Minas | P_MINA24_6E-58N | Minas 02102 | 6E-58N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230497DR | 2023-10-21 18:30 | 2023-10-26 03:00 | 2023-11-01 21:00 | Release
Minas | P_MINA24_4A-43E | Minas 02105 | 4A-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230492DR | 2023-11-01 21:00 | 2023-11-08 13:00 | 2023-11-17 04:00 | Complete
Minas | P_MINA24_8D-12N1 | Minas 02108 | 8D-12N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230501DR | 2023-11-17 04:00 | 2023-11-23 10:00 | 2023-12-02 16:00 | Complete
Minas | P_MINA24_6E-57 | Minas 02111 | 6E-57 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230496DR | 2023-12-02 16:00 | 2023-12-17 16:00 | 2023-12-28 12:00 | Complete
Minas | P_MINA24_8D-23N1 | Minas 02115 | 8D-23N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230502DR | 2023-12-28 12:00 | 2024-06-29 11:00 | 2024-01-29 | Complete
Minas | P_3A-75N1 | Minas 02117 | 3A-75N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220634DR | 2024-01-29 | 2024-02-03 23:00 | 2024-02-14 | Complete
Minas | P_MINA24_6F-83 | Minas 02119 | 6F-83 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230508DR | 2024-02-14 | 2024-02-21 19:30 | 2024-03-05 12:45 | Complete
Minas | P_MINA24_7E-82N | Minas 02121 | 7E-82N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230520DR | 2024-03-05 12:45 | 2024-03-10 22:00 | 2024-03-20 18:00 | Complete
Minas | P_MINA24_8E-63N | Minas 02122 | 8E-63N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230505DR | 2024-03-20 18:00 | 2024-03-27 13:30 | 2024-04-08 09:30 | Complete
Minas | P_MINA24_8E-55N | Minas 02123 | 8E-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230504DR | 2024-04-08 09:30 | 2024-04-11 14:30 | 2024-04-22 22:00 | Complete
Minas | P_MINA24_10C-16 | Minas 02127 | 10C-16 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230507DR | 2024-04-22 22:00 | 2024-05-04 16:00 | 2024-05-17 08:30 | Complete
Minas | P_MINA24_7D-95N | Minas 02129 | 7D-95N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230517DR | 2024-05-17 08:30 | 2024-05-29 02:00 | 2024-06-09 11:00 | Complete
Minas | P_MINA24_5C-33 | Minas 02132 | 5C-33 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230521DR | 2024-06-09 11:00 | 2024-06-18 05:00 | 2024-06-28 09:00 | Complete
Minas | P_MINA24_6F-91 | Minas 02134 | 6F-91 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230509DR | 2024-06-28 09:00 | 2024-07-08 12:00 |  | In Progress
Hitam | Hitam P04 | Hitam 00011 | O-O-22A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/2210093DR | 2021-08-02 14:00 | 2021-08-06 | 2021-09-01 05:00 | Complete
Hitam | Hitam P04 | Hitam 00011 | O-O-22A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-021 | GRK2/402/2210093DR | 2021-09-01 05:00 | 2021-09-01 05:00 | 2021-09-03 18:00 | Complete
Kotabatak | KOTA21_P_TE_2A | Kotabatak 00457 | N1-W1-42A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210100DR | 2021-09-03 18:00 | 2021-09-17 14:00 | 2021-10-01 03:00 | Complete
Kotabatak | KOTA21_P_TE_INJ_1 | Kotabatak 00458 | N1-W1-46A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210102DR | 2021-10-01 03:00 | 2021-10-05 19:00 | 2021-10-15 09:00 | Complete
Kotabatak | KOTA21_P_TE_B2 | Kotabatak 00459 | N1-W1-84E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210098DR | 2021-10-15 09:00 | 2021-10-21 10:00 | 2021-11-02 | Complete
Petapahan | PTP-P4 | Petapahan 00152 | N2-W1-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210151DR | 2021-11-02 | 2021-11-10 22:00 | 2021-11-24 16:30 | Complete
Kotabatak | KTB-P2 | Kotabatak 00463 | S1-E1-72 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210104DR | 2021-11-24 16:30 | 2021-12-01 09:00 | 2021-12-18 17:00 | Complete
Kotabatak | KTB-X04 | Kotabatak 00467 | N1-O-73A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/2210131DR | 2021-12-18 17:00 | 2021-12-26 11:30 | 2022-01-05 03:30 | Complete
Kotabatak | KTB-X18 | Kotabatak 00470 | O-O-13 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220165DR | 2022-01-05 03:30 | 2022-01-10 19:00 | 2022-01-20 08:30 | Complete
Kotabatak | KTB-X03 | Kotabatak 00473 | N1-O-32A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210103DR | 2022-01-20 08:30 | 2022-01-25 08:00 | 2022-02-09 04:00 | Complete
Kotabatak | KTB-X05 | Kotabatak 00476 | O-O-18 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220173DR | 2022-02-09 04:00 | 2022-02-14 13:30 | 2022-02-24 13:00 | Complete
Kotabatak | KTB-X06 | Kotabatak 00479 | S1-O-12A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220170DR | 2022-02-24 13:00 | 2022-03-02 01:00 | 2022-03-12 15:30 | Complete
Kotabatak | KTB-X07 | Kotabatak 00481 | N1-W1-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220176DR | 2022-03-12 15:30 | 2022-03-21 21:00 | 2022-04-01 09:00 | Complete
Petapahan | PETP21_HW_P07_Ext | Petapahan 00156 | N2-W1-34B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220268DR | 2022-04-01 09:00 | 2022-04-12 01:00 | 2022-06-01 13:00 | Suspended
Kotabatak | KTB-X17 | Kotabatak 00485 | O-O-39 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220180DR | 2022-07-04 09:00 | 2022-07-12 22:00 | 2022-07-23 05:00 | Complete
Kotabatak | KTB-X02 | Kotabatak 00489 | N1-E1-73 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220182DR | 2022-07-23 05:00 | 2022-07-26 03:00 | 2022-08-08 04:00 | Complete
Petapahan | PTP-P2R | Petapahan 00158 | N2-W1-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220511DR | 2022-08-08 04:00 | 2022-08-24 16:45 | 2022-09-10 02:00 | Complete
Petapahan | PTP-P6 | Petapahan 00159 | N2-W1-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220524DR | 2022-09-10 02:00 | 2022-09-14 11:00 | 2022-09-30 16:00 | Complete
Petapahan | P_PETP_INF13_S01 | Petapahan 00160 | N1-W1-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220335DR | 2022-09-30 16:00 | 2022-10-07 06:00 | 2022-12-10 21:00 | Complete
Petapahan | PTPBL1-P13 | Petapahan 00161 | O-E1-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220356DR | 2022-12-09 20:00 | 2022-12-24 23:30 | 2023-01-11 20:00 | Complete
Petapahan | PTPBL1-P14 | Petapahan 00163 | O-E1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220381DR | 2023-01-11 20:00 | 2023-01-17 22:00 | 2023-02-03 15:00 | Complete
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220624DR | 2023-02-03 15:00 | 2023-02-11 01:00 | 2023-03-02 | Complete
Kotabatak | KTB-A271 | Kotabatak 00514 | S1-E1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230385DR | 2023-03-02 | 2023-03-08 22:00 | 2023-03-21 12:00 | Complete
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220544DR | 2023-03-21 12:00 | 2023-04-12 17:00 | 2023-04-23 03:00 | Complete
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230387DR | 2023-04-23 03:00 | 2023-04-29 06:00 | 2023-05-12 | Complete
Kotabatak | KTB-A128 | Kotabatak 00524 | S1-E1-18 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230383DR | 2023-05-12 | 2023-05-17 | 2023-05-27 | Complete
Kotabatak | KTB-X33-INJ | Kotabatak 00530 | O-W2-29 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230382DR | 2023-05-27 | 2023-06-01 09:00 | 2023-06-10 19:00 | Complete
Kotabatak | KB_PL34 | Kotabatak 00531 | O-W1-13 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230392DR | 2023-06-10 19:00 | 2023-06-14 09:00 | 2023-06-30 | Complete
Kotabatak | KTB-X34-INJ | Kotabatak 00532 | O-W1-20 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230389DR | 2023-06-30 | 2023-07-03 01:00 | 2023-07-14 01:00 | Complete
Kotabatak | KB_PL1 | Kotabatak 00538 | O-W2-19 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230416DR | 2023-07-14 01:00 | 2023-07-17 23:00 | 2023-07-27 03:30 | Complete
Kotabatak | KTB-X24 | Kotabatak 00539 | N1-W2-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230426DR | 2023-07-27 03:30 | 2023-07-30 | 2023-08-09 07:00 | Release
Kotabatak | KB_PL3 | Kotabatak 00540 | O-W2-25 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230420DR | 2023-08-09 07:00 | 2023-08-12 09:00 | 2023-08-23 12:00 | Complete
Topaz | P_TOPA23_P10 | Topaz 00012 | O-O-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230680DR | 2023-08-23 12:00 | 2023-08-29 22:00 | 2023-09-11 11:00 | Complete
Libo Se | LISE23_CC16 | Libo Se 00058 | S1-E4-86 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230628DR | 2023-09-11 11:00 | 2023-09-23 13:00 | 2023-10-20 07:00 | Complete
Libo Se | LISE23_SC03 | Libo Se 00059 | S2-W3-67A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230657DR | 2023-10-20 07:00 | 2023-10-25 19:00 | 2023-11-11 23:00 | Complete
Libo Se | LISE23_SO01 | Libo Se 00060 | S3-E5-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230659DR | 2023-11-11 23:00 | 2023-11-17 04:30 | 2023-12-06 05:00 | Complete
Libo Se | LISE23_CC15 | Libo Se 00061 | S2-E5-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230627DR | 2023-12-06 05:00 | 2023-12-28 | 2024-01-16 | Complete
Libo Se | LISE23_CC09 | Libo Se 00062 | S2-E4-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230621DR | 2024-01-16 | 2024-02-01 09:00 | 2024-02-18 12:00 | Complete
Libo Se | LISE23_CC08 | Libo Se 00063 | S2-E4-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230620DR | 2024-02-18 12:00 | 2024-02-21 19:00 | 2024-03-07 07:00 | Complete
Petani | P_PETA24_31 | Petani 00202 | O-O-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | PTO2/402/3230894DR | 2024-03-07 07:00 | 2024-03-20 02:00 | 2024-04-06 13:30 | Complete
Benar | BNR-X02 | Benar 00056 | N1-W1-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | GRK2/402/2220240DR | 2022-07-21 11:00 | 2022-07-21 11:00 | 2022-08-03 08:00 | Complete
Benar | BNR-X19 | Benar 00057 | O-E1-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | GRK2/402/2220087DR | 2022-08-03 08:00 | 2022-08-08 17:00 | 2022-08-18 05:00 | Complete
Benar | BNR-X20 | Benar 00058 | S1-O-15A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220521DR | 2022-08-18 05:00 | 2022-08-28 20:00 | 2022-09-15 05:00 | Complete
Benar | BNR-X04 | Benar 00059 | N1-E1-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220533DR | 2022-09-15 05:00 | 2022-09-25 03:00 | 2022-10-06 | Complete
Benar | BNR-X05 | Benar 00060 | N2-0-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220355DR | 2022-10-06 | 2022-10-15 | 2022-10-24 03:30 | Release
Benar | BNR-X15 | Benar 00061 | N1-O-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220379DR | 2022-10-24 03:30 | 2022-10-31 | 2022-11-12 21:30 | Complete
Benar | P_BENA22-P09 | Benar 00062 | N2-E1-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220422DR | 2022-11-12 21:30 | 2022-11-22 03:30 | 2022-12-06 06:00 | Complete
Benar | P_BENA22-P06 | Benar 00063 | N1-O-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220441DR | 2022-12-06 06:00 | 2022-12-14 14:00 | 2022-12-24 05:00 | Complete
Benar | BNR-X23 | Benar 00064 | O-O-58A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220397DR | 2022-12-24 05:00 | 2022-12-31 20:00 | 2023-01-10 18:30 | Complete
Benar | BNR-X16 | Benar 00065 | O-E1-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220615DR | 2023-01-10 18:30 | 2023-01-15 16:30 | 2023-01-28 22:30 | Complete
Benar | P_BENA23_P04 | Benar 00066 | N1-O-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SBN2/402/3220849DR | 2023-01-28 22:30 | 2023-02-03 14:00 | 2023-02-27 01:00 | Complete
Menggala No | MNO-P12 | Menggala No 00060 | N3-W1-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230204DR | 2023-02-27 01:00 | 2023-03-14 07:00 | 2023-04-12 01:30 | Complete
Menggala No | MNO-P23 | Menggala No 00061 | N3-W1-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230205DR | 2023-04-12 01:30 | 2023-04-23 12:00 | 2023-05-08 | Complete
Menggala No | MNO-P25 | Menggala No 00062 | N4-W1-83D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230208DR | 2023-05-08 | 2023-05-18 20:00 | 2023-05-31 15:00 | Complete
Menggala No | MNO-P22 | Menggala No 00063 | N4-W1-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230206DR | 2023-05-31 15:00 | 2023-06-07 | 2023-06-23 07:00 | Complete
Menggala No | MNO-P24 | Menggala No 00064 | N4-W2-25 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230207DR | 2023-06-23 07:00 | 2023-07-01 02:30 | 2023-07-16 21:00 | Complete
Menggala No | MNO-P26 | Menggala No 00065 | N4-W2-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230209DR | 2023-07-16 21:00 | 2023-07-31 22:30 | 2023-08-14 12:00 | Release
Balam So | BLSO23-LQR-TE033 | Balam So 00546 | N1-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220585DR | 2023-08-14 12:00 | 2023-08-22 22:00 | 2023-08-30 | Complete
Balam So | BLSO23-LQR-TE050 | Balam So 00549 | N1-W1-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230336DR | 2023-08-30 | 2023-09-05 18:00 | 2023-09-11 10:00 | Release
Balam So | BLSO23-LQR-TE069 | Balam So 00550 | N1-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230358DR | 2023-09-11 10:00 | 2023-09-16 03:00 | 2023-09-23 10:00 | Complete
Balam So | LQR-TE003_BLSO_41 | Balam So 00553 | N1-W1-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220583DR | 2023-09-23 10:00 | 2023-09-28 02:00 | 2023-10-05 13:00 | Complete
Balam So | LQR-TE217_BLSO_43 | Balam So 00555 | N1-W1-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220584DR | 2023-10-05 13:00 | 2023-10-08 09:00 | 2023-10-15 15:00 | Complete
Kulin | KLN23-P01 | Kulin 00093 | S2-E1-32 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | KLN2/402/3230009DR | 2023-10-15 15:00 | 2023-10-25 12:00 | 2023-11-03 21:00 | Complete
Kulin | KLN23-P02 | Kulin 00094 | S2-0-38 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | KLN2/402/3230010DR | 2023-11-03 21:00 | 2023-11-09 | 2023-11-21 05:00 | Complete
Bekasap | BKS23-P01 | Bekasap 00232 | S1-E2-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SAB2/402/3230478DR | 2023-11-21 05:00 | 2023-11-30 19:30 | 2023-12-21 10:30 | Complete
Pematang | P_PEMA24_13 | Pematang 00128 | O-O-42B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230162DR | 2023-12-21 10:30 | 2023-12-29 12:00 | 2024-01-18 | Complete
Pematang | P_PEMA24_INJ3 | Pematang 00130 | O-O-23B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230170DR | 2024-01-18 | 2024-01-28 12:00 | 2024-02-16 | Complete
Pematang | P_PEMA24_INJ4 | Pematang 00132 | O-W1-36A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230171DR | 2024-02-16 | 2024-02-23 | 2024-03-18 07:00 | Complete
Pematang | P_PEMA24_INJ2 | Pematang 00134 | O-O-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230169DR | 2024-03-18 07:00 | 2024-03-25 12:00 | 2024-04-18 | Complete
Pungut | PUNG23_D02B | Pungut 00058 | S1-0-48D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230200DR | 2024-04-18 | 2024-04-27 03:00 | 2024-05-10 09:00 | Complete
Pungut | PUNG23_D02C | Pungut 00059 | S1-0-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230203DR | 2024-05-10 09:00 | 2024-05-16 13:00 | 2024-05-29 | Complete
Pungut | PUNG23_D13 | Pungut 00060 | S2-E1-54F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230193DR | 2024-05-29 | 2024-06-04 04:00 | 2024-06-23 12:00 | Complete
Pungut | PUNG23_D14 | Pungut 00061 | S2-E1-54G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230195DR | 2024-06-23 12:00 | 2024-06-28 01:00 | 2024-07-10 08:00 | Complete
Balam So | P_BLSO24_LQR09 | Balam So 00604 | N1-W1-44C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230360DR | 2024-07-10 08:00 |  |  | In Progress
Minas | P_4A-44 | Minas 02025 | 4A-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220527DR | 2022-10-29 | 2022-10-29 | 2022-11-13 20:00 | Complete
Minas | P_7D-91N | Minas 02031 | 7D-91N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220346DR | 2022-11-13 20:00 | 2022-12-12 10:00 | 2022-12-31 14:00 | Complete
Minas | P_6F-82 | Minas 02039 | 6F-82 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220454DR | 2022-12-31 14:00 | 2023-01-07 04:00 | 2023-01-20 02:00 | Complete
Minas | P_7E-14 | Minas 02041 | 7E-14 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220637DR | 2023-01-20 02:00 | 2023-01-25 16:00 | 2023-02-12 05:00 | Release
Minas | MNS-P07 | Minas 02045 | 9D-79N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220632DR | 2023-02-12 05:00 | 2023-02-26 04:00 | 2023-03-18 05:00 | Complete
Minas | P_8E-77N | Minas 02051 | 8E-77N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220643DR | 2023-03-18 05:00 | 2023-03-27 14:30 | 2023-04-10 08:30 | Complete
Minas | P_5C-57N | Minas 02057 | 5C-57N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230212DR | 2023-04-10 08:30 | 2023-04-18 20:30 | 2023-05-02 05:00 | Complete
Minas | P_6D-64N | Minas 02061 | 6D-64N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220652DR | 2023-05-02 05:00 | 2023-05-09 01:30 | 2023-05-18 18:30 | Complete
Minas | P_5C-57 | Minas 02066 | 5C-57 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230213DR | 2023-05-18 18:30 | 2023-05-25 20:00 | 2023-06-09 | Complete
Minas | P_5E-64N | Minas 02071 | 5E-64N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230230DR | 2023-06-09 | 2023-06-21 03:00 | 2023-06-30 06:30 | Release
Minas | P_4C-35E | Minas 02074 | 4C-35E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230220DR | 2023-06-30 06:30 | 2023-07-07 11:00 | 2023-07-17 17:00 | Release
Minas | P_4C-45N1 | Minas 02079 | 4C-45N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230225DR | 2023-07-17 17:00 | 2023-07-20 19:00 | 2023-07-29 21:00 | Release
Minas | P_4C-46 | Minas 02080 | 4C-46 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230222DR | 2023-07-29 21:00 | 2023-08-01 23:00 | 2023-08-13 17:00 | Complete
Minas | P_6B-24E | Minas 02087 | 6B-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230236DR | 2023-08-13 17:00 | 2023-08-20 17:00 | 2023-08-31 12:30 | Complete
Minas | P_MINA24_7E-67 | Minas 02091 | 7E-67 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230498DR | 2023-08-31 12:30 | 2023-09-10 03:00 | 2023-09-23 05:00 | Complete
Minas | P_MINA24_7E-67E | Minas 02092 | 7E-67E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230499DR | 2023-09-23 05:00 | 2023-09-26 08:00 | 2023-10-05 22:00 | Complete
Minas | P_8D-66N1 | Minas 02098 | 8D-66N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230536DR | 2023-10-05 22:00 | 2023-10-09 19:00 | 2023-10-20 08:00 | Complete
Minas | P_MINA24_8C-79E | Minas 02101 | 8C-79E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230511DR | 2023-10-20 08:00 | 2023-10-23 21:00 | 2023-11-02 04:00 | Complete
Minas | P_5D-93E | Minas 02104 | 5D-93E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230240DR | 2023-11-02 04:00 | 2023-11-06 18:00 | 2023-11-15 23:59 | Complete
Minas | P_6D-18E | Minas 02107 | 6D-18E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230243DR | 2023-11-16 | 2023-11-19 08:00 | 2023-11-29 13:00 | Complete
Minas | P_MINA24_5C-27N | Minas 02110 | 5C-27N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230494DR | 2023-11-29 13:00 | 2023-12-06 20:00 | 2023-12-18 21:30 | Complete
Minas | P_8E-42E | Minas 02113 | 8E-42E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230235DR | 2023-12-18 21:30 | 2024-01-13 03:30 | 2024-01-24 04:00 | Complete
Bangko | P_BNKO24_P01 | Bangko 00437 | N1-W2-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230597DR | 2024-01-24 04:00 | 2024-02-12 07:00 | 2024-03-02 10:00 | Complete
Balam So | P_BLSO24_LQR_P15 | Balam So 00590 | O-W1-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSE2/402/3240398DR | 2024-03-02 10:00 | 2024-03-10 07:30 | 2024-03-19 23:00 | Complete
Bangko | P_BNKO24_P04 | Bangko 00439 | S1-E1-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230599DR | 2024-03-19 23:00 | 2024-03-27 10:00 | 2024-04-11 04:00 | Complete
Minas | P_MINA24_2D-96N | Minas 02125 | 2D-96N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230490DR | 2024-04-11 04:00 |  | 2024-04-24 | Suspended
Minas | P_MINA24_4E-95 | Minas 02126 | 4E-95 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230519DR | 2024-04-24 | 2024-05-07 10:00 | 2024-05-22 13:00 | Complete
Minas | P_MINA24_3D-91N | Minas 02130 | 3D-91N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230513DR | 2024-05-22 13:00 | 2024-06-04 04:00 | 2024-06-14 16:30 | Complete
Minas | P_MINA24_8D-23N1 | Minas 02115 | 8D-23N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230502DR | 2024-06-14 16:30 | 2024-06-29 11:00 | 2024-07-14 17:00 | Complete
Minas | P_MINA24_6D-43E | Minas 02133 | 6D-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230518DR | 2024-07-14 17:00 |  |  | In Progress
Petapahan | PTP BL2-P19 | Petapahan 00162 | N1-W1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220660DR | 2022-12-31 23:00 | 2022-12-31 23:00 | 2023-01-25 13:00 | Release
Petapahan | PTP BL2-P24 | Petapahan 00164 | N1-W1-42 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220436DR | 2023-01-25 13:00 | 2023-02-05 02:00 | 2023-03-16 13:00 | Complete
Kotabatak | KB_PL44 | Kotabatak 00520 | N1-W1-41 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220392DR | 2023-03-16 13:00 | 2023-03-31 05:00 | 2023-04-17 09:00 | Release
Kotabatak | KB_PL39 | Kotabatak 00521 | N1-W1-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220393DR | 2023-04-17 09:00 | 2023-04-25 | 2023-05-19 10:00 | Release
Kotabatak | KTB-X35-INJ | Kotabatak 00533 | N1-O-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220455DR | 2023-05-19 10:00 | 2023-05-31 21:00 | 2023-06-15 15:00 | Complete
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220628DR | 2023-06-15 15:00 | 2023-06-18 16:30 | 2023-07-03 05:00 | Complete
Kotabatak | KB_PL33 Inj | Kotabatak 00522 | N1-W1-64 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220424DR | 2023-07-03 05:00 | 2023-07-10 15:00 | 2023-07-23 16:00 | Complete
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220623DR | 2023-07-23 16:00 | 2023-07-27 17:30 | 2023-08-10 15:00 | Complete
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSE2/402/3230394DR | 2023-08-10 15:00 | 2023-08-16 21:00 | 2023-08-30 02:00 | Complete
Kotabatak | KB_PL38 | Kotabatak 00542 | O-O-73 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230429DR | 2023-08-30 02:00 | 2023-09-01 21:00 | 2023-09-15 19:30 | Complete
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSE2/402/3230397DR | 2023-09-15 19:30 | 2023-09-19 15:30 | 2023-10-02 08:00 | Complete
Kotabatak | KTB-A223 | Kotabatak 00544 | O-E1-51 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230412DR | 2023-10-02 08:00 | 2023-10-04 18:00 | 2023-10-18 04:00 | Complete
Kotabatak | KB_PL41 | Kotabatak 00545 | O-E1-80 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230410DR | 2023-10-18 04:00 | 2023-10-21 13:00 | 2023-11-10 20:00 | Complete
Kotabatak | KTB-A005 | Kotabatak 00548 | O-W1-40 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230407DR | 2023-11-10 20:00 | 2023-11-16 16:00 | 2023-11-28 21:30 | Release
Kotabatak | KTB-A010 | Kotabatak 00549 | O-W1-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230417DR | 2023-11-28 21:30 | 2023-12-03 12:00 | 2023-12-21 06:30 | Release
Kotabatak | KTB-A146_INJ | Kotabatak 00550 | O-W1-45 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230432DR | 2023-12-21 06:30 | 2024-01-13 17:00 | 2024-01-27 11:30 | Complete
Kotabatak | KTB-A232_INJ | Kotabatak 00551 | O-E1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230437DR | 2024-01-27 11:30 | 2024-02-10 16:00 | 2024-02-27 14:00 | Complete
Kotabatak | KTB-A254 | Kotabatak 00552 | O-O-27 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230414DR | 2024-02-27 14:00 | 2024-03-02 18:00 | 2024-03-14 08:00 | Complete
Kotabatak | KTB-A268_INJ | Kotabatak 00553 | N1-W1-15B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230438DR | 2024-03-14 08:00 | 2024-03-20 21:00 | 2024-04-01 | Complete
Kotabatak | KTB-A125 | Kotabatak 00554 | O-E1-79 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230421DR | 2024-04-01 | 2024-04-07 16:00 | 2024-04-19 02:00 | Complete
Kotabatak | KTB-A207_INJ | Kotabatak 00555 | O-E1-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230436DR | 2024-04-19 02:00 | 2024-04-22 11:00 | 2024-05-03 06:00 | Complete
Kotabatak | KTB-A235 | Kotabatak 00557 | O-E1-14 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230423DR | 2024-05-03 06:00 | 2024-05-10 15:00 | 2024-05-31 07:00 | Release
Kotabatak | KTB-A264 | Kotabatak 00558 | N1-W1-23 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230427DR | 2024-05-31 07:00 | 2024-06-05 22:30 | 2024-06-22 21:00 | Release
Kotabatak | KTB-A250 | Kotabatak 00559 | N1-W1-43 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230413DR | 2024-06-22 21:00 | 2024-06-26 14:00 | 2024-07-09 10:00 | Release
Kotabatak | KTB-A052 | Kotabatak 00560 | N1-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230409DR | 2024-07-09 10:00 | 2024-07-14 07:00 |  | In Progress
Pungut | PUNG21_P04 | Pungut 00048 | S2-E1-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210134DR | 2021-09-07 18:00 | 2021-09-07 18:00 | 2021-09-23 14:00 | Complete
Pungut | PUNG21_P03 | Pungut 00049 | S1-O-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210133DR | 2021-09-23 14:00 | 2021-09-30 21:00 | 2021-10-19 | Complete
Bekasap | BKS-P17 | Bekasap 00199 | S1-O-14D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210011DR | 2021-10-19 | 2021-10-27 14:30 | 2021-11-06 14:00 | Complete
Bekasap | BKS-P15 | Bekasap 00202 | O-O-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210009DR | 2021-11-06 14:00 | 2021-11-10 14:00 | 2021-11-21 | Complete
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210008DR | 2021-11-21 | 2021-11-26 04:00 | 2021-12-08 19:00 | Release
Bekasap | BKS-P4 | Bekasap 00206 | O-O-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210016DR | 2021-12-08 19:00 | 2022-01-08 20:15 | 2022-01-18 15:00 | Complete
Bekasap | BKS-P11 | Bekasap 00210 | S1-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210005DR | 2022-01-18 15:00 | 2022-01-23 22:30 | 2022-02-06 | Complete
Bekasap | BKS-P1 | Bekasap 00212 | O-E1-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220080DR | 2022-02-06 | 2022-02-11 03:30 | 2022-02-21 15:00 | Complete
Bekasap | BKS-P8 | Bekasap 00213 | O-E1-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220081DR | 2022-02-21 15:00 | 2022-02-24 19:15 | 2022-03-07 10:00 | Complete
Bekasap | BKS-X15 | Bekasap 00215 | O-E1-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220085DR | 2022-03-07 10:00 | 2022-03-13 16:00 | 2022-03-26 20:00 | Complete
Bekasap | BKS-X08 | Bekasap 00217 | S1–O–35A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220084DR | 2022-03-26 20:00 | 2022-03-31 03:00 | 2022-04-13 15:00 | Complete
Bangko | BNK-P4 | Bangko 00380 | N1-W1-11B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210069DR | 2022-04-13 15:00 | 2022-04-21 01:30 | 2022-05-03 | Complete
Bangko | BNK-P6 | Bangko 00377 | N1-W2-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220065DR | 2022-05-03 | 2022-05-08 15:00 | 2022-05-28 | Release
Bangko | BNK-X01 | Bangko 00387 | O-O-21B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220067DR | 2022-05-28 | 2022-06-02 08:00 | 2022-06-16 08:00 | Release
Bangko | BNK-X02 | Bangko 00389 | O-O-21C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220069DR | 2022-06-16 08:00 | 2022-06-20 10:30 | 2022-07-04 | Complete
Bangko | BNK-X06 | Bangko 00395 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220077DR | 2022-07-04 | 2022-07-10 18:30 | 2022-07-23 10:00 | Complete
Bangko | BNK-X07 | Bangko 00397 | O-O-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220079DR | 2022-07-23 10:00 | 2022-07-28 18:00 | 2022-08-09 01:30 | Complete
Bangko | BNK-X04 | Bangko 00391 | O-O-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220504DR | 2022-08-09 01:30 | 2022-08-14 01:00 | 2022-08-26 02:00 | Complete
Bangko | BNK-X05 | Bangko 00393 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220516DR | 2022-08-25 02:00 | 2022-08-30 13:00 | 2022-09-10 14:00 | Complete
Bangko | BNK_P5A_LQR | Bangko 00415 | N2-W1-85A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220389DR | 2022-09-10 14:00 | 2022-09-15 16:00 | 2022-09-25 10:00 | Complete
Balam So | BLSO-P45 | Balam So 00497 | O-W1-15F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220321DR | 2022-09-25 10:00 | 2022-10-11 16:00 | 2022-10-24 20:30 | Complete
Balam So | BLSO-P46 | Balam So 00502 | N1-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220341DR | 2022-10-24 20:30 | 2022-10-31 | 2022-11-07 12:00 | Release
Balam So | BLSO-P38 | Balam So 00505 | N1-O-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220361DR | 2022-11-07 12:00 | 2022-11-15 12:00 | 2022-11-29 22:00 | Complete
Balam So | BLSO23-P13 | Balam So 00511 | O-O-34E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220593DR | 2022-11-28 22:00 | 2022-12-06 03:00 | 2022-12-20 | Complete
Balam So | BLSO23-P12 | Balam So 00514 | O-O-34F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220595DR | 2022-12-20 | 2022-12-24 21:00 | 2023-01-06 | Complete
Balam So | BLSO23-P04 | Balam So 00516 | O-O-36D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220589DR | 2023-01-06 | 2023-01-10 16:30 | 2023-01-18 21:00 | Complete
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220372DR | 2023-01-18 21:00 | 2023-01-25 10:00 | 2023-01-30 17:00 | Release
Balam So | BLSO23-LQR-TE025 | Balam So 00520 | O-W1-24C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220429DR | 2023-01-30 17:00 | 2023-02-06 16:00 | 2023-02-25 | Complete
Balam So | BLSO23-LQR-TE062 | Balam So 00521 | O-O-64B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220396DR | 2023-02-25 | 2023-03-04 | 2023-03-12 08:00 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220548DR | 2023-03-12 08:00 | 2023-03-16 10:00 | 2023-03-21 15:45 | Complete
Balam So | BLSO23-LQR-TE037 | Balam So 00523 | O-O-34G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220453DR | 2023-03-21 15:45 | 2023-03-27 13:00 | 2023-04-04 04:00 | Complete
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230364DR | 2023-04-04 04:00 | 2023-04-09 12:00 | 2023-04-14 18:00 | Complete
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220588DR | 2023-04-14 18:00 | 2023-04-18 12:00 | 2023-04-23 07:00 | Complete
Balam So | BLSO23-P02 | Balam So 00527 | N1-W1-74G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220594DR | 2023-04-23 07:00 | 2023-04-29 23:00 | 2023-05-07 17:30 | Complete
Balam So | BLSO23-P03 | Balam So 00529 | N1-W1-74H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220597DR | 2023-05-07 17:30 | 2023-05-10 20:30 | 2023-05-19 02:00 | Complete
Balam So | LQR-TE089_BLSO_2 | Balam So 00530 | O-O-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220550DR | 2023-05-19 02:00 | 2023-05-23 03:00 | 2023-05-30 15:00 | Complete
Balam So | BLSO23-LQR-TE040 | Balam So 00531 | N1-W1-34A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220586DR | 2023-05-30 15:00 | 2023-06-03 15:00 | 2023-06-09 12:30 | Complete
Balam So | BLSO23-P05 | Balam So 00533 | O-O-45B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220598DR | 2023-06-09 14:30 | 2023-06-13 13:30 | 2023-06-21 08:00 | Complete
Balam So | BLSO23-P08 | Balam So 00534 | O-O-45C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220603DR | 2023-06-21 08:00 | 2023-06-24 | 2023-07-02 | Complete
Balam So | LQR-TE155_BLSO_7 | Balam So 00538 | O-O-56D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220549DR | 2023-07-02 | 2023-07-13 23:00 | 2023-07-26 09:00 | Complete
Balam So | BLSO23-LQR-TE042 | Balam So 00539 | O-O-77B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230349DR | 2023-07-26 09:00 | 2023-07-30 01:00 | 2023-08-04 05:00 | Complete
Balam So | BLSO23-LQR-TE030 | Balam So 00543 | N1-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230332DR | 2023-08-04 05:00 | 2023-08-09 01:30 | 2023-08-14 02:00 | Complete
Balam So | BLSO23-P16 | Balam So 00544 | O-O-56E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220602DR | 2023-08-14 02:00 | 2023-08-18 11:00 | 2023-08-25 21:00 | Complete
Balam So | BLSO23-LQR-TE048 | Balam So 00547 | N1-W1-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230357DR | 2023-08-25 21:00 | 2023-08-30 10:00 | 2023-09-07 | Complete
Bangko | BNK23_P22 | Bangko 00425 | N1-W2-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230289DR | 2023-09-07 | 2023-09-14 17:00 | 2023-09-28 18:00 | Complete
Bangko | BNK23_P23 | Bangko 00428 | O-O-21D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230290DR | 2023-09-28 18:00 | 2023-10-02 17:00 | 2023-10-17 16:00 | Complete
Bangko | BNK23_P09 | Bangko 00433 | O-O-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230272DR | 2023-10-17 16:00 | 2023-10-21 02:30 | 2023-11-01 19:00 | Complete
Balam So | LQR-TE200_BLSO_5 | Balam So 00562 | O-O-23I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230330DR | 2023-11-01 19:00 | 2023-11-08 06:30 | 2023-11-15 14:00 | Complete
Balam So | P_BLSO24_LQR05 | Balam So 00564 | N1-W1-67D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230344DR | 2023-11-15 14:00 | 2023-11-20 05:00 | 2023-11-27 | Complete
Balam So | BLSO23-LQR-TE032 | Balam So 00565 | N1-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230340DR | 2023-11-27 | 2023-12-16 17:00 | 2023-12-26 | Complete
Balam So | BLSO23-LQR-TE055 | Balam So 00566 | N1-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230341DR | 2023-12-26 | 2023-12-30 14:15 | 2024-01-07 03:00 | Complete
Balam So | BLSO23-LQR-TE027 | Balam So 00574 | N1-W1-87B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230370DR | 2024-01-07 03:00 | 2024-01-12 18:00 | 2024-01-19 14:00 | Complete
Balam So | BLSO23-P14 | Balam So 00575 | N1-W1-87C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220600DR | 2024-01-19 14:00 | 2024-01-21 22:00 | 2024-01-29 05:00 | Complete
Balam So | BLSO-P09 | Balam So 00583 | N1-O-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220447DR | 2024-01-29 05:00 | 2024-02-07 05:00 | 2024-02-14 06:00 | Complete
Balam So | P_BLSO24_LQR07 | Balam So 00589 | N1-W1-73G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230361DR | 2024-02-14 06:00 | 2024-02-23 06:00 | 2024-03-02 06:00 | Complete
Balam So | LQR-TE213_BLSO_46 | Balam So 00584 | N1-W1-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230376DR | 2024-03-02 06:00 | 2024-03-09 13:30 | 2024-03-18 | Complete
Balam So | P_BLSO24_LQR10 | Balam So 00585 | N1-W1-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230363DR | 2024-03-18 | 2024-03-20 13:00 | 2024-03-27 16:30 | Complete
Balam So | BLSO23-LQR-TE067 | Balam So 00586 | N1-W1-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230338DR | 2024-03-27 16:30 | 2024-03-31 21:00 | 2024-04-08 09:00 | Complete
Minas | MINA21_P01 | Minas 01984 | 4C-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210118DR | 2021-09-22 | 2021-09-22 | 2021-10-15 21:30 | Complete
Minas | MINA21_P02 | Minas 01985 | 2D-72E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210119DR | 2021-10-15 21:30 | 2021-10-31 21:15 | 2021-11-13 05:00 | Complete
Minas | MNS-P5 | Minas 01986 | 8E-52N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210112DR | 2021-11-13 05:00 | 2021-11-21 04:00 | 2021-12-04 03:30 | Complete
Minas | MNS-P2 | Minas 01987 | 8D-18N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/2210020DR | 2021-12-04 03:30 | 2021-12-28 12:00 | 2022-01-14 13:00 | Complete
Minas | MNS-P6 | Minas 01989 | 8E-32N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210105DR | 2022-01-14 13:00 | 2022-01-19 12:30 | 2022-02-05 | Complete
Minas | MNS-P10 | Minas 01992 | 8E-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210108DR | 2022-02-05 | 2022-02-13 18:30 | 2022-03-12 13:00 | Release
Minas | MNS-P1 | Minas 01995 | 8D-48S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220204DR | 2022-03-12 13:00 | 2022-03-20 15:30 | 2022-03-30 10:30 | Release
Minas | MNS-P13 | Minas 01997 | 8D-57N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220201DR | 2022-03-30 10:30 | 2022-04-04 19:00 | 2022-04-15 18:00 | Complete
Minas | MNS-P06 | Minas 01998 | 7E-56N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220213DR | 2022-04-14 18:00 | 2022-04-20 05:00 | 2022-05-01 12:30 | Complete
Minas | MNA-P11 | Minas 02002 | 8D-49N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220217DR | 2022-05-01 12:30 | 2022-05-06 12:00 | 2022-05-17 12:30 | Complete
Minas | MNS-P01 | Minas 02007 | 8E-94E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220209DR | 2022-05-17 12:30 | 2022-05-23 03:30 | 2022-06-06 | Complete
Minas | P_7D-17N | Minas 02009 | 7D-17N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220225DR | 2022-06-06 | 2022-06-11 04:00 | 2022-06-21 15:00 | Complete
Minas | P_7D-53N | Minas 02010 | 7D-53N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220228DR | 2022-06-21 15:00 | 2022-06-27 06:00 | 2022-07-07 08:00 | Complete
Minas | MNS-P12_1 | Minas 02013 | 8C-88N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220211DR | 2022-07-07 08:00 | 2022-07-16 04:00 | 2022-07-25 09:30 | Complete
Minas | P_6E-73E | Minas 02016 | 6E-73E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220223DR | 2022-07-25 09:30 | 2022-07-31 | 2022-08-09 02:45 | Complete
Minas | P_7D-48N | Minas 02019 | 7D-48N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220319DR | 2022-08-09 02:45 | 2022-08-14 02:30 | 2022-09-12 | Complete
Minas | P_6C-11E | Minas 02022 | 6C-11E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220531DR | 2022-09-12 | 2022-09-19 04:30 | 2022-10-03 06:00 | Complete
Minas | P_4D-58N | Minas 02024 | 4D-58N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220337DR | 2022-10-03 06:00 | 2022-10-15 12:00 | 2022-11-06 15:00 | Complete
Minas | P_3C-87 | Minas 02028 | 3C-87 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220405DR | 2022-11-06 15:00 | 2022-11-15 18:00 | 2022-11-27 01:30 | Complete
Minas | P_4C-14E | Minas 02029 | 4C-14E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220382DR | 2022-11-27 01:30 | 2022-12-02 17:15 | 2022-12-15 12:00 | Release
Minas | P_6D-53N | Minas 02033 | 6D-53N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220350DR | 2022-12-15 12:00 | 2022-12-27 08:30 | 2023-01-07 08:00 | Release
Minas | P_1E-72 | Minas 02038 | 1E-72 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220641DR | 2023-01-07 08:00 | 2023-01-17 05:30 | 2023-02-04 | Complete
Minas | P_7C-37E | Minas 02040 | 7C-37E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220642DR | 2023-02-04 | 2023-02-21 08:00 | 2023-03-04 18:00 | Complete
Minas | P_5B-77E | Minas 02043 | 5B-77E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220656DR | 2023-03-04 18:00 | 2023-03-13 06:00 | 2023-03-29 02:00 | Complete
Minas | P_8C-66E | Minas 02053 | 8C-66E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220639DR | 2023-03-29 02:00 | 2023-04-08 03:00 | 2023-04-19 | Complete
Minas | P_9E-11N | Minas 02048 | 9E-11N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230210DR | 2023-04-19 | 2023-04-27 04:00 | 2023-05-11 22:00 | Complete
Minas | P_9E-21N | Minas 02049 | 9E-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220654DR | 2023-05-11 22:00 | 2023-05-16 22:00 | 2023-05-25 17:00 | Complete
Minas | P_5C-59 | Minas 02067 | 5C-59 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230215DR | 2023-05-25 17:00 | 2023-06-02 08:00 | 2023-06-14 16:00 | Complete
Minas | P_4D-38E | Minas 02070 | 4D-38E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220640DR | 2023-06-14 16:00 | 2023-06-22 08:00 | 2023-07-02 06:30 | Complete
Minas | P_5D-14E1 | Minas 02077 | 5D-14E1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220648DR | 2023-07-02 06:30 | 2023-07-08 14:00 | 2023-07-17 04:00 | Complete
Minas | P_7D-23N | Minas 02078 | 7D-23N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230247DR | 2023-07-17 04:00 | 2023-07-23 14:00 | 2023-08-04 05:00 | Complete
Minas | P_3D-79N | Minas 02083 | 3D-79N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220653DR | 2023-08-04 05:00 | 2023-08-13 | 2023-08-22 18:00 | Complete
Minas | P_6D-11E1 | Minas 02086 | 6D-11E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230231DR | 2023-08-22 18:00 | 2023-08-28 11:00 | 2023-09-05 13:30 | Complete
Bangko | BNK_P88B_LQR | Bangko 00426 | O-W2-26B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220457DR | 2023-09-05 13:30 | 2023-09-17 14:00 | 2023-09-25 10:30 | Complete
Bangko | BNK23_P08 | Bangko 00430 | O-O-52B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230275DR | 2023-09-25 10:30 | 2023-09-29 18:00 | 2023-10-17 16:30 | Complete
Bangko | WFE-BNK_6 | Bangko 00432 | N2-W1-82A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230287DR | 2023-10-17 16:30 | 2023-10-22 13:00 | 2023-11-01 | Complete
Bangko | BNK23_P11 | Bangko 00435 | N1-W2-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230269DR | 2023-11-01 | 2023-11-05 15:00 | 2023-11-15 13:00 | Complete
Balam So | BLSO23-LQR-TE056 | Balam So 00560 | N1-O-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230359DR | 2023-11-15 13:00 | 2023-11-23 13:00 | 2023-11-29 23:00 | Complete
Balam So | P_BLSO24_LQR01 | Balam So 00568 | O-W1-24D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230323DR | 2023-11-29 23:00 | 2023-12-12 13:00 | 2023-12-19 | Complete
Balam So | BLSO23-P07 | Balam So 00571 | N1-W1-63H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220599DR | 2023-12-19 | 2023-12-24 10:00 | 2023-12-31 14:30 | Complete
Balam So | P_BLSO24_LQR04 | Balam So 00572 | O-W1-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230346DR | 2023-12-31 14:30 | 2024-01-15 22:00 | 2024-01-22 07:30 | Complete
Bangko | P_BNKO24_P02 | Bangko 00438 | S1-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230598DR | 2024-01-22 07:30 | 2024-01-31 11:30 | 2024-02-11 18:30 | Complete
Balam So | LQR-TE011_BLSO_33 | Balam So 00588 | N1-W1-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230331DR | 2024-02-11 18:30 | 2024-02-16 19:00 | 2024-02-24 | Complete
Balam Se | P_BLSE24_P03 | Balam Se 00040 | O-O-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3240647DR | 2024-02-24 | 2024-03-04 18:00 | 2024-03-30 07:30 | Release
Duri | P_3L44D | Duri 10852 | 3L-44D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210093DR | 2021-08-04 15:30 | 2021-08-06 05:00 | 2021-08-11 15:00 | Complete
Duri | P_3K49C | Duri 10853 | 3K-49C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210024DR | 2021-08-11 15:00 | 2021-08-13 20:30 | 2021-08-18 09:00 | Complete
Duri | P_4K50D | Duri 10854 | 4K-50D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/3210155DR | 2021-08-18 09:00 | 2021-08-19 22:00 | 2021-08-24 12:00 | Complete
Duri | P_3F0108B | Duri 10859 | 3F-0108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210022DR | 2021-08-24 12:00 | 2021-08-25 22:00 | 2021-08-29 18:00 | Complete
Duri | P_3E1009B | Duri 10860 | 3E-1009B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210023DR | 2021-08-29 18:00 | 2021-08-31 19:00 | 2021-09-04 15:00 | Complete
Duri | 6G-0501B | Duri 10865 | 6G-0501B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210086DR | 2021-09-04 15:00 | 2021-09-06 01:30 | 2021-09-10 11:00 | Complete
Duri | 6G-0303B | Duri 10866 | 6G-0303B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210087DR | 2021-09-10 11:00 | 2021-09-11 23:00 | 2021-09-16 09:00 | Complete
Duri | 6F-0802B | Duri 10870 | 6F-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210083DR | 2021-09-16 09:00 | 2021-09-17 20:00 | 2021-09-22 06:00 | Complete
Duri | 6G-0802B | Duri 10871 | 6G-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210084DR | 2021-09-22 06:00 | 2021-09-23 15:00 | 2021-09-27 21:00 | Complete
Duri | 6F-0702B | Duri 10874 | 6F-0702B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210031DR | 2021-09-27 21:00 | 2021-09-30 14:30 | 2021-10-05 07:00 | Complete
Duri | 6F-0801B | Duri 10875 | 6F-0801B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210033DR | 2021-10-05 07:00 | 2021-10-06 19:00 | 2021-10-11 07:00 | Complete
Duri | 5F-0309B | Duri 10878 | 5F-0309B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210035DR | 2021-10-11 07:00 | 2021-10-12 20:00 | 2021-10-17 07:00 | Complete
Duri | 5F-1007B | Duri 10879 | 5F-1007B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210045DR | 2021-10-17 07:00 | 2021-10-18 21:00 | 2021-10-23 09:15 | Complete
Duri | 6F-1203B | Duri 10882 | 6F-1203B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210051DR | 2021-10-23 09:15 | 2021-10-26 09:30 | 2021-10-31 09:30 | Complete
Duri | 6G-0601B | Duri 10883 | 6G-0601B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210082DR | 2021-10-31 10:00 | 2021-11-03 02:30 | 2021-11-07 14:00 | Complete
Duri | 5G-0412C | Duri 10887 | 5G-0412C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210007DR | 2021-11-07 14:00 | 2021-11-10 03:00 | 2021-11-14 18:15 | Complete
Duri | 6G-1002B | Duri 10891 | 6G-1002B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210085DR | 2021-11-14 18:15 | 2021-11-17 10:30 | 2021-11-22 | Complete
Duri | 5G-0412B | Duri 10888 | 5G-0412B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210010DR | 2021-11-22 | 2021-11-24 | 2021-11-28 15:30 | Complete
Duri | 6G-0402B | Duri 10892 | 6G-0402B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210013DR | 2021-11-28 15:30 | 2021-11-30 15:30 | 2021-12-06 | Complete
Duri | 5G-0209B | Duri 10895 | 5G-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210021DR | 2021-12-06 | 2021-12-08 11:30 | 2021-12-12 17:30 | Complete
Duri | 5F-0612C | Duri 10896 | 5F-0612C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210076DR | 2021-12-12 17:30 | 2021-12-25 10:00 | 2021-12-29 15:15 | Complete
Duri | 4V-28C | Duri 10899 | 4V-28C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210077DR | 2021-12-29 15:15 | 2022-01-07 | 2022-01-13 16:00 | Complete
Duri | 4V-28D | Duri 10900 | 4V-28D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210078DR | 2022-01-13 16:00 | 2022-01-17 01:00 | 2022-01-23 04:00 | Complete
Duri | 3G-0606B | Duri 10903 | 3G-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220089DR | 2022-01-23 04:00 | 2022-01-30 13:00 | 2022-02-05 03:00 | Complete
Duri | 3H-0201B | Duri 10904 | 3H-0201B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220091DR | 2022-02-05 03:00 | 2022-02-08 21:00 | 2022-02-15 05:30 | Complete
Duri | 3H-0302B | Duri 10907 | 3H-0302B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220093DR | 2022-02-15 05:30 | 2022-02-17 14:00 | 2022-02-22 15:00 | Complete
Duri | 4H-0912B | Duri 10911 | 4H-0912B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220102DR | 2022-02-22 15:00 | 2022-02-25 04:00 | 2022-03-02 01:00 | Complete
Duri | 4H-0913B | Duri 10912 | 4H-0913B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220097DR | 2022-03-02 01:00 | 2022-03-03 23:00 | 2022-03-09 21:00 | Complete
Duri | 6G-0301B | Duri 10923 | 6G-0301B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220112DR | 2022-03-09 21:00 | 2022-03-15 20:00 | 2022-03-20 16:00 | Complete
Duri | 5G-0404B | Duri 10919 | 5G-0404B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220103DR | 2022-03-20 16:00 | 2022-03-23 09:00 | 2022-03-29 | Complete
Duri | 5G-0308C | Duri 10927 | 5G-0308C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220114DR | 2022-03-28 | 2022-03-29 12:00 | 2022-04-02 17:00 | Complete
Duri | 5E-1009C | Duri 10930 | 5E-1009C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220116DR | 2022-04-02 17:00 | 2022-04-05 23:30 | 2022-04-10 14:30 | Complete
Duri | 5E-1110B | Duri 10937 | 5E-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220161DR | 2022-04-10 14:30 | 2022-04-21 06:00 | 2022-04-25 20:30 | Complete
Duri | 5E-1010C | Duri 10940 | 5E-1010C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220152DR | 2022-04-25 20:30 | 2022-04-28 13:00 | 2022-05-03 05:00 | Complete
Duri | 5E-1210B | Duri 10942 | 5E-1210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220160DR | 2022-05-03 05:00 | 2022-05-05 14:00 | 2022-05-10 07:00 | Complete
Duri | 5E-0910B | Duri 10939 | 5E-0910B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220158DR | 2022-05-10 07:00 | 2022-05-13 02:00 | 2022-05-17 20:00 | Complete
Duri | 5F-0210B | Duri 10941 | 5F-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220157DR | 2022-05-17 20:00 | 2022-05-20 07:00 | 2022-05-26 18:00 | Complete
Duri | 5F-0310B | Duri 10949 | 5F-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220159DR | 2022-05-26 18:00 | 2022-05-29 | 2022-06-03 08:00 | Complete
Duri | 5F-0308B | Duri 10947 | 5F-0308B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220136DR | 2022-06-03 08:00 | 2022-06-05 18:00 | 2022-06-12 21:30 | Complete
Duri | 5F-0412B | Duri 10950 | 5F-0412B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220134DR | 2022-06-12 21:30 | 2022-06-15 12:00 | 2022-06-21 07:30 | Complete
Duri | 6F-0501C | Duri 10960 | 6F-0501C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220144DR | 2022-06-21 07:30 | 2022-06-24 23:00 | 2022-06-29 15:00 | Complete
Duri | 5F-0510C | Duri 10956 | 5F-0510C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220154DR | 2022-06-29 15:00 | 2022-06-30 23:30 | 2022-07-05 15:30 | Complete
Duri | 5F-0507C | Duri 10952 | 5F-0507C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220162DR | 2022-07-05 15:30 | 2022-07-07 03:30 | 2022-07-11 12:30 | Complete
Duri | 4I-0312B | Duri 10968 | 4I-0312B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220121DR | 2022-07-11 12:30 | 2022-07-13 23:00 | 2022-07-18 02:15 | Complete
Duri | 5F-0606B | Duri 10962 | 5F-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220148DR | 2022-07-18 02:15 | 2022-07-20 03:00 | 2022-07-24 12:00 | Complete
Petani | Petani P01 | Petani 00130 | O-O-76B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-3516 | GRK2/402/2210139DR | 2021-11-02 02:30 | 2021-11-06 02:30 | 2021-11-15 09:30 | Complete
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | APS-3523 | GRK2/402/2210034DR | 2021-09-29 03:30 | 2021-09-30 20:30 | 2021-10-04 22:30 | Complete
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-3523 | GRK2/402/2210065DR | 2022-03-24 11:00 | 2022-03-25 18:00 | 2022-03-29 11:00 | Complete
Balam So | BLSO-P02 | Balam So 00459 | O-O-36C | Perforation - Re-perforation | PRF04 - Perforation - Re-Perforation | Land Workover Unit | APS-3523 | GRK2/402/2220004DR | 2022-07-16 02:00 | 2022-07-17 14:00 | 2022-07-24 13:00 | Complete
Balam So | BLSO-P16 | Balam So 00454 | O-O-36B | Perforation - Re-perforation | PRF04 - Perforation - Re-Perforation | Land Workover Unit | APS-3523 | GRK2/402/2220009DR | 2022-07-24 13:00 | 2022-07-25 17:30 | 2022-07-28 19:00 | Complete
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220010DR | 2022-04-19 | 2022-04-22 15:30 | 2022-04-26 09:30 | Complete
Balam So | BLSO-P31 | Balam So 00455 | S1-O-45C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220023DR | 2022-05-04 14:00 | 2022-05-05 09:00 | 2022-05-13 | Complete
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220028DR | 2022-05-17 16:30 | 2022-05-18 16:30 | 2022-06-02 | Complete
Balam So | BLSO-P17 | Balam So 00472 | O-O-35G | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220025DR | 2022-06-26 22:00 | 2022-06-28 | 2022-07-04 21:00 | Complete
Balam So | BLSO-P23 | Balam So 00470 | N1-W1-84A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220022DR | 2022-07-04 21:00 | 2022-07-06 09:00 | 2022-07-16 | Complete
Balam So | BLSO-P26 | Balam So 00462 | N1-W1-67C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220024DR | 2022-08-03 21:30 | 2022-08-05 06:00 | 2022-08-06 12:00 | Complete
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210093DR | 2021-08-07 20:30 | 2021-08-07 20:30 | 2021-09-07 14:00 | Complete
Bangko | Bangko P29 | Bangko 00347 | O-W1-78A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210032DR | 2021-09-07 14:00 | 2021-09-19 12:00 | 2021-10-03 | Complete
Tilan | Tilan P02 | Tilan 00033 | O-O-27F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210165DR | 2021-10-03 | 2021-10-16 12:00 | 2021-11-21 09:00 | Complete
Tilan | Tilan P01 | Tilan 00034 | O-O-44C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210166DR | 2021-11-21 09:00 | 2021-11-29 08:45 | 2021-12-31 02:30 | Complete
Pager | PG-P2 | Pager 00048 | O-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210130DR | 2021-12-31 02:30 | 2022-01-14 10:00 | 2022-01-31 18:00 | Complete
Pager | PG-P1 | Pager 00049 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210129DR | 2022-01-31 18:00 | 2022-02-05 16:00 | 2022-03-02 09:00 | Complete
Pager | PG-P3 | Pager 00050 | O-O-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220238DR | 2022-03-02 09:00 | 2022-03-15 02:00 | 2022-04-01 06:00 | Complete
Petani | PETA22-P14 | Petani 00142 | S1-O-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220258DR | 2022-04-01 06:00 | 2022-04-09 | 2022-04-29 04:00 | Complete
Petani | PTN-X11 | Petani 00144 | S1-O-26C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220250DR | 2022-04-29 04:00 | 2022-05-07 22:00 | 2022-05-26 | Release
Hitam | Hitam P07 | Hitam 00012 | N1-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220163DR | 2022-05-26 | 2022-06-06 22:30 | 2022-07-03 16:00 | Complete
Kotabatak | KB_PL4 | Kotabatak 00487 | O-W2-17 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220253DR | 2022-07-03 16:00 | 2022-07-18 13:00 | 2022-08-01 13:00 | Complete
Kotabatak | KB_PL5 Inj | Kotabatak 00490 | N1-W2-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/3220191DR | 2022-08-01 13:00 | 2022-08-05 19:30 | 2022-08-16 12:00 | Release
Kotabatak | KTB-X08 | Kotabatak 00493 | N1-W2-59 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220513DR | 2022-08-16 12:00 | 2022-08-21 20:00 | 2022-09-02 10:00 | Complete
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220522DR | 2022-09-02 10:00 | 2022-09-07 18:00 | 2022-09-20 13:00 | Complete
Kotabatak | KB_PL12 | Kotabatak 00496 | S1-O-22 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220345DR | 2022-09-20 13:00 | 2022-10-03 03:30 | 2022-10-13 17:00 | Complete
Kotabatak | KB_PL19 | Kotabatak 00499 | S1-O-19 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220367DR | 2022-10-13 17:00 | 2022-10-19 12:00 | 2022-10-31 17:00 | Complete
Kotabatak | KB_PL47 Inj | Kotabatak 00501 | N1-W2-36 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220537DR | 2022-10-31 17:00 | 2022-11-07 19:00 | 2022-11-21 10:00 | Release
Kotabatak | KTB-P1 | Kotabatak 00503 | S2-O-25 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220446DR | 2022-11-21 10:00 | 2022-11-28 22:00 | 2022-12-25 15:00 | Release
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220625DR | 2022-12-25 15:00 | 2023-01-03 16:30 | 2023-01-15 15:30 | Complete
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220627DR | 2023-01-15 15:30 | 2023-01-20 18:00 | 2023-02-01 03:30 | Complete
Kotabatak | KTB-X11 | Kotabatak 00511 | N1-W1-54 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220426DR | 2023-02-01 03:30 | 2023-02-07 11:00 | 2023-02-28 09:00 | Complete
Kotabatak | KTB-X36-INJ | Kotabatak 00513 | N1-W1-37 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220388DR | 2023-02-28 09:00 | 2023-03-06 | 2023-03-23 15:00 | Complete
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230384DR | 2023-03-23 15:00 | 2023-04-02 19:00 | 2023-04-15 11:00 | Complete
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230386DR | 2023-04-15 11:00 | 2023-04-20 17:30 | 2023-05-03 20:00 | Complete
Kotabatak | KTB-A267 | Kotabatak 00519 | N1-W1-49 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230388DR | 2023-05-03 20:00 | 2023-05-10 | 2023-05-20 06:00 | Complete
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230391DR | 2023-05-20 06:00 | 2023-05-26 15:00 | 2023-06-07 10:30 | Complete
Kotabatak | KB_PL17 Inj | Kotabatak 00529 | O-O-11 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230390DR | 2023-06-07 10:30 | 2023-06-10 12:00 | 2023-06-19 14:00 | Complete
Kotabatak | KB_PL13 | Kotabatak 00527 | N1-O-84 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220626DR | 2023-06-19 14:00 | 2023-06-22 19:00 | 2023-07-02 16:30 | Complete
Kotabatak | KTB-X37-INJ | Kotabatak 00528 | S1-W1-47 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230396DR | 2023-07-02 16:30 | 2023-07-08 01:45 | 2023-07-18 21:00 | Complete
Kotabatak | KB_PL9 | Kotabatak 00535 | S1-W1-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230431DR | 2023-07-18 21:00 | 2023-07-22 12:00 | 2023-08-02 22:30 | Complete
Kotabatak | KTB-A198_INJ | Kotabatak 00536 | S1-W1-43 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230434DR | 2023-08-02 22:30 | 2023-08-07 18:00 | 2023-08-20 | Complete
Kotabatak | KTB-A98 | Kotabatak 00537 | S1-W1-42 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230430DR | 2023-08-20 | 2023-08-22 15:30 | 2023-09-03 | Complete
Kotabatak | KTB-A023 | Kotabatak 00546 | O-W1-55 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230418DR | 2023-09-03 | 2023-09-09 | 2023-09-19 14:00 | Complete
Kotabatak | KTB-A185_INJ | Kotabatak 00547 | O-W1-66 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230433DR | 2023-09-19 14:00 | 2023-09-24 14:00 | 2023-10-07 10:00 | Complete
Petapahan | PTPBL3-P9B | Petapahan 00166 | N2-W1-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220878DR | 2023-10-07 10:00 | 2023-10-14 13:30 | 2023-11-03 05:00 | Complete
Petapahan | PTPBL3-P15 | Petapahan 00168 | N2-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220879DR | 2023-11-03 05:00 | 2023-11-08 05:00 | 2023-11-27 07:00 | Complete
Petapahan | PETP21-P09 | Petapahan 00170 | O-O-68 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220877DR | 2023-11-27 07:00 | 2023-12-11 19:30 | 2023-12-25 06:00 | Complete
Petapahan | PTP BL2-P16 | Petapahan 00171 | N1-W1-44D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220880DR | 2023-12-25 06:00 | 2024-01-07 12:00 | 2024-01-26 05:00 | Complete
Petapahan | PTP BL2-Z09 | Petapahan 00172 | N1-W1-44E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220411DR | 2024-01-26 05:00 | 2024-01-26 17:00 | 2024-02-16 16:30 | Complete
Petapahan | P_PETP24_INJ04 | Petapahan 00173 | N2-W1-57A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220882DR | 2024-02-16 16:30 | 2024-03-01 23:30 | 2024-03-19 15:00 | Complete
Petapahan | PTPBL3-P8 | Petapahan 00174 | N2-W1-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220876DR | 2024-03-19 15:00 | 2024-03-23 22:30 | 2024-04-14 | Complete
Kotabatak | KB_PL15 | Kotabatak 00556 | O-E1-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230393DR | 2024-04-14 | 2024-04-22 04:00 | 2024-05-06 12:00 | Complete
Duri | 5F-0609B | Duri 10965 | 5F-0609B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | GRK2/402/2220156DR | 2022-07-24 12:00 | 2022-07-30 08:00 | 2022-08-05 13:15 | Complete
Duri | 6F-0602B | Duri 10967 | 6F-0602B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | GRK2/402/2220141DR | 2022-08-05 13:15 | 2022-08-08 20:00 | 2022-08-14 | Complete
Duri | 5F-0707B | Duri 10969 | 5F-0707B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220555DR | 2022-08-14 | 2022-08-16 08:00 | 2022-08-21 14:00 | Complete
Duri | 5F-0710B | Duri 10971 | 5F-0710B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220556DR | 2022-08-21 14:00 | 2022-08-23 05:00 | 2022-08-28 05:00 | Complete
Duri | 5F-0809B | Duri 10975 | 5F-0809B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220463DR | 2022-08-28 05:00 | 2022-08-30 12:30 | 2022-09-04 12:45 | Complete
Duri | 5F-0812B | Duri 10978 | 5F-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220464DR | 2022-09-04 12:45 | 2022-09-06 12:45 | 2022-09-11 | Complete
Duri | 5H-1103B | Duri 10980 | 5H-1103B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220478DR | 2022-09-11 12:00 | 2022-09-13 04:30 | 2022-09-18 02:30 | Complete
Duri | 5H-0703C | Duri 10983 | 5H-0703C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220481DR | 2022-09-18 02:30 | 2022-09-20 02:30 | 2022-09-24 18:00 | Complete
Duri | 5F-1009B | Duri 10987 | 5F-1009B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220468DR | 2022-09-24 18:00 | 2022-09-28 13:00 | 2022-10-03 11:00 | Complete
Duri | 6F-1101B | Duri 10985 | 6F-1101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220470DR | 2022-10-03 11:00 | 2022-10-05 22:30 | 2022-10-11 04:00 | Complete
Duri | 5H-0503C | Duri 10982 | 5H-0503C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220482DR | 2022-10-11 04:00 | 2022-10-15 23:00 | 2022-10-21 15:00 | Complete
Duri | 6H-0202B | Duri 10995 | 6H-0202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220487DR | 2022-10-21 15:00 | 2022-10-24 02:00 | 2022-10-29 | Complete
Duri | 6F-0902B | Duri 10991 | 6F-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220467DR | 2022-10-29 | 2022-11-02 04:00 | 2022-11-08 | Complete
Duri | 6F-1102B | Duri 10994 | 6F-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220471DR | 2022-11-08 | 2022-11-11 01:00 | 2022-11-16 15:30 | Complete
Duri | 6H-0301B | Duri 10996 | 6H-0301B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220486DR | 2022-11-16 15:30 | 2022-11-19 04:30 | 2022-11-26 22:00 | Complete
Duri | 5F-1108B | Duri 10999 | 5F-1108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220473DR | 2022-11-26 22:00 | 2022-11-29 17:00 | 2022-12-05 | Complete
Duri | 5F-1209B | Duri 11004 | 5F-1209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220474DR | 2022-12-05 | 2022-12-06 16:00 | 2022-12-11 14:00 | Complete
Duri | 5G-0108B | Duri 11011 | 5G-0108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220476DR | 2022-12-11 14:00 | 2022-12-17 12:00 | 2022-12-21 23:30 | Complete
Duri | 6F-1202B | Duri 11008 | 6F-1202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220475DR | 2022-12-21 23:30 | 2022-12-25 10:30 | 2022-12-30 12:00 | Complete
Duri | 5G-0110B | Duri 11015 | 5G-0110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220557DR | 2022-12-30 12:00 | 2023-01-01 13:00 | 2023-01-06 13:00 | Complete
Duri | 6G-0202C | Duri 11012 | 6G-0202C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220558DR | 2023-01-06 13:00 | 2023-01-08 17:00 | 2023-01-14 | Complete
Duri | 5G-0310B | Duri 11016 | 5G-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220559DR | 2023-01-14 | 2023-01-16 | 2023-01-20 20:30 | Complete
Duri | 6G-0405B | Duri 11027 | 6G-0405B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220560DR | 2023-01-20 20:30 | 2023-01-23 | 2023-01-29 03:30 | Complete
Duri | 5G-0513B | Duri 11028 | 5G-0513B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220561DR | 2023-01-29 03:30 | 2023-01-31 01:00 | 2023-02-05 03:30 | Complete
Duri | 5G-0703B | Duri 11029 | 5G-0703B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220562DR | 2023-02-05 03:30 | 2023-02-07 | 2023-02-23 15:00 | Complete
Duri | 5H-0601B | Duri 11030 | 5H-0601B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | DRI2/402/3220825DR | 2023-02-22 15:00 | 2023-02-25 03:30 | 2023-03-03 02:00 | Complete
Duri | 5G-1102B | Duri 11031 | 5G-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | DRI2/402/3220826DR | 2023-03-03 02:00 | 2023-03-06 23:00 | 2023-03-11 15:00 | Complete
Duri | 5G-0711B | Duri 11034 | 5G-0711B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220870DR | 2023-03-11 15:00 | 2023-03-20 10:00 | 2023-03-27 03:00 | Complete
Duri | 5G-1105B | Duri 11050 | 5G-1105B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220866DR | 2023-03-27 03:00 | 2023-04-04 18:00 | 2023-04-10 06:00 | Complete
Duri | 6G-0901B | Duri 11051 | 6G-0901B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220873DR | 2023-04-10 06:00 | 2023-04-13 15:00 | 2023-04-18 10:00 | Complete
Duri | 5H-0403B | Duri 11052 | 5H-0403B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220857DR | 2023-04-18 10:00 | 2023-04-21 01:00 | 2023-04-26 14:00 | Complete
Duri | 6G-1102B | Duri 11053 | 6G-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220871DR | 2023-04-26 14:00 | 2023-04-29 06:00 | 2023-05-03 13:00 | Complete
Duri | 6G-0801B | Duri 11057 | 6G-0801B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230095DR | 2023-05-03 13:00 | 2023-06-01 23:00 | 2023-06-07 13:00 | Complete
Duri | 5G-0112B | Duri 11059 | 5G-0112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230113DR | 2023-06-07 13:00 | 2023-06-10 | 2023-06-15 21:00 | Complete
Duri | 6F-1001B | Duri 11078 | 6F-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230059DR | 2023-06-15 21:00 | 2023-06-18 01:00 | 2023-06-24 07:00 | Complete
Duri | 5F-1013B | Duri 11072 | 5F-1013B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230096DR | 2023-06-24 07:00 | 2023-06-26 12:00 | 2023-07-03 02:30 | Complete
Duri | 5F-1013C | Duri 11073 | 5F-1013C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230058DR | 2023-07-03 02:30 | 2023-07-04 22:00 | 2023-07-10 22:00 | Complete
Duri | 5H-0406B | Duri 11086 | 5H-0406B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220864DR | 2023-07-10 22:00 | 2023-07-13 16:00 | 2023-07-18 23:00 | Complete
Duri | 5E-1210C | Duri 11087 | 5E-1210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230116DR | 2023-07-18 23:00 | 2023-07-21 02:00 | 2023-07-27 15:00 | Complete
Duri | 5F-1112B | Duri 11090 | 5F-1112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230097DR | 2023-07-27 15:00 | 2023-07-29 22:00 | 2023-08-04 14:00 | Complete
Duri | 5K-23F | Duri 11091 | 5K-23F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230067DR | 2023-08-04 14:00 | 2023-08-06 02:00 | 2023-08-14 12:00 | Complete
Duri | 6K-22D | Duri 11042 | 6K-22D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230121DR | 2023-08-14 12:00 | 2023-08-16 18:00 | 2023-08-24 13:00 | Complete
Duri | 6G-0102B | Duri 11060 | 6G-0102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230068DR | 2023-08-24 13:00 | 2023-08-26 12:00 | 2023-09-01 19:00 | Complete
Duri | 6G-0301C | Duri 11107 | 6G-0301C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230070DR | 2023-09-01 19:00 | 2023-09-03 03:00 | 2023-09-08 15:00 | Complete
Duri | 6G-0301D | Duri 11108 | 6G-0301D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230124DR | 2023-09-08 15:00 | 2023-09-09 19:00 | 2023-09-15 21:00 | Complete
Duri | 5F-1011B | Duri 11119 | 5F-1011B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230071DR | 2023-09-15 21:00 | 2023-09-17 01:00 | 2023-09-22 21:00 | Complete
Duri | 2H-1010A | Duri 11121 | 2H-1010A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220797DR | 2023-09-22 21:00 | 2023-09-24 | 2023-10-01 05:00 | Complete
Duri | 2H-1011A | Duri 11122 | 2H-1011A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220799DR | 2023-10-01 05:00 | 2023-10-02 03:00 | 2023-10-07 18:30 | Complete
Duri | 2H-1112A | Duri 11126 | 2H-1112A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220795DR | 2023-10-07 18:30 | 2023-10-08 16:00 | 2023-10-16 05:30 | Complete
Duri | 2H-1210A | Duri 11132 | 2H-1210A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220776DR | 2023-10-16 05:30 | 2023-10-17 02:00 | 2023-10-23 13:00 | Complete
Duri | 2H-1211A | Duri 11136 | 2H-1211A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220779DR | 2023-10-23 13:00 | 2023-10-24 11:00 | 2023-10-30 18:30 | Complete
Duri | 2J-0113A | Duri 11139 | 2J-0113A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220787DR | 2023-10-30 18:30 | 2023-10-31 23:00 | 2023-11-07 09:00 | Complete
Duri | 2J-0112A | Duri 11140 | 2J-0112A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220773DR | 2023-11-07 09:00 | 2023-11-08 14:00 | 2023-11-15 01:30 | Complete
Duri | 2J-0211A | Duri 11146 | 2J-0211A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220784DR | 2023-11-15 01:30 | 2023-11-16 10:00 | 2023-11-23 17:00 | Complete
Duri | 2J-0312A | Duri 11147 | 2J-0312A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220775DR | 2023-11-23 17:00 | 2023-11-25 | 2023-12-01 03:00 | Complete
Duri | 2J-0811A | Duri 11157 | 2J-0811A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220745DR | 2023-12-01 03:00 | 2023-12-02 20:00 | 2023-12-10 05:30 | Complete
Duri | 2J-0413A | Duri 11158 | 2J-0413A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220763DR | 2023-12-10 05:30 | 2023-12-14 15:30 | 2023-12-21 04:00 | Complete
Duri | 2J-0910A | Duri 11168 | 2J-0910A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220737DR | 2023-12-21 04:00 | 2023-12-27 01:00 | 2024-01-06 14:00 | Complete
Duri | 3J-0502A | Duri 11169 | 3J-0502A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220757DR | 2024-01-06 14:00 | 2024-01-28 15:00 | 2024-02-03 05:30 | Complete
Duri | 2J-0613A | Duri 11175 | 2J-0613A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220754DR | 2024-01-09 | 2024-01-16 21:00 | 2024-01-25 | Complete
Duri | 2J-0410A | Duri 11181 | 2J-0410A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220762DR | 2024-02-03 05:30 | 2024-02-06 18:00 | 2024-02-12 19:30 | Complete
Duri | 5H-0901B | Duri 11182 | 5H-0901B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240034DR | 2024-02-12 19:30 | 2024-02-15 03:00 | 2024-02-20 19:00 | Complete
Duri | 6G-1101B | Duri 11183 | 6G-1101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240035DR | 2024-02-20 19:00 | 2024-02-22 11:30 | 2024-02-28 | Complete
Duri | 5E-1111B | Duri 11191 | 5E-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240036DR | 2024-02-28 | 2024-02-29 18:00 | 2024-03-06 16:00 | Complete
Duri | 3F-0303A | Duri 11192 | 3F-0303A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240038DR | 2024-03-06 16:00 | 2024-03-08 09:00 | 2024-03-15 20:00 | Complete
Duri | 6K-12B | Duri 11202 | 6K-12B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230092DR | 2024-03-15 20:00 | 2024-03-18 12:00 | 2024-03-26 08:00 | Complete
Duri | 5J-78E | Duri 11207 | 5J-78E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240039DR | 2024-03-26 08:00 | 2024-03-28 15:00 | 2024-04-04 17:00 | Complete
Duri | 5J-85D | Duri 11210 | 5J-85D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240048DR | 2024-04-04 17:00 | 2024-04-07 08:30 | 2024-04-15 12:00 | Complete
Duri | 5J-86D | Duri 11216 | 5J-86D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240049DR | 2024-04-15 12:00 | 2024-04-19 16:30 | 2024-04-30 | Complete
Duri | 5G-0905C | Duri 11219 | 5G-0905C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240044DR | 2024-04-30 | 2024-05-02 | 2024-05-08 05:00 | Complete
Duri | 5G-1010B | Duri 11223 | 5G-1010B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240076DR | 2024-05-08 05:00 | 2024-05-09 22:30 | 2024-05-16 02:00 | Complete
Duri | 5G-1010C | Duri 11225 | 5G-1010C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240050DR | 2024-05-16 02:00 | 2024-05-17 14:30 | 2024-05-23 18:00 | Complete
Duri | 5F-0207B | Duri 11231 | 5F-0207B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240043DR | 2024-05-23 18:00 | 2024-05-25 12:00 | 2024-05-31 14:00 | Complete
Duri | 5G-0909B | Duri 11234 | 5G-0909B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240838DR | 2024-05-31 14:00 | 2024-06-04 18:00 | 2024-06-11 | Complete
Duri | 5E-0907B | Duri 11238 | 5E-0907B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230091DR | 2024-06-11 | 2024-06-12 23:00 | 2024-06-19 04:00 | Complete
Duri | 4G-0313B | Duri 11228 | 4G-0313B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240836DR | 2024-06-19 04:00 | 2024-06-21 04:00 | 2024-06-26 17:00 | Complete
Duri | 3H-1201A | Duri 11241 | 3H-1201A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220801DR | 2024-06-26 17:00 | 2024-06-28 09:00 | 2024-07-04 17:00 | Complete
Duri |  | Duri 11249 | 2H-1213A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220800DR | 2024-07-04 17:00 | 2024-07-06 16:00 | 2024-07-14 02:00 | Complete
Duri | 3J-0102A | Duri 11245 | 3J-0102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220796DR | 2024-07-14 02:00 |  |  | In Progress
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220373DR | 2022-09-22 19:00 | 2022-09-22 19:00 | 2022-09-26 11:30 | Complete
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220394DR | 2022-09-26 11:30 | 2022-10-02 03:00 | 2022-10-05 | Complete
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220440DR | 2022-10-05 | 2022-10-14 04:00 | 2022-10-16 10:00 | Release
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220415DR | 2022-10-16 10:00 | 2022-10-20 19:00 | 2022-10-22 14:00 | Complete
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220407DR | 2022-10-22 14:00 | 2022-10-24 23:00 | 2022-10-26 19:00 | Release
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220390DR | 2022-10-26 19:00 | 2022-10-30 02:00 | 2022-11-01 | Complete
Duri | 4I-0113B | Duri 10993 | 4I-0113B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220494DR | 2022-11-01 | 2022-11-19 05:00 | 2022-12-12 | Complete
Duri | 5G-0610B | Duri 10998 | 5G-0610B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220493DR | 2022-12-12 | 2022-12-20 03:00 | 2022-12-30 | Complete
Duri | 4H-0812B | Duri 11000 | 4H-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220495DR | 2022-12-30 | 2023-01-02 17:00 | 2023-01-09 12:30 | Complete
Duri | 6G-0701B | Duri 11017 | 6G-0701B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220499DR | 2023-01-09 12:30 | 2023-01-12 18:00 | 2023-01-19 14:30 | Complete
Duri | 5G-0806B | Duri 11005 | 5G-0806B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220496DR | 2023-01-19 14:30 | 2023-01-22 05:00 | 2023-01-28 19:00 | Complete
Duri | 6G-0804B | Duri 11009 | 6G-0804B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220497DR | 2023-01-28 19:00 | 2023-02-01 01:00 | 2023-02-08 10:00 | Complete
Duri | 5G-0710B | Duri 11014 | 5G-0710B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220498DR | 2023-02-08 10:00 | 2023-02-10 18:00 | 2023-03-02 18:00 | Complete
Duri | 5G-0910B | Duri 11022 | 5G-0910B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220573DR | 2023-03-02 18:00 | 2023-03-09 07:00 | 2023-03-17 05:00 | Complete
Duri | 5G-1111B | Duri 11039 | 5G-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220869DR | 2023-03-17 05:00 | 2023-03-23 03:00 | 2023-03-30 13:00 | Complete
Duri | 5H-0409B | Duri 11040 | 5H-0409B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220872DR | 2023-03-30 13:00 | 2023-04-02 17:00 | 2023-04-09 07:00 | Complete
Duri | 5H-0210B | Duri 11038 | 5H-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220863DR | 2023-04-09 07:00 | 2023-04-19 13:00 | 2023-04-26 03:00 | Complete
Duri | 6G-0503B | Duri 11019 | 6G-0503B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220500DR | 2023-04-26 03:00 | 2023-04-28 17:30 | 2023-05-04 18:00 | Complete
Duri | 5G-0605B | Duri 11033 | 5G-0605B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | DRI2/402/3220828DR | 2023-05-04 18:00 | 2023-05-07 13:00 | 2023-05-13 15:30 | Complete
Duri | 5H-0606B | Duri 11055 | 5H-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230056DR | 2023-05-13 15:30 | 2023-05-22 07:00 | 2023-05-29 | Complete
Duri | 5H-0213B | Duri 11045 | 5H-0213B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220862DR | 2023-05-29 | 2023-06-01 18:00 | 2023-06-10 02:00 | Complete
Duri | 5G-1103C | Duri 11047 | 5G-1103C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220868DR | 2023-06-10 02:00 | 2023-06-12 10:30 | 2023-06-18 16:00 | Complete
Duri | 6G-0101C | Duri 11075 | 6G-0101C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230115DR | 2023-06-18 16:00 | 2023-06-21 06:30 | 2023-07-01 15:00 | Complete
Duri | 5F-0708B | Duri 11076 | 5F-0708B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230102DR | 2023-07-01 15:00 | 2023-07-03 15:00 | 2023-07-10 05:30 | Complete
Duri | 5F-0708C | Duri 11077 | 5F-0708C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230118DR | 2023-07-10 05:30 | 2023-07-13 | 2023-07-20 05:00 | Complete
Duri | 5F-0106B | Duri 11092 | 5F-0106B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230120DR | 2023-07-20 05:00 | 2023-07-22 08:00 | 2023-07-29 11:00 | Complete
Duri | 5F-1211B | Duri 11093 | 5F-1211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230077DR | 2023-07-29 11:00 | 2023-07-31 | 2023-08-07 08:00 | Complete
Duri | 5F-0613B | Duri 11094 | 5F-0613B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230061DR | 2023-08-07 08:00 | 2023-08-08 22:00 | 2023-08-16 02:00 | Complete
Duri | 5F-0408B | Duri 11100 | 5F-0408B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230126DR | 2023-08-16 02:00 | 2023-08-27 02:00 | 2023-09-03 06:00 | Complete
Duri | 5F-1010B | Duri 11104 | 5F-1010B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230076DR | 2023-09-03 06:00 | 2023-09-04 20:00 | 2023-09-11 | Complete
Duri | 5F-0808B | Duri 11103 | 5F-0808B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230103DR | 2023-09-11 | 2023-09-12 14:00 | 2023-09-18 09:00 | Complete
Duri | 5G-0211B | Duri 11109 | 5G-0211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230083DR | 2023-09-18 09:00 | 2023-09-21 09:30 | 2023-09-27 10:00 | Complete
Duri | 5E-1209B | Duri 11110 | 5E-1209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230117DR | 2023-09-27 10:00 | 2023-09-29 | 2023-10-04 16:00 | Complete
Duri | 5F-0709B | Duri 11111 | 5F-0709B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230073DR | 2023-10-04 16:00 | 2023-10-06 03:00 | 2023-10-11 18:00 | Complete
Duri | 2J-1010A | Duri 11128 | 2J-1010A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220735DR | 2023-10-11 18:00 | 2023-10-13 08:00 | 2023-10-20 12:00 | Complete
Duri | 2J-1011A | Duri 11129 | 2J-1011A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220736DR | 2023-10-20 12:00 | 2023-10-21 23:00 | 2023-10-27 16:00 | Complete
Duri | 2J-0912A | Duri 11137 | 2J-0912A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220741DR | 2023-10-27 16:00 | 2023-10-29 02:00 | 2023-11-04 | Complete
Duri | 3J-0401A | Duri 11138 | 3J-0401A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220768DR | 2023-11-04 | 2023-11-05 17:00 | 2023-11-12 08:00 | Complete
Duri | 2J-0810A | Duri 11148 | 2J-0810A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220743DR | 2023-11-12 08:00 | 2023-11-14 | 2023-11-22 01:30 | Complete
Duri | 2J-0913A | Duri 11149 | 2J-0913A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220738DR | 2023-11-22 01:30 | 2023-11-24 01:00 | 2023-12-02 13:00 | Complete
Duri | 2H-1113A | Duri 11150 | 2H-1113A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220782DR | 2023-12-02 13:00 | 2023-12-05 08:00 | 2023-12-11 22:00 | Complete
Duri | 3J-0601A | Duri 11156 | 3J-0601A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220756DR | 2023-12-11 22:00 | 2023-12-14 14:00 | 2023-12-20 05:00 | Complete
Duri | 2J-0512A | Duri 11164 | 2J-0512A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220761DR | 2023-12-20 05:00 | 2023-12-26 12:00 | 2024-01-04 15:00 | Complete
Duri | 2J-0513A | Duri 11165 | 2J-0513A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220753DR | 2024-01-04 15:00 | 2024-01-16 17:00 | 2024-01-24 16:00 | Complete
Duri | 2J-0813A | Duri 11171 | 2J-0813A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220740DR | 2024-01-24 16:00 | 2024-01-29 16:00 | 2024-02-04 11:00 | Complete
Duri | 2J-0411A | Duri 11172 | 2J-0411A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220764DR | 2024-02-04 11:00 | 2024-02-06 | 2024-02-11 19:00 | Complete
Duri | 2J-0310A | Duri 11185 | 2J-0310A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220769DR | 2024-02-11 19:00 | 2024-02-13 06:30 | 2024-02-19 07:00 | Complete
Duri | 2H-1110A | Duri 11187 | 2H-1110A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220789DR | 2024-02-19 07:00 | 2024-02-22 16:00 | 2024-02-29 02:00 | Complete
Duri | 2J-0110A | Duri 11188 | 2J-0110A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220767DR | 2024-02-29 02:00 | 2024-03-01 14:00 | 2024-03-07 09:00 | Complete
Duri | 3H-1001A | Duri 11196 | 3H-1001A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220794DR | 2024-03-07 08:30 | 2024-03-08 21:00 | 2024-03-14 13:00 | Complete
Duri | 3H-1102A | Duri 11189 | 3H-1102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220788DR | 2024-03-14 13:00 | 2024-03-16 06:00 | 2024-03-22 03:00 | Complete
Duri | 2J-0213A | Duri 11206 | 2J-0213A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220783DR | 2024-03-22 03:00 | 2024-03-23 14:00 | 2024-03-29 02:00 | Complete
Duri | 2J-0210A | Duri 11209 | 2J-0210A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220778DR | 2024-03-29 02:00 | 2024-03-30 13:00 | 2024-04-05 12:00 | Complete
Duri | 2H-1013A | Duri 11212 | 2H-1013A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220791DR | 2024-04-05 12:00 | 2024-04-07 12:00 | 2024-04-14 07:00 | Complete
Duri | 5G-0208B | Duri 11067 | 5G-0208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230123DR | 2024-04-14 07:00 | 2024-04-16 21:00 | 2024-04-25 16:30 | Complete
Duri | 5G-0108C | Duri 11215 | 5G-0108C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240040DR | 2024-04-25 16:30 | 2024-04-27 07:00 | 2024-05-04 | Complete
Duri | 6G-0901C | Duri 11218 | 6G-0901C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240051DR | 2024-05-04 | 2024-05-05 13:00 | 2024-05-12 | Complete
Duri | 5F-1208B | Duri 11226 | 5F-1208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230131DR | 2024-05-12 | 2024-05-13 23:30 | 2024-05-21 10:00 | Complete
Duri | 5G-0313C | Duri 11229 | 5G-0313C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240083DR | 2024-05-21 10:00 | 2024-05-23 11:00 | 2024-05-29 23:00 | Complete
Duri | 5G-0313B | Duri 11232 | 5G-0313B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240063DR | 2024-05-29 23:00 | 2024-05-31 08:00 | 2024-06-06 | Complete
Duri | 3S-67B | Duri 11236 | 3S-67B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240081DR | 2024-06-06 | 2024-06-08 06:30 | 2024-06-15 10:00 | Complete
Duri | 5N-56F | Duri 11240 | 5N-56F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240082DR | 2024-06-15 10:00 | 2024-06-17 20:00 | 2024-06-25 | Complete
Duri | 5E-1211B | Duri 11243 | 5E-1211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240055DR | 2024-06-25 | 2024-06-26 22:00 | 2024-07-03 12:00 | Complete
Duri | 5F-0209B | Duri 11244 | 5F-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240890DR | 2024-07-03 12:00 | 2024-07-05 02:00 | 2024-07-11 05:00 | Complete
Duri | 4E-0610A | Duri 11248 | 4E-0610A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240052DR | 2024-07-11 05:00 | 2024-07-13 12:00 |  | In Progress
Sikladi | SKL23_P05 | Sikladi 00030 | N1-O-14A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220925DR | 2023-06-10 | 2023-06-11 06:00 | 2023-06-21 02:00 | Complete
Ubi | UBI-X11 | Ubi 00053 | N3-O-34A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220919DR | 2023-07-20 10:30 | 2023-07-23 01:00 | 2023-08-01 | Complete
Sikladi | SKL23_P04 | Sikladi 00035 | N1-O-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220923DR | 2023-10-01 19:30 | 2023-10-04 21:30 | 2023-10-14 | Complete
Benar | BNR-X05 | Benar 00060 | N2-0-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSO2/402/3220355DR | 2022-11-23 13:00 | 2022-12-04 07:30 | 2022-12-24 20:00 | Complete
Ubi | UBI-X05 | Ubi 00052 | N4-O-84C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSA2/402/3220918DR | 2023-06-02 16:00 | 2023-06-04 11:30 | 2023-06-13 05:00 | Complete
Menggala No | MNO-P26 | Menggala No 00065 | N4-W2-36A | Perforation Initial | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSM2/402/3230209DR | 2023-09-22 13:00 | 2023-09-23 21:30 | 2023-10-11 | Complete
Ubi | UBI-X13 | Ubi 00054 | N1-W1-18A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSA2/402/3220920DR | 2023-10-23 18:30 | 2023-10-26 01:30 | 2023-11-01 22:30 | Complete
Petani | PETA22-P12 | Petani 00194 | S1-O-88D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-08 | SSA2/402/3220908DR | 2024-04-20 10:00 | 2024-04-21 12:00 | 2024-04-28 15:00 | Complete
Balam So | BLSO-P46 | Balam So 00502 | N1-O-73B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-12 | SSO2/402/3220341DR | 2023-01-14 21:30 | 2023-01-16 23:00 | 2023-01-22 17:30 | Complete
Balam So | BLSO-P25 | Balam So 00458 | N1-W1-67B | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ARJ-15 | GRK2/402/2220019DR | 2022-08-24 17:00 | 2022-08-26 11:00 | 2022-08-31 20:00 | Complete
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Perforation | PRF01 - Regular Perforation | Land Workover Unit | ARJ-15 | GRK2/402/2220010DR | 2022-10-05 23:30 | 2022-10-07 03:00 | 2022-10-13 19:30 | Complete
Balam So | BLSO-P41 | Balam So 00485 | O-W1-15G | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220317DR | 2022-10-13 19:30 | 2022-10-17 11:00 | 2022-10-30 19:00 | Complete
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ARJ-15 | GRK2/402/2220028DR | 2022-11-04 22:00 | 2022-11-05 18:00 | 2022-11-10 20:30 | Complete
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220351DR | 2022-11-15 21:30 | 2022-11-24 21:30 | 2022-11-27 08:00 | Complete
Balam So | BLSO-P21 | Balam So 00463 | O-W1-18B | Perforation | PRF01 - Regular Perforation | Land Workover Unit | ARJ-15 | GRK2/402/2220011DR | 2023-01-28 21:30 | 2023-01-29 23:00 | 2023-02-01 21:00 | Complete
Balam Se | P_BLSE23_P02_MN | Balam Se 00031 | O-O-32C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220581DR | 2023-12-22 18:00 | 2023-12-27 07:00 | 2024-01-03 17:30 | Complete
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSE2/402/3230314DR | 2024-01-22 19:00 | 2024-01-24 23:00 | 2024-01-31 16:00 | Complete
Minas | MNA-P7 | Minas 01993 | 8E-61N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | GRK2/402/3220202DR | 2022-06-06 08:00 | 2022-06-06 16:00 | 2022-06-11 14:30 | Complete
Minas | P_6C-28E | Minas 02008 | 6C-28E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | GRK2/402/3220230DR | 2022-08-06 21:00 | 2022-08-07 02:30 | 2022-08-11 | Complete
Minas | MNS-P07 | Minas 02045 | 9D-79N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220632DR | 2023-04-18 17:00 | 2023-04-19 06:00 | 2023-04-24 06:00 | Complete
Minas | P_5E-96N | Minas 02052 | 5E-96N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220636DR | 2023-05-19 09:00 | 2023-05-19 22:00 | 2023-05-25 07:00 | Complete
Minas | P_4D-38E | Minas 02070 | 4D-38E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220640DR | 2023-08-01 11:00 | 2023-08-01 23:00 | 2023-08-14 | Complete
Minas | P_3D-33E | Minas 02072 | 3D-33E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220638DR | 2023-08-14 | 2023-08-14 11:00 | 2023-08-20 05:00 | Complete
Minas | MNS-P10 | Minas 01992 | 8E-83E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | GRK2/402/3210108DR | 2022-04-21 08:00 | 2022-04-21 20:00 | 2022-04-27 10:00 | Complete
Minas | MNS-P06 | Minas 01998 | 7E-56N | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | AU-06 | GRK2/402/3220213DR | 2022-06-09 22:30 | 2022-06-10 17:30 | 2022-06-11 05:00 | Complete
Minas | P_6E-73E | Minas 02016 | 6E-73E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | GRK2/402/3220223DR | 2022-08-23 06:00 | 2022-08-23 16:00 | 2022-08-29 22:30 | Complete
Minas | P_7C-16N | Minas 02055 | 7C-16N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSO2/402/3220644DR | 2023-05-11 23:00 | 2023-05-12 08:00 | 2023-05-21 14:00 | Complete
Minas | P_5E-64N | Minas 02071 | 5E-64N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230230DR | 2023-08-04 | 2023-08-04 10:00 | 2023-08-07 14:00 | Complete
Minas | P_3D-12N | Minas 02099 | 3D-12N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230229DR | 2023-11-23 11:00 | 2023-11-24 07:30 | 2023-11-29 02:30 | Complete
Minas | P_MINA24_6E-58N | Minas 02102 | 6E-58N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230497DR | 2024-01-22 | 2024-01-25 09:30 | 2024-01-29 | Complete
Minas | P_3A-92E | Minas 02109 | 3A-92E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230219DR | 2024-02-01 15:00 | 2024-02-04 19:00 | 2024-02-09 05:30 | Complete
Minas | P_MINA24_5C-27N | Minas 02110 | 5C-27N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230494DR | 2024-02-21 | 2024-02-26 12:00 | 2024-03-14 08:30 | Complete
Minas | P_4C-14E | Minas 02029 | 4C-14E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220382DR | 2023-01-03 19:00 | 2023-01-04 01:30 | 2023-01-15 22:00 | Complete
Minas | P_4C-25N2 | Minas 02047 | 4C-25N2 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220430DR | 2023-05-15 05:00 | 2023-05-15 13:00 | 2023-05-22 | Complete
Minas | P_6D-64N | Minas 02061 | 6D-64N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220652DR | 2023-06-17 16:00 | 2023-06-18 01:30 | 2023-06-22 15:30 | Complete
Minas | P_5D-14E1 | Minas 02077 | 5D-14E1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220648DR | 2023-09-05 20:00 | 2023-09-06 05:00 | 2023-09-10 05:00 | Complete
Minas | P_3B-34 | Minas 02082 | 3B-34 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220433DR | 2023-09-23 18:30 | 2023-09-24 05:30 | 2023-09-27 08:30 | Complete
Minas | Minas P03 | Minas 02097 | 8D-43N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220458DR | 2023-11-22 07:00 | 2023-11-22 15:00 | 2023-11-27 16:00 | Complete
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | MBS2/402/3230833EX | 2024-06-17 | 2024-05-16 | 2024-06-18 17:00 | Complete
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | MBS2/402/3230833EX | 2024-07-03 11:30 | 2024-05-16 | 2024-07-06 02:30 | Complete
Duri | 3L-18D | Duri 11131 | 3L-18D | Pump Repair | PMP27 - Rod Pump-Bump Down Job | Mast Unit | BDJ-01 | RHT2/402/2230110DR | 2024-02-05 10:15 |  | 2024-02-05 11:30 | Complete
Duri | 4H-54C | Duri 11200 | 4H-54C | Pump Repair | PMP27 - Rod Pump-Bump Down Job | Mast Unit | BDJ-01 | RHT2/402/2240033DR | 2024-05-31 10:30 |  | 2024-05-31 12:00 | Complete
Topaz | P_TOPA23_P03 | Topaz 00013 | O-O-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-18 | SSV2/402/3230678DR | 2024-05-31 21:30 | 2024-05-31 21:30 | 2024-07-07 20:30 | Complete
Topaz | P_TOPA23_P01 | Topaz 00014 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-18 | SSV2/402/3230677DR | 2024-07-07 20:30 |  |  | In Progress
Tilan | P_TILA24_01 | Tilan 00038 | O-O-25D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | TLA2/402/3230739DR | 2024-03-24 | 2024-03-24 | 2024-04-17 19:00 | Complete
Petani | P_PETA24_26 | Petani 00205 | O-O-33D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230897DR | 2024-04-17 19:00 | 2024-04-28 | 2024-05-15 02:00 | Complete
Petani | P_PETA24_29 | Petani 00206 | O-O-52D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230920DR | 2024-05-15 02:00 | 2024-05-21 12:00 | 2024-06-06 02:30 | Complete
Petani | P_PETA24_30 | Petani 00208 | O-O-33E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230921DR | 2024-06-06 02:30 | 2024-06-19 13:30 | 2024-07-05 | Complete
Petani | P_PETA24_28 | Petani 00212 | O-O-33F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230919DR | 2024-07-05 | 2024-07-08 18:30 |  | In Progress
Petani | PETA24_INJ02 | Petani 00204 | O-O-74F | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | SSM2/402/3230611DR | 2024-05-13 10:00 | 2024-05-13 10:00 | 2024-05-31 16:00 | Complete
Petani | P_PETA24_20 | Petani 00207 | S1-E1-42B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | PTO2/402/3230912DR | 2024-05-31 16:00 | 2024-06-10 01:00 | 2024-07-02 07:00 | Complete
Petani | P_PETA24_24 | Petani 00209 | S1-E1-42C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | PTO2/402/3230916DR | 2024-07-02 07:00 | 2024-07-06 16:30 |  | In Progress
Petapahan | PETP21-P08 | Petapahan 00150 | O-E1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210145DR | 2021-09-29 20:00 | 2021-09-29 20:00 | 2021-10-12 23:00 | Complete
Kotabatak | KOTA21_P_TE_B3 | Kotabatak 00460 | N1-W1-55 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210097DR | 2021-10-12 23:00 | 2021-10-19 15:00 | 2021-10-31 18:00 | Complete
Kotabatak | KOTA21_P_TE_2B | Kotabatak 00461 | N1-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210099DR | 2021-10-31 18:00 | 2021-11-05 | 2021-11-17 02:30 | Release
Kotabatak | KOTA21_P_TE_A2 | Kotabatak 00462 | N1-W1-59 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210095DR | 2021-11-17 02:30 | 2021-11-21 21:00 | 2021-12-01 16:00 | Release
Kotabatak | KOTA21_P_TE_B1 | Kotabatak 00464 | N1-W1-60 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210096DR | 2021-12-01 16:00 | 2021-12-04 06:30 | 2021-12-15 14:00 | Complete
Kotabatak | KTB-X23 | Kotabatak 00466 | S1-O-17 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210101DR | 2021-12-15 14:00 | 2021-12-26 22:00 | 2022-01-06 | Complete
Kotabatak | KTB-X27 | Kotabatak 00472 | N1-W1-27 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220167DR | 2022-01-06 | 2022-01-16 17:00 | 2022-01-27 | Complete
Kotabatak | KTB-X09 | Kotabatak 00469 | N1-W1-25A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220169DR | 2022-01-27 | 2022-01-30 11:00 | 2022-02-10 | Complete
Kotabatak | KTB-X21 | Kotabatak 00475 | O-O-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220164DR | 2022-02-10 | 2022-02-20 02:00 | 2022-03-06 | Complete
Kotabatak | KTB-X13 | Kotabatak 00478 | O-W1-32 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220172DR | 2022-03-06 | 2022-03-14 14:00 | 2022-03-26 19:00 | Complete
Kotabatak | KTB-X22 | Kotabatak 00480 | O-O-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220175DR | 2022-03-26 19:00 | 2022-04-02 08:00 | 2022-04-14 | Complete
Kotabatak | KTB-X12 | Kotabatak 00482 | O-W1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220171DR | 2022-04-14 | 2022-04-21 02:00 | 2022-05-03 20:00 | Complete
Kotabatak | KOTA21_P_TE_8A_HZ | Kotabatak 00483 | O-E1-32 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220177DR | 2022-05-03 20:00 | 2022-05-10 01:00 | 2022-06-07 09:00 | Complete
Kotabatak | KTB-X30 | Kotabatak 00484 | S1-W1-46 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220178DR | 2022-06-07 09:00 | 2022-06-14 15:00 | 2022-06-28 01:00 | Complete
Kotabatak | KB_PL2 Inj | Kotabatak 00486 | O-W2-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/2220261DR | 2022-06-28 01:00 | 2022-07-04 14:00 | 2022-07-18 | Complete
Petapahan | PETP21_HW_P05 | Petapahan 00157 | N2-W1-49B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220269DR | 2022-07-18 | 2022-08-03 03:00 | 2022-09-26 22:00 | Complete
Kotabatak | KB_PL43 | Kotabatak 00498 | N1-W2-54 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220423DR | 2022-10-09 18:00 | 2022-10-09 18:00 | 2022-10-25 18:00 | Complete
Kotabatak | KB_PL37 | Kotabatak 00500 | O-O-79 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220338DR | 2022-10-24 18:00 | 2022-11-02 21:00 | 2022-11-14 14:00 | Complete
Kotabatak | KB_PL32 Inj | Kotabatak 00502 | O-E1-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220370DR | 2022-11-14 14:00 | 2022-11-21 02:00 | 2022-12-05 05:00 | Complete
Kotabatak | KB_PL31 | Kotabatak 00504 | O-E1-37 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220339DR | 2022-12-05 05:00 | 2022-12-12 22:00 | 2022-12-29 08:00 | Complete
Kotabatak | KB_PL48 | Kotabatak 00506 | O-E1-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220369DR | 2022-12-28 08:00 | 2023-01-06 04:00 | 2023-01-20 | Complete
Kotabatak | KB_PL24 Inj | Kotabatak 00508 | O-E1-59 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220402DR | 2023-01-20 | 2023-01-29 12:00 | 2023-02-24 | Complete
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220360DR | 2023-02-24 | 2023-03-01 19:00 | 2023-03-28 07:00 | Complete
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220380DR | 2023-03-28 07:00 | 2023-04-03 17:00 | 2023-04-19 06:30 | Complete
Minas | MINA21_HW_P04 | Minas 02058 | 6E-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220631DR | 2023-04-19 06:30 | 2023-05-05 01:00 | 2023-05-26 | Complete
Petapahan | PETP21_HW_P07_Ext | Petapahan 00156 | N2-W1-34B | Drill and Complete | DRL01 - Drill Hole (Re-Entry) | Land Drilling Rig | BDSI-27 | SSA2/402/3220885DR | 2023-05-26 | 2023-06-13 20:30 | 2023-08-15 18:00 | Complete
Petapahan | PTP_SO_P01 | Petapahan 00165 | N2-W2-87A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3230152DR | 2023-08-15 18:00 | 2023-08-24 04:00 | 2023-09-07 09:00 | Release
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220629DR | 2023-09-07 09:00 | 2023-09-22 01:30 | 2023-10-24 05:00 | Complete
Petapahan | PTP BL2-Z10 | Petapahan 00167 | N1-W2-28C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3220884DR | 2023-10-24 05:00 | 2023-11-03 21:30 | 2023-11-15 12:00 | Release
Petapahan | PTP BL2-P20 | Petapahan 00169 | N1-W2-28B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3220881DR | 2023-11-15 12:00 | 2023-11-19 18:00 | 2023-12-04 20:30 | Complete
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | MBS2/402/3230833EX | 2023-12-04 20:30 | 2023-12-30 21:00 | 2024-02-29 19:00 | Complete
Minas | MINAHW23_P04 | Minas 02118 | 2D-85A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230252DR | 2024-02-29 19:00 | 2024-03-14 | 2024-04-09 19:00 | Complete
Minas | MINAHW23_P08 | Minas 02124 | 6C-19A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230251DR | 2024-04-09 19:00 | 2024-04-20 05:00 | 2024-05-07 03:00 | Complete
Minas | MINAHW23_P09 | Minas 02128 | 5D-94A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230256DR | 2024-05-07 03:00 | 2024-05-13 02:30 | 2024-05-31 13:00 | Complete
Minas | MINAHW23_P16 | Minas 02131 | 3D-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230255DR | 2024-05-31 13:00 | 2024-06-24 03:00 |  | In Progress
Petapahan | PETP21-P11 | Petapahan 00149 | O-E1-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210148DR | 2021-09-21 04:00 | 2021-09-21 04:00 | 2021-10-06 22:00 | Complete
Petapahan | PETP21-P10 | Petapahan 00151 | O-E1-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210147DR | 2021-10-06 22:00 | 2021-10-20 09:30 | 2021-11-03 13:00 | Complete
Petapahan | PTP-P3 | Petapahan 00153 | N2-W1-23B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210152DR | 2021-11-03 13:00 | 2021-11-09 05:00 | 2021-11-27 02:00 | Complete
Petapahan | PTP-P5 | Petapahan 00154 | N2-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210156DR | 2021-11-26 02:00 | 2021-11-28 19:00 | 2021-12-14 10:30 | Complete
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210149DR | 2021-12-14 10:30 | 2021-12-22 05:00 | 2022-01-05 | Complete
Kotabatak | KTB-X15 | Kotabatak 00468 | O-O-53A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210150DR | 2022-01-05 | 2022-01-13 14:15 | 2022-01-25 08:30 | Complete
Kotabatak | KTB-X16 | Kotabatak 00471 | O-O-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220166DR | 2022-01-25 08:30 | 2022-01-31 02:00 | 2022-02-12 17:00 | Complete
Kotabatak | KTB-X25 | Kotabatak 00477 | N1-O-69 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220174DR | 2022-02-12 17:00 | 2022-02-18 06:00 | 2022-03-02 | Complete
Kotabatak | KTB-X28 | Kotabatak 00474 | O-W1-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220168DR | 2022-03-02 | 2022-03-09 04:00 | 2022-03-21 11:00 | Complete
Petapahan | PTP-P1 | Petapahan 00155 | N2-W1-16A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220267DR | 2022-03-21 11:00 | 2022-03-28 03:00 | 2022-04-23 | Complete
Minas | MNS-P12 | Minas 02000 | 8D-48N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220210DR | 2022-04-23 | 2022-05-06 02:30 | 2022-05-17 04:30 | Complete
Minas | P_6D-31N | Minas 02003 | 6D-31N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220232DR | 2022-05-17 04:30 | 2022-05-25 | 2022-06-03 03:00 | Complete
Minas | MINA21_HW_P02 | Minas 02005 | 8F-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220224DR | 2022-06-03 03:00 | 2022-06-12 | 2022-07-10 | Complete
Petani | PETA22-P05 | Petani 00151 | O-O-43D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220218DR | 2022-07-10 | 2022-07-25 09:00 | 2022-08-13 03:00 | Complete
Petani | PETA22-P20 | Petani 00154 | S1-O-15A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSO2/402/3220508DR | 2022-08-13 03:00 | 2022-08-23 21:00 | 2022-09-13 12:00 | Complete
Petani | PETA22-P18 | Petani 00159 | N1-W1-38A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PTF2/402/3220460DR | 2022-09-13 12:00 | 2022-09-20 19:30 | 2022-10-10 11:00 | Complete
Petani | PETA22-P27 | Petani 00158 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSO2/402/3220327DR | 2022-10-10 11:00 | 2022-10-20 01:30 | 2022-11-09 16:00 | Complete
Kelok Ne | P_KENE_P02 | Kelok NE 00004 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | KEN2/402/3220807DR | 2022-11-09 16:00 | 2022-11-29 16:00 | 2023-01-17 05:00 | Release
Sidingin North | Exp_P02_Sidingin | Sidingin North 00001 | O-O-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SDN2/402/2220001EX | 2023-01-17 05:00 | 2023-02-08 16:00 | 2023-04-13 08:30 | Release
Pinang | P_PINA23_P11 | Pinang 00055 | N1-W1-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220842DR | 2023-04-13 18:30 | 2023-05-10 04:30 | 2023-05-25 13:00 | Complete
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNA2/402/3220823DR | 2023-05-25 13:00 | 2023-05-31 17:30 | 2023-06-15 12:30 | Release
Pinang | P_PINA23_HW03 | Pinang 00061 | O-W1-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220841DR | 2023-06-15 12:30 | 2023-06-23 | 2023-07-21 15:00 | Complete
Pinang | P_PINA23_HW01 | Pinang 00063 | O-O-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220840DR | 2023-07-21 15:00 | 2023-07-31 23:45 | 2023-08-29 18:00 | Complete
Pinang | P_PINA23_HW02 | Pinang 00064 | O-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220839DR | 2023-08-29 18:00 | 2023-09-06 01:30 | 2023-10-06 18:00 | Complete
Pungut | PUNG23_H02 | Pungut 00053 | S2-O-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230194DR | 2023-10-12 | 2023-11-06 | 2023-11-27 12:00 | Complete
Pungut | PUNG23_D03 | Pungut 00054 | S1-O-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230191DR | 2023-11-27 12:00 | 2023-12-06 11:00 | 2023-12-18 02:00 | Complete
Pungut | PUNG23_H03 | Pungut 00055 | S1-O-18B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230198DR | 2023-12-18 02:00 | 2023-12-23 18:00 | 2024-01-27 02:00 | Complete
Pungut | PUNG23_H01 | Pungut 00056 | S2-E1-54D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230196DR | 2024-01-27 02:00 | 2024-02-07 | 2024-03-03 11:00 | Complete
Pungut | PUNG23_P15 | Pungut 00057 | S2-E1-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230201DR | 2024-03-03 11:00 | 2024-03-09 | 2024-03-22 14:00 | Complete
Astrea | Astrea-1 | Astrea 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | AST2/402/3230001EX | 2024-03-22 14:00 | 2024-04-10 17:00 | 2024-05-27 | Complete
Pukat | P_PUKA24_02 | Pukat 00006 | S1-O-71A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SPS2/402/3240891DR | 2024-05-27 | 2024-06-10 | 2024-06-24 19:00 | Complete
Petani | P_PETA24-P01 | Petani 00213 | N1-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PTO2/402/3230900DR | 2024-06-24 17:00 | 2024-07-11 |  | In Progress
Kotabatak | KTB-X26 | Kotabatak 00488 | N1-W1-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | GRK2/402/3220188DR | 2022-07-27 | 2022-07-27 | 2022-08-10 21:00 | Complete
Kotabatak | KB_PL18 Inj | Kotabatak 00491 | N1-O-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220507DR | 2022-08-10 21:00 | 2022-08-21 | 2022-09-01 20:00 | Complete
Kotabatak | KB_PL10 Inj | Kotabatak 00492 | N1-W1-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220325DR | 2022-09-01 20:00 | 2022-09-09 22:00 | 2022-09-21 18:30 | Complete
Kotabatak | KB_PL45 | Kotabatak 00495 | N1-W2-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220534DR | 2022-09-21 18:30 | 2022-09-29 09:30 | 2022-10-12 06:00 | Complete
Kotabatak | KB_PL46 | Kotabatak 00497 | N1-W2-39 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220358DR | 2022-10-12 06:00 | 2022-10-17 22:00 | 2022-10-31 15:00 | Complete
Petani | PETA23_P16 | Petani 00161 | S1-O-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTM2/402/3220814DR | 2022-10-31 15:00 | 2022-11-18 19:30 | 2022-12-08 11:00 | Complete
Petani | PETA22-P17 | Petani 00164 | O-O-74B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTJ2/402/3220810DR | 2022-12-08 11:00 | 2022-12-15 05:00 | 2023-01-03 12:00 | Complete
Pager | PG22-P01 | Pager 00053 | O-O-65B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220334DR | 2023-01-03 12:00 | 2023-01-13 09:00 | 2023-01-28 19:30 | Complete
Pager | PG22-P05 | Pager 00055 | O-O-54C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220354DR | 2023-01-28 19:30 | 2023-02-04 | 2023-02-28 10:00 | Complete
Pematang | PMT-P11 | Pematang 00118 | O-O-62C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220391DR | 2023-02-28 10:00 | 2023-03-10 13:30 | 2023-03-30 10:15 | Complete
Petani | PETA22-INJ5 | Petani 00170 | N1-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220916DR | 2023-03-30 10:15 | 2023-04-09 10:30 | 2023-05-03 17:00 | Complete
Petani | PETA23_P03 | Petani 00172 | N1-O-81A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220905DR | 2023-05-03 17:00 | 2023-05-10 18:00 | 2023-05-26 22:00 | Complete
Petani | PETA23_P11 | Petani 00175 | O-O-56A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230296DR | 2023-05-26 22:00 | 2023-06-02 20:00 | 2023-06-18 10:00 | Complete
Petani | PETA23-P31 | Petani 00177 | O-O-56B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220915DR | 2023-06-18 10:00 | 2023-06-22 01:30 | 2023-07-09 22:00 | Complete
Petani | PETA23B-P04 | Petani 00180 | O-O-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230297DR | 2023-07-09 22:00 | 2023-07-19 21:00 | 2023-08-06 11:00 | Complete
Petani | PT22_P25 | Petani 00183 | O-O-74C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230295DR | 2023-08-06 11:00 | 2023-08-12 04:00 | 2023-08-26 17:00 | Complete
Petani | PT22_P22 | Petani 00186 | O-O-74D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230294DR | 2023-08-26 17:00 | 2023-08-29 20:30 | 2023-09-13 14:00 | Complete
Petani | PETA-BK3140-P04 | Petani 00188 | O-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220911DR | 2023-09-13 14:00 | 2023-09-20 05:00 | 2023-10-14 | Complete
Petani | PETA23B-P01 | Petani 00195 | O-O-33C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220899DR | 2023-10-14 | 2023-10-19 02:00 | 2023-11-05 03:15 | Complete
Petani | PETA_BK3140_P01 | Petani 00199 | O-O-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220909DR | 2023-11-05 03:15 | 2023-11-13 21:00 | 2023-12-09 | Complete
Petani | PETA_BK3140_P03 | Petani 00200 | O-O-52C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220910DR | 2023-12-09 | 2023-12-14 12:00 | 2024-02-19 08:00 | Complete
Petani | PETA22-P16 | Petani 00201 | O-O-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230299DR | 2024-02-19 08:00 | 2024-02-29 22:00 | 2024-04-15 | Complete
Petani | PETA22-P29 | Petani 00203 | O-O-85I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220907DR | 2024-04-15 | 2024-04-19 02:00 | 2024-05-31 07:30 | Complete
Kopar | KPR-X10_OPT | Kopar 00047 | S1-O-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTO2/402/3240789DR | 2024-05-31 07:30 | 2024-06-18 08:00 | 2024-07-06 10:00 | Complete
Petani | P_PETA24_25 | Petani 00211 | O-O-32F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTO2/402/3230917DR | 2024-07-06 10:00 | 2024-07-14 04:00 |  | In Progress
Kopar | KPR-X16_OPT | Kopar 00046 | O-O-84C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-60 | PTO2/402/3240791DR | 2024-07-12 21:00 | 2024-07-12 21:00 |  | In Progress
Hiu | P_HIU24_11 | Hiu 00010 | O-W2-52A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-61 | SPS2/402/3240900DR | 2024-07-09 03:00 | 2024-07-09 03:00 |  | In Progress
Petani | PETA22-P24 | Petani 00153 | O-W1-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-87 | GRK2/402/2220257DR | 2022-10-13 09:00 | 2022-10-17 04:00 | 2022-10-24 20:00 | Complete
Petani | PTN-X06 | Petani 00145 | O-O-43C | Perforation | PRF01 - Regular Perforation | Land Workover Unit | BDSI-87 | GRK2/402/2220249DR | 2022-11-23 04:00 | 2022-11-25 20:00 | 2022-12-02 15:00 | Complete
Petani | PETA23B-P01 | Petani 00195 | O-O-33C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-87 | SSA2/402/3220899DR | 2023-11-26 13:30 | 2023-11-27 21:30 | 2023-12-06 06:30 | Complete
Petani | PETA22-INJ3 | Petani 00189 | S1-O-15C | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BDSI-87 | SSA2/402/3220917DR | 2024-07-04 13:30 | 2024-07-05 05:30 | 2024-07-11 08:00 | Complete
Minas | P_6C-21N | Minas 02018 | 6C-21N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220514DR | 2022-09-25 11:00 | 2022-09-30 20:30 | 2022-10-07 10:30 | Complete
Minas | MNS-P03 | Minas 02014 | 9C-66 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220510DR | 2022-11-20 13:00 | 2022-11-22 02:00 | 2022-11-29 | Complete
Minas | P_7E-94E1 | Minas 02035 | 7E-94E1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220378DR | 2023-03-29 | 2023-03-30 15:00 | 2023-04-04 11:00 | Complete
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Pump Repair | PMP05 - Rod Pump Not Pumping Normal | Land Workover Unit | BDSI-94 | SSO2/402/3220373DR | 2022-12-31 18:00 | 2023-01-02 12:00 | 2023-01-05 | Complete
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-94 | SSE2/402/3230314DR | 2024-04-09 10:30 | 2024-04-12 | 2024-04-16 | Complete
Kotabatak | KOTA21_P_TE_2A | Kotabatak 00457 | N1-W1-42A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210100DR | 2021-10-12 06:00 | 2021-10-12 13:00 | 2021-10-19 | Complete
Kotabatak | KOTA21_P_TE_INJ_1 | Kotabatak 00458 | N1-W1-46A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | GRK2/402/3210102DR | 2021-10-28 | 2021-10-28 12:00 | 2021-11-24 | Complete
Kotabatak | KOTA21_P_TE_B2 | Kotabatak 00459 | N1-W1-84E | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210098DR | 2021-11-24 | 2021-11-26 22:00 | 2021-12-09 | Complete
Kotabatak | KOTA21_P_TE_B3 | Kotabatak 00460 | N1-W1-55 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210097DR | 2021-12-09 | 2021-12-10 05:00 | 2021-12-17 18:00 | Complete
Kotabatak | KOTA21_P_TE_2B | Kotabatak 00461 | N1-W1-46B | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210099DR | 2021-12-17 18:00 | 2021-12-18 17:30 | 2021-12-26 20:00 | Complete
Kotabatak | KTB-P2 | Kotabatak 00463 | S1-E1-72 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210104DR | 2022-01-07 | 2022-01-07 08:00 | 2022-01-18 11:00 | Complete
Kotabatak | KTB-X04 | Kotabatak 00467 | N1-O-73A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/2210131DR | 2022-01-22 08:00 | 2022-01-22 14:30 | 2022-01-28 19:00 | Complete
Kotabatak | KOTA21_P_TE_A2 | Kotabatak 00462 | N1-W1-59 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210095DR | 2022-02-08 11:00 | 2022-02-08 21:00 | 2022-02-16 11:00 | Complete
Kotabatak | KOTA21_P_TE_B1 | Kotabatak 00464 | N1-W1-60 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210096DR | 2022-02-16 11:00 | 2022-02-17 08:00 | 2022-02-28 11:00 | Complete
Kotabatak | KTB-X15 | Kotabatak 00468 | O-O-53A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210150DR | 2022-02-28 11:00 | 2022-03-01 19:00 | 2022-03-07 18:00 | Complete
Kotabatak | KTB-X16 | Kotabatak 00471 | O-O-34 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3220166DR | 2022-03-21 09:00 | 2022-03-21 17:00 | 2022-03-29 19:00 | Complete
Kotabatak | KTB-X21 | Kotabatak 00475 | O-O-76 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220164DR | 2022-04-30 19:00 | 2022-05-01 01:00 | 2022-05-07 12:00 | Complete
Kotabatak | KTB-X27 | Kotabatak 00472 | N1-W1-27 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220167DR | 2022-05-20 07:00 | 2022-05-20 19:00 | 2022-05-26 20:00 | Complete
Kotabatak | KTB-X22 | Kotabatak 00480 | O-O-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220175DR | 2022-06-12 19:00 | 2022-06-13 03:00 | 2022-06-19 09:00 | Complete
Kotabatak | KTB-X18 | Kotabatak 00470 | O-O-13 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3220165DR | 2022-06-23 10:00 | 2022-06-23 20:00 | 2022-06-30 02:30 | Complete
Kotabatak | KTB-X13 | Kotabatak 00478 | O-W1-32 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220172DR | 2022-06-30 02:30 | 2022-06-30 09:00 | 2022-07-07 14:00 | Complete
Kotabatak | KTB-X12 | Kotabatak 00482 | O-W1-12 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220171DR | 2022-07-07 14:00 | 2022-07-07 22:30 | 2022-07-14 14:30 | Complete
Kotabatak | KTB-X07 | Kotabatak 00481 | N1-W1-34 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220176DR | 2022-07-28 | 2022-07-28 14:00 | 2022-08-09 17:00 | Complete
Kotabatak | KTB-X25 | Kotabatak 00477 | N1-O-69 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220174DR | 2022-08-11 11:00 | 2022-08-11 20:00 | 2022-08-19 20:30 | Complete
Kotabatak | KTB-X28 | Kotabatak 00474 | O-W1-63 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220168DR | 2022-08-19 20:30 | 2022-08-20 07:00 | 2022-08-28 19:00 | Complete
Kotabatak | KB_PL10 Inj | Kotabatak 00492 | N1-W1-78 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220325DR | 2022-10-17 16:00 | 2022-10-17 23:00 | 2022-10-27 08:30 | Complete
Kotabatak | KTB-X17 | Kotabatak 00485 | O-O-39 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220180DR | 2022-10-27 08:30 | 2022-10-27 21:30 | 2022-11-08 09:30 | Complete
Kotabatak | KTB-X08 | Kotabatak 00493 | N1-W2-59 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220513DR | 2022-11-08 09:30 | 2022-11-09 03:00 | 2022-11-16 02:00 | Complete
Kotabatak | KTB-X02 | Kotabatak 00489 | N1-E1-73 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220182DR | 2022-11-16 02:00 | 2022-11-17 02:30 | 2022-11-27 15:00 | Complete
Kotabatak | KB_PL4 | Kotabatak 00487 | O-W2-17 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/2220253DR | 2022-11-27 15:00 | 2022-11-27 22:00 | 2022-12-05 04:00 | Complete
Kotabatak | KB_PL18 Inj | Kotabatak 00491 | N1-O-76 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220507DR | 2022-12-10 10:30 | 2022-12-12 14:00 | 2022-12-20 21:30 | Complete
Kotabatak | KB_PL19 | Kotabatak 00499 | S1-O-19 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220367DR | 2022-12-20 21:30 | 2022-12-21 13:00 | 2022-12-31 18:00 | Complete
Kotabatak | KB_PL45 | Kotabatak 00495 | N1-W2-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220534DR | 2022-12-31 18:00 | 2023-01-02 17:00 | 2023-01-11 17:00 | Complete
Kotabatak | KB_PL32 Inj | Kotabatak 00502 | O-E1-34 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220370DR | 2023-01-11 17:00 | 2023-01-12 09:30 | 2023-01-21 12:00 | Complete
Kotabatak | KB_PL43 | Kotabatak 00498 | N1-W2-54 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220423DR | 2023-01-21 12:00 | 2023-01-24 05:30 | 2023-02-01 | Complete
Kotabatak | KB_PL47 Inj | Kotabatak 00501 | N1-W2-36 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220537DR | 2023-02-01 | 2023-02-01 08:00 | 2023-02-20 05:00 | Complete
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220522DR | 2023-02-23 | 2023-02-23 18:00 | 2023-02-27 05:00 | Complete
Kotabatak | KB_PL12 | Kotabatak 00496 | S1-O-22 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220345DR | 2023-05-04 18:00 | 2023-05-05 04:00 | 2023-05-12 18:00 | Complete
Kotabatak | KB_PL37 | Kotabatak 00500 | O-O-79 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220338DR | 2023-05-12 18:00 | 2023-05-13 07:00 | 2023-05-23 | Complete
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220360DR | 2023-06-02 | 2023-06-02 10:00 | 2023-06-05 10:00 | Complete
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220625DR | 2023-06-05 10:00 | 2023-06-06 11:00 | 2023-06-09 09:00 | Complete
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220627DR | 2023-06-09 09:00 | 2023-06-09 20:00 | 2023-06-12 21:00 | Complete
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230384DR | 2023-06-12 21:00 | 2023-06-13 02:00 | 2023-06-16 | Complete
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230386DR | 2023-06-16 | 2023-06-16 05:00 | 2023-06-18 11:00 | Complete
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220624DR | 2023-06-18 11:00 | 2023-06-19 01:00 | 2023-06-21 04:00 | Complete
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220380DR | 2023-06-21 04:00 | 2023-06-21 12:00 | 2023-06-24 13:00 | Complete
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220624DR | 2023-07-16 | 2023-06-19 01:00 | 2023-07-22 18:00 | Complete
Kotabatak | KTB-A271 | Kotabatak 00514 | S1-E1-12 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230385DR | 2023-07-22 18:00 | 2023-07-23 03:00 | 2023-07-30 | Complete
Kotabatak | KTB-A128 | Kotabatak 00524 | S1-E1-18 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230383DR | 2023-07-30 | 2023-07-31 | 2023-08-08 | Complete
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220628DR | 2023-09-02 | 2023-09-02 08:00 | 2023-09-05 03:00 | Complete
Kotabatak | KTB-X35-INJ | Kotabatak 00533 | N1-O-88 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220455DR | 2023-09-05 03:00 | 2023-09-05 12:00 | 2023-09-13 02:30 | Complete
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220628DR | 2023-09-13 02:30 | 2023-09-02 08:00 | 2023-09-18 20:00 | Complete
Kotabatak | KTB-X33-INJ | Kotabatak 00530 | O-W2-29 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230382DR | 2023-09-18 20:00 | 2023-09-19 08:00 | 2023-09-25 12:00 | Complete
Kotabatak | KB_PL34 | Kotabatak 00531 | O-W1-13 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230392DR | 2023-09-25 12:00 | 2023-09-25 20:00 | 2023-10-02 12:00 | Complete
Kotabatak | KTB-X34-INJ | Kotabatak 00532 | O-W1-20 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230389DR | 2023-10-02 12:00 | 2023-10-03 02:00 | 2023-10-09 12:00 | Complete
Kotabatak | KTB-X37-INJ | Kotabatak 00528 | S1-W1-47 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230396DR | 2023-10-09 12:00 | 2023-10-10 | 2023-10-17 | Complete
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2023-10-26 | 2023-10-26 12:00 | 2023-10-29 16:00 | Complete
Kotabatak | KB_PL39 | Kotabatak 00521 | N1-W1-63 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220393DR | 2023-10-29 16:00 | 2023-10-31 20:00 | 2023-11-06 14:00 | Complete
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Remedial Liner | RLN06 - Install Liner-Cementing | Land Workover Unit | BMS-02 | SSO2/402/3220629DR | 2023-11-06 14:00 | 2023-11-07 01:30 | 2023-11-18 04:00 | Complete
Kotabatak | KTB-X24 | Kotabatak 00539 | N1-W2-78 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230426DR | 2023-11-18 04:00 | 2023-11-18 20:00 | 2023-11-27 18:00 | Complete
Kotabatak | KB_PL3 | Kotabatak 00540 | O-W2-25 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230420DR | 2024-01-08 08:00 | 2024-01-10 17:00 | 2024-01-26 18:00 | Complete
Kotabatak | KB_PL44 | Kotabatak 00520 | N1-W1-41 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220392DR | 2024-02-02 06:00 | 2024-02-02 17:00 | 2024-02-10 | Complete
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2024-02-10 | 2023-10-26 12:00 | 2024-02-15 09:00 | Complete
Kotabatak | KB_PL33 Inj | Kotabatak 00522 | N1-W1-64 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220424DR | 2024-02-15 09:00 | 2024-02-18 01:00 | 2024-02-26 11:00 | Complete
Kotabatak | KB_PL38 | Kotabatak 00542 | O-O-73 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230429DR | 2024-02-26 11:00 | 2024-02-27 15:00 | 2024-03-05 12:00 | Complete
Kotabatak | KB_PL41 | Kotabatak 00545 | O-E1-80 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230410DR | 2024-03-05 12:00 | 2024-03-06 03:00 | 2024-03-15 | Complete
Kotabatak | KTB-A223 | Kotabatak 00544 | O-E1-51 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230412DR | 2024-03-15 | 2024-03-16 | 2024-03-23 12:00 | Complete
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Logging | LOG14 - Run Temperature And CBL/ USIT Log | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-03-23 12:00 |  |  | Suspended
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-03-23 12:00 | 2024-03-24 08:00 | 2024-03-26 10:00 | Complete
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230394DR | 2024-03-26 10:00 | 2024-04-09 13:00 | 2024-03-29 10:00 | Complete
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230394DR | 2024-04-09 04:00 | 2024-04-09 13:00 | 2024-04-15 19:00 | Complete
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-04-15 19:00 | 2024-03-24 08:00 | 2024-04-23 19:00 | Complete
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Land Workover Unit | BMS-02 | SSO2/402/3220629DR | 2024-05-05 15:00 | 2024-04-18 22:00 | 2024-05-09 08:00 | In Progress
Kotabatak | KTB-A268_INJ | Kotabatak 00553 | N1-W1-15B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SKB2/402/3230438DR | 2024-06-05 22:00 | 2024-06-06 08:00 | 2024-06-13 12:00 | Complete
Kotabatak | KTB-A125 | Kotabatak 00554 | O-E1-79 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230421DR | 2024-06-13 12:00 | 2024-06-14 | 2024-06-22 12:00 | Complete
Kotabatak | KTB-A207_INJ | Kotabatak 00555 | O-E1-78 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SKB2/402/3230436DR | 2024-06-22 12:00 | 2024-06-23 16:30 | 2024-07-01 04:00 | Complete
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2024-07-01 04:00 | 2023-10-26 12:00 | 2024-07-12 13:00 | Complete
Kotabatak | KTB-A023 | Kotabatak 00546 | O-W1-55 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230418DR | 2024-07-12 13:00 | 2024-07-12 23:00 |  | In Progress
Petapahan | PTP BL2-P19 | Petapahan 00162 | N1-W1-64A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSO2/402/3220660DR | 2023-02-25 10:00 | 2023-02-25 22:00 | 2023-03-01 | Complete
Petapahan | PTP_SO_P01 | Petapahan 00165 | N2-W2-87A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSA2/402/3230152DR | 2023-09-22 03:00 | 2023-09-22 21:00 | 2023-10-01 11:00 | Complete
Petapahan | PTP BL2-Z10 | Petapahan 00167 | N1-W2-28C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSA2/402/3220884DR | 2024-03-24 | 2024-03-24 19:00 | 2024-04-04 18:00 | Complete
Petapahan | PTP BL2-Z09 | Petapahan 00172 | N1-W1-44E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSO2/402/3220411DR | 2024-06-18 12:00 | 2024-06-19 10:00 | 2024-06-29 17:00 | Complete
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-05 | GRK2/402/2210123DR | 2021-11-15 22:30 | 2021-11-16 08:00 | 2021-11-16 16:30 | Complete
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220372DR | 2023-09-21 | 2023-09-21 20:30 | 2023-09-23 07:30 | Complete
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220372DR | 2023-10-20 21:30 | 2023-09-21 20:30 | 2023-10-25 07:30 | Complete
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220554DR | 2023-10-28 13:30 | 2023-10-29 19:00 | 2023-11-01 04:30 | Complete
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220554DR | 2023-11-11 06:00 | 2023-10-29 19:00 | 2023-11-14 19:00 | Complete
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220588DR | 2023-11-14 19:00 | 2023-11-15 21:00 | 2023-11-18 10:30 | Complete
Bangko | WFE-BNK_5 | Bangko 00423 | N2-W1-51A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-05 | SSM2/402/3230286DR | 2024-02-25 04:30 | 2024-02-25 22:00 | 2024-02-28 21:00 | Complete
Bangko | WFE-BNK_4 | Bangko 00429 | O-O-33B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-05 | SSM2/402/3230284DR | 2024-03-24 17:30 | 2024-03-25 15:30 | 2024-03-28 16:30 | Complete
Bangko | BNK23_P24 | Bangko 00427 | N1-W2-54B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSM2/402/3230274DR | 2024-04-05 08:30 | 2024-04-06 01:00 | 2024-04-10 05:00 | Complete
Bangko | BNK23_P08 | Bangko 00430 | O-O-52B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSM2/402/3230275DR | 2024-04-12 02:00 | 2024-04-12 21:00 | 2024-04-28 08:30 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220383DR | 2024-06-09 19:00 | 2024-06-10 17:00 | 2024-06-12 17:00 | In Progress
Bangko | BNK_P244A_LQR | Bangko 00414 | N1-W3-41A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220398DR | 2024-06-14 22:00 | 2024-06-15 22:00 | 2024-06-19 06:30 | Complete
Bangko | BNK_P277B_LQR | Bangko 00409 | N1-W4-18A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220366DR | 2024-06-21 22:00 | 2024-06-23 05:00 | 2024-07-10 16:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220383DR | 2024-07-10 16:00 | 2024-06-10 17:00 |  | In Progress
Bekasap | BKS-P16 | Bekasap 00208 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2210017DR | 2022-01-21 17:30 | 2022-01-22 20:00 | 2022-02-04 10:30 | Complete
Petani | PTN-P1 | Petani 00134 | N1-W1-57A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Land Workover Unit | BMS-06 | GRK2/402/2210141DR | 2022-02-03 12:00 |  |  | Suspended
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2210018DR | 2022-02-10 | 2022-02-12 | 2022-02-16 | Complete
Bekasap | BKS-X10 | Bekasap 00218 | O-E1-43B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-06 | GRK2/402/2220286DR | 2022-06-04 11:00 | 2022-06-04 23:00 | 2022-06-05 11:00 | Complete
Bekasap | BKS-X14 | Bekasap 00220 | O-E1-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2220275DR | 2022-09-10 12:00 | 2022-09-11 02:00 | 2022-09-26 | Complete
Pematang | PMT-P05 | Pematang 00111 | O-O-53A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-07 | SSO2/402/3220364DR | 2022-12-14 07:00 | 2022-12-17 17:30 | 2023-01-03 | Complete
Sidingin North | Exp_P02_Sidingin | Sidingin North 00001 | O-O-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-07 | SDN2/402/2220001EX | 2023-07-31 20:00 | 2023-08-06 11:00 | 2023-10-02 14:30 | Complete
Astrea | Astrea-1 | Astrea 00001 | O-O-44 | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-07 | AST2/402/3230001EX | 2024-06-25 12:00 | 2024-06-30 02:00 |  | In Progress
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210149DR | 2022-02-15 09:00 | 2022-02-15 20:30 | 2022-02-23 | Complete
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210149DR | 2022-03-18 22:00 | 2022-02-15 20:30 | 2022-03-25 07:00 | Complete
Kotabatak | KTB-X23 | Kotabatak 00466 | S1-O-17 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210101DR | 2022-03-25 07:00 | 2022-03-25 12:30 | 2022-04-02 12:00 | Complete
Kotabatak | KTB-X05 | Kotabatak 00476 | O-O-18 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220173DR | 2022-04-02 12:00 | 2022-04-02 23:00 | 2022-04-14 04:00 | Complete
Kotabatak | KTB-X03 | Kotabatak 00473 | N1-O-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3210103DR | 2022-06-14 14:00 | 2022-06-14 22:00 | 2022-06-23 20:00 | Complete
Kotabatak | KTB-X09 | Kotabatak 00469 | N1-W1-25A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220169DR | 2022-07-18 09:00 | 2022-07-18 23:00 | 2022-07-25 22:00 | Complete
Kotabatak | KTB-X06 | Kotabatak 00479 | S1-O-12A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220170DR | 2022-07-25 22:00 | 2022-07-26 22:00 | 2022-08-05 14:00 | Complete
Kotabatak | KTB-X30 | Kotabatak 00484 | S1-W1-46 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220178DR | 2022-08-06 15:30 | 2022-08-06 15:30 | 2022-08-17 21:00 | Complete
Kotabatak | KB_PL2 Inj | Kotabatak 00486 | O-W2-15 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-08 | GRK2/402/2220261DR | 2022-08-26 09:00 | 2022-08-26 17:00 | 2022-09-03 | Complete
Kotabatak | KB_PL5 Inj | Kotabatak 00490 | N1-W2-76 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-08 | GRK2/402/3220191DR | 2022-09-28 20:00 | 2022-09-29 05:00 | 2022-10-10 08:00 | Complete
Minas | P_6D-53N | Minas 02033 | 6D-53N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220350DR | 2023-01-31 03:30 | 2023-02-01 02:30 | 2023-02-07 06:00 | Complete
Minas | P_6C-89E | Minas 02034 | 6C-89E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220387DR | 2023-03-03 05:00 | 2023-03-06 00:30 | 2023-03-10 17:30 | Complete
Minas | P_7E-14 | Minas 02041 | 7E-14 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220637DR | 2023-03-27 10:30 | 2023-03-28 14:00 | 2023-04-10 | Complete
Minas | P_10C-26 | Minas 02050 | 10C-26 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220646DR | 2023-05-07 21:00 | 2023-05-08 17:30 | 2023-05-13 | Complete
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230246DR | 2023-07-15 06:00 | 2023-07-15 16:00 | 2023-07-25 06:00 | Complete
Minas | MNS-P21 | Minas 02075 | 9D-48E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230216DR | 2023-08-19 16:00 | 2023-08-21 15:00 | 2023-08-25 09:00 | Complete
Minas | P_4C-35E | Minas 02074 | 4C-35E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230220DR | 2023-09-14 14:30 | 2023-09-15 11:00 | 2023-09-18 15:00 | Complete
Minas | P_4C-45N1 | Minas 02079 | 4C-45N1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230225DR | 2023-09-18 15:00 | 2023-09-19 08:00 | 2023-09-27 14:00 | Complete
Minas | P_4C-46 | Minas 02080 | 4C-46 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230222DR | 2023-09-27 14:00 | 2023-09-28 01:00 | 2023-10-02 12:00 | Complete
Seruni | SRN-P1 | Seruni 00054 | N2-W3-47A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | GRK2/402/2210161DR | 2022-01-20 21:00 | 2022-01-21 13:30 | 2022-01-26 19:00 | Complete
Seruni | SRN-P3 | Seruni 00055 | N2-W3-34A | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-11 | GRK2/402/2210163DR | 2022-02-06 | 2022-02-11 23:00 | 2022-03-02 21:00 | Complete
Seruni | SRN-P14 | Seruni 00057 | N1-W2-31B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-11 | GRK2/402/2220276DR | 2022-06-06 13:00 | 2022-06-07 16:00 | 2022-06-08 04:00 | Complete
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | GRK2/402/2220061DR | 2022-09-06 08:00 | 2022-09-07 02:00 | 2022-09-10 | Complete
Bangko | BNK_P5A_LQR | Bangko 00415 | N2-W1-85A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220389DR | 2022-11-24 06:00 | 2022-11-26 02:00 | 2022-12-04 | Complete
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220425DR | 2023-05-12 | 2023-05-13 02:00 | 2023-05-14 08:00 | Complete
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220450DR | 2023-05-14 08:00 | 2023-05-15 02:00 | 2023-05-16 10:00 | Complete
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220419DR | 2023-05-16 10:00 | 2023-05-17 | 2023-05-18 | Complete
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220348DR | 2023-05-18 | 2023-05-19 08:00 | 2023-05-20 08:00 | Complete
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220359DR | 2023-05-20 08:00 | 2023-05-21 08:00 | 2023-05-22 | Complete
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220425DR | 2023-05-22 | 2023-05-13 02:00 | 2023-05-27 | Complete
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220419DR | 2023-05-27 | 2023-05-17 | 2023-05-31 | Complete
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220450DR | 2023-05-31 | 2023-05-15 02:00 | 2023-06-03 05:00 | Complete
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220348DR | 2023-06-03 05:00 | 2023-05-19 08:00 | 2023-06-06 10:00 | Complete
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220437DR | 2023-06-12 19:00 | 2023-06-13 12:00 | 2023-06-14 15:00 | Complete
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220377DR | 2023-06-14 15:00 | 2023-06-15 03:00 | 2023-06-16 | Complete
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220434DR | 2023-06-19 17:00 | 2023-06-05 14:00 | 2023-06-23 | Complete
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220437DR | 2023-06-28 | 2023-06-13 12:00 | 2023-07-02 | Complete
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220377DR | 2023-07-04 19:00 | 2023-06-15 03:00 | 2023-07-09 20:00 | Complete
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220359DR | 2023-07-09 20:00 | 2023-05-21 08:00 | 2023-07-18 13:00 | Complete
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220407DR | 2023-07-18 13:00 | 2023-07-20 02:00 | 2023-07-21 07:00 | Complete
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220440DR | 2023-07-26 | 2023-07-27 | 2023-07-28 20:00 | Complete
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220407DR | 2023-07-30 14:30 | 2023-07-20 02:00 | 2023-08-01 10:00 | Complete
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220373DR | 2023-09-24 19:00 | 2023-09-25 14:00 | 2023-09-28 06:00 | Complete
Balam So | LQR-TE003_BLSO_41 | Balam So 00553 | N1-W1-73B | Clean-Out | CLO03 - Clean/ Bail Out Sand | Land Workover Unit | BMS-11 | SSO2/402/3220583DR | 2024-02-03 | 2024-02-03 18:00 | 2024-02-04 17:00 | Complete
Balam So | LQR-TE012_BLSO_34 | Balam So 00559 | N1-W1-66E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220357DR | 2024-02-04 17:00 | 2024-02-06 14:00 | 2024-02-09 19:00 | Complete
Balam So | LQR-TE212_BLSO_52 | Balam So 00558 | N1-W1-66D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230368DR | 2024-02-09 19:00 | 2024-02-10 15:00 | 2024-02-12 | Complete
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230364DR | 2024-02-25 20:30 | 2024-02-26 20:00 | 2024-02-28 08:00 | Complete
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220588DR | 2024-03-06 | 2023-11-15 21:00 | 2024-03-10 14:00 | Complete
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230364DR | 2024-03-10 14:00 | 2024-02-26 20:00 | 2024-03-14 16:30 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220548DR | 2024-03-14 16:30 | 2024-05-05 05:00 | 2024-03-16 07:00 | Complete
Balam So | BLSO23-LQR-TE040 | Balam So 00531 | N1-W1-34A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220586DR | 2024-03-18 03:00 | 2024-03-19 04:00 | 2024-03-26 03:00 | Complete
Balam So | BLSO23-LQR-TE019 | Balam So 00532 | O-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220587DR | 2024-03-21 | 2024-03-27 | 2024-04-02 | Complete
Balam So | BLSO23-LQR-TE024 | Balam So 00537 | O-O-75A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220439DR | 2024-04-02 | 2024-04-03 | 2024-04-08 17:00 | Complete
Balam So | BLSO23-LQR-TE068 | Balam So 00536 | O-O-75B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220406DR | 2024-04-08 17:00 | 2024-04-09 15:00 | 2024-04-16 | Complete
Balam So | BLSO23-LQR-TE042 | Balam So 00539 | O-O-77B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230349DR | 2024-04-19 | 2024-04-20 |  | Complete
Balam So | BLSO23-LQR-TE050 | Balam So 00549 | N1-W1-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230336DR | 2024-04-26 | 2024-04-27 11:00 | 2024-05-03 07:30 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220548DR | 2024-05-03 07:30 | 2024-05-05 05:00 | 2024-05-08 05:00 | Complete
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220416DR | 2024-05-19 08:00 | 2024-05-20 02:00 | 2024-05-21 16:00 | Complete
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230350DR | 2024-05-24 17:00 | 2024-05-25 10:00 | 2024-05-27 18:00 | Suspended
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230355DR | 2024-06-11 11:00 | 2024-06-12 16:00 | 2024-06-14 20:00 | Suspended
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220416DR | 2024-06-14 20:00 | 2024-05-20 02:00 | 2024-06-20 | Complete
Balam So | BLSO23-LQR-TE065 | Balam So 00545 | N1-O-21A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230343DR | 2024-06-27 | 2024-06-27 23:00 | 2024-07-03 09:00 | Complete
Balam So | BLSO23-LQR-TE046 | Balam So 00552 | O-O-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230351DR | 2024-07-03 09:00 | 2024-07-04 07:00 | 2024-07-09 06:30 | Complete
Petani | PTN-X09 | Petani 00139 | O-O-68A | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-15 | GRK2/402/2220245DR | 2022-05-26 11:00 | 2022-05-27 22:00 | 2022-06-10 16:00 | Complete
Petani | PTN-X11 | Petani 00144 | S1-O-26C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | GRK2/402/2220250DR | 2022-06-24 21:00 | 2022-06-26 14:30 | 2022-07-07 07:00 | Complete
Bekasap | BKS-X12 | Bekasap 00222 | O-O-48B | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-15 | SSO2/402/3220332DR | 2022-11-22 19:00 | 2022-11-26 05:00 | 2022-12-09 04:00 | Complete
Pematang | PMT-P17 | Pematang 00113 | O-O-52E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSO2/402/3220344DR | 2022-12-29 | 2022-12-29 13:00 | 2023-01-23 16:00 | Complete
Libo Se | LISE23_CC16 | Libo Se 00058 | S1-E4-86 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSV2/402/3230628DR | 2023-11-10 | 2023-11-13 02:00 | 2023-11-26 19:00 | Complete
Libo Se | LISE23_SC03 | Libo Se 00059 | S2-W3-67A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSV2/402/3230657DR | 2024-04-04 12:00 | 2024-04-05 19:00 | 2024-04-16 12:00 | Complete
Duri | 6F-1102B | Duri 10994 | 6F-1102B | Pump Repair | PMP09 - Rod Pump Stuck Normal | Land Workover Unit | BMS-16 | RHO2/402/2220471DR | 2023-01-15 10:30 | 2023-01-15 22:00 | 2023-01-16 15:30 | Complete
Petani | PETA22-P06 | Petani 00152 | O-O-54C | Perforation | PRF01 - Regular Perforation | Land Workover Unit | BMS-17 | GRK2/402/2220254DR | 2022-09-19 16:00 | 2022-09-20 05:00 | 2022-09-30 13:00 | Complete
Petani | PETA22-INJ2 | Petani 00155 | S1-E1-33B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-17 | SSO2/402/3220502DR | 2022-10-10 23:00 | 2022-10-11 19:00 | 2022-10-21 | Complete
Petani | PETA22-INJ4 | Petani 00156 | N1-W1-25A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-17 | SSO2/402/3220505DR | 2022-10-27 03:00 | 2022-10-29 21:00 | 2022-11-08 10:30 | Complete
Petani | PTN-X09 | Petani 00139 | O-O-68A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | BMS-18 | GRK2/402/2220245DR | 2022-07-23 21:00 | 2022-07-24 12:30 | 2022-07-28 18:00 | Complete
Petani | PTN-X09 | Petani 00139 | O-O-68A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | BMS-18 | GRK2/402/2220245DR | 2022-08-03 13:30 | 2022-07-24 12:30 | 2022-08-12 12:00 | Complete
Petani | PETA22-INJ5 | Petani 00170 | N1-W1-27A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3220916DR | 2023-07-13 12:30 | 2023-07-14 02:00 | 2023-07-29 21:30 | Complete
Petani | PETA23B-P03 | Petani 00192 | O-O-63E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSM2/402/3230301DR | 2024-03-01 16:00 | 2024-03-03 23:00 | 2024-03-17 13:00 | Complete
Pematang | PMT-P08 | Pematang 00123 | O-O-51A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSA2/402/3220894DR | 2024-03-21 01:00 | 2024-03-21 17:00 | 2024-03-26 | Complete
Kopar | KPR-X20 | Kopar 00040 | O-O-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSO2/402/3220622DR | 2024-04-09 06:30 | 2024-04-09 22:30 | 2024-04-18 21:00 | Complete
Pematang | P_PEMA24_INJ3 | Pematang 00130 | O-O-23B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3230170DR | 2024-04-22 13:00 | 2024-04-23 16:00 | 2024-05-01 | Complete
Pematang | P_PEMA24_INJ6 | Pematang 00131 | O-O-57D | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3230173DR | 2024-05-04 05:00 | 2024-05-05 14:00 | 2024-05-16 07:00 | Complete
Petani | PTN-X03 | Petani 00136 | O-O-11A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220242DR | 2022-01-29 20:00 | 2022-01-29 20:00 | 2022-02-25 07:00 | Complete
Petani | PTN-X04 | Petani 00138 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220244DR | 2022-02-25 07:00 | 2022-03-07 23:00 | 2022-04-03 02:00 | Complete
Petani | PTN-X05 | Petani 00141 | O-O-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220246DR | 2022-04-03 02:00 | 2022-04-09 | 2022-04-30 14:30 | Complete
Petani | PTN-X06 | Petani 00145 | O-O-43C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220249DR | 2022-04-30 14:30 | 2022-05-03 16:00 | 2022-05-25 19:00 | Complete
Petani | PTN-X02 | Petani 00148 | N1-O-72A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220251DR | 2022-05-25 19:00 | 2022-05-30 08:00 | 2022-06-19 05:00 | Complete
Petani | PETA22-P01 | Petani 00149 | N1-O-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220260DR | 2022-06-19 05:00 | 2022-06-23 20:30 | 2022-07-16 06:00 | Complete
Petani | PETA22-P24 | Petani 00153 | O-W1-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220257DR | 2022-07-16 06:00 | 2022-07-21 09:00 | 2022-08-07 | Release
Petani | PETA22-INJ2 | Petani 00155 | S1-E1-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220502DR | 2022-08-07 | 2022-08-12 16:00 | 2022-08-30 15:30 | Release
Petani | PETA22-P08 | Petani 00157 | O-O-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220539DR | 2022-08-30 15:30 | 2022-09-11 | 2022-09-29 22:00 | Complete
Petani | PETA22-P02 | Petani 00160 | O-O-21C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTF2/402/3220459DR | 2022-09-29 22:00 | 2022-10-11 04:00 | 2022-11-08 13:00 | Complete
Petani | PETA23_P17 | Petani 00162 | O-O-32E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTG2/402/3220461DR | 2022-11-08 13:00 | 2022-11-14 | 2022-12-11 02:00 | Complete
Petani | PETA23_P05 | Petani 00163 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTG2/402/3220462DR | 2022-12-11 02:00 | 2022-12-15 13:00 | 2023-01-07 | Complete
Pager | PG22-P17 | Pager 00054 | O-O-22A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220385DR | 2023-01-07 | 2023-01-23 16:00 | 2023-03-09 12:00 | Complete
Pager | PG22-P20 | Pager 00056 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220414DR | 2023-03-09 12:00 | 2023-03-16 07:00 | 2023-04-26 | Complete
Petani | PETA23B-P07 | Petani 00171 | S1-O-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSM2/402/3230292DR | 2023-04-26 | 2023-07-29 23:00 | 2023-08-23 13:00 | Complete
Petani | PETA23B-P09 | Petani 00184 | S1-O-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSM2/402/3230293DR | 2023-08-23 13:00 | 2023-08-31 10:30 | 2023-09-22 18:30 | Complete
Petani | PETA22-P11 | Petani 00190 | S1-O-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTI2/402/3220809DR | 2023-09-22 18:30 | 2023-09-27 09:00 | 2023-10-18 13:00 | Complete
Petani | PETA22-P12 | Petani 00194 | S1-O-88D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSA2/402/3220908DR | 2023-10-18 13:00 | 2023-10-22 13:00 | 2023-11-15 12:00 | Complete
Petani | PETA22-P15 | Petani 00197 | S1-O-88E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSA2/402/3220904DR | 2023-11-15 12:00 | 2023-11-22 08:00 | 2023-12-09 | Complete
Kopar | KPR-X15 | Kopar 00041 | S1-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220620DR | 2023-12-09 | 2024-03-14 22:30 | 2024-01-29 | Complete
Tilan | TILA23-P03 | Tilan 00035 | O-O-27H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220664DR | 2022-12-03 20:00 | 2022-12-03 20:00 | 2023-01-03 20:00 | Complete
Tilan | TILA23-P02 | Tilan 00036 | O-O-27G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220663DR | 2023-01-03 20:00 | 2023-01-08 20:00 | 2023-02-03 02:00 | Complete
Tilan | TILA23-P01 | Tilan 00037 | O-O-25C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220662DR | 2023-02-03 02:00 | 2023-02-11 04:00 | 2023-05-04 21:00 | Complete
Petani | PETA23_P01 | Petani 00169 | N1-W1-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSA2/402/3220906DR | 2023-05-04 21:00 | 2023-05-28 14:00 | 2023-06-20 20:00 | Complete
Petani | PETA23B-P11 | Petani 00176 | S1-E1-33D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSA2/402/3220900DR | 2023-06-20 20:00 | 2023-07-04 02:00 | 2023-07-26 08:30 | Complete
Petani | PETA23B-P12 | Petani 00179 | S1-E1-33C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230303DR | 2023-07-26 08:30 | 2023-07-29 22:00 | 2023-08-23 01:30 | Complete
Petani | PETA23B-P06 | Petani 00185 | O-O-85H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230304DR | 2023-08-23 01:30 | 2023-09-15 21:00 | 2023-10-04 18:00 | Complete
Petani | PETA23B-P05 | Petani 00191 | O-O-85G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTB2/402/3230480DR | 2023-10-04 18:00 | 2023-10-07 12:00 | 2023-10-25 19:30 | Complete
Petani | PETA22-P09 | Petani 00193 | O-O-85D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230305DR | 2023-10-25 19:30 | 2023-10-31 11:00 | 2023-11-13 19:30 | Release
Petani | PETA23B-P08 | Petani 00198 | N1-O-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTB2/402/3230479DR | 2023-11-13 19:30 | 2024-02-09 17:00 | 2024-03-02 21:00 | Complete
Kopar | KPR-X15 | Kopar 00041 | S1-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220620DR | 2024-03-02 21:00 | 2024-03-14 22:30 | 2024-03-31 | Complete
Kopar | KPR-X03 | Kopar 00043 | O-O-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220617DR | 2024-03-31 | 2024-04-09 04:00 | 2024-05-07 | Complete
Kopar | KPR-X04_OPT | Kopar 00045 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTO2/402/3240787DR | 2024-05-07 | 2024-05-10 21:00 | 2024-06-03 | Complete
Kopar | KPR-X11 | Kopar 00048 | S1-O-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220619DR | 2024-06-03 | 2024-06-14 | 2024-07-01 17:00 | Complete
Petani | P_PETA24_33 | Petani 00210 | S1-O-16A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTO2/402/3230898DR | 2024-07-01 17:00 |  |  | In Progress
Sikladi | Sikladi P05 | Sikladi 00027 | O-O-28A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210093DR | 2021-07-28 14:30 | 2021-08-02 16:00 | 2021-08-15 07:00 | Complete
Sikladi | Sikladi P05 | Sikladi 00027 | O-O-28A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210093DR | 2021-08-15 07:00 | 2021-08-15 10:30 | 2021-08-17 04:00 | Complete
Sikladi | SIKL21-P06 | Sikladi 00028 | O-O-28B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210157DR | 2021-08-17 04:00 | 2021-08-19 15:00 | 2021-08-29 22:00 | Complete
Sikladi | SIKL21-P06 | Sikladi 00028 | O-O-28B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210157DR | 2021-08-28 22:00 | 2021-08-28 22:00 | 2021-08-31 | Complete
Sikladi | SIKL21-P07 | Sikladi 00029 | N1-O-86A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210158DR | 2021-08-31 | 2021-09-05 18:00 | 2021-09-16 06:00 | Complete
Sikladi | SIKL21-P07 | Sikladi 00029 | N1-O-86A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210158DR | 2021-09-16 06:00 | 2021-09-16 06:00 | 2021-09-18 02:00 | Complete
Pinang | Pinang P04 | Pinang 00051 | N1-W2-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210135DR | 2021-09-18 02:00 | 2021-09-30 23:00 | 2021-10-15 09:30 | Complete
Pinang | Pinang P06 | Pinang 00052 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210137DR | 2021-10-15 09:30 | 2021-10-19 11:00 | 2021-10-31 13:00 | Complete
Pinang | Pinang P05 | Pinang 00053 | N1-W2-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210136DR | 2021-10-31 13:00 | 2021-11-05 17:00 | 2021-11-18 16:00 | Complete
Pinang | Pinang P07 | Pinang 00054 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210138DR | 2021-11-18 16:00 | 2021-11-24 15:00 | 2021-12-06 20:30 | Complete
Bangko | BNK-P21 | Bangko 00369 | N2-W1-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210049DR | 2021-12-06 20:30 | 2021-12-24 07:00 | 2022-01-02 22:00 | Complete
Bangko | BNK-P8 | Bangko 00381 | N1-W2-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210071DR | 2022-01-02 22:00 | 2022-01-19 07:00 | 2022-01-28 13:00 | Complete
Balam So | BLSO-P08 | Balam So 00450 | O-O-15C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220016DR | 2022-01-28 13:00 | 2022-02-07 12:00 | 2022-02-14 01:00 | Complete
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220010DR | 2022-02-26 21:00 | 2022-02-26 21:00 | 2022-03-06 04:00 | Release
Balam So | BLSO-P15 | Balam So 00456 | O-O-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220005DR | 2022-03-06 04:00 | 2022-03-12 08:15 | 2022-03-18 22:00 | Complete
Balam So | BLSO-P04 | Balam So 00460 | O-O-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220008DR | 2022-03-18 22:00 | 2022-03-20 21:30 | 2022-03-27 14:00 | Complete
Balam So | BLSO-P21 | Balam So 00463 | O-W1-18B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220011DR | 2022-03-27 14:00 | 2022-04-02 08:00 | 2022-04-10 06:30 | Complete
Balam So | BLSO-P22 | Balam So 00467 | O-W1-18C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220017DR | 2022-04-10 06:30 | 2022-04-12 12:00 | 2022-04-19 16:00 | Complete
Balam So | BLSO-P23 | Balam So 00470 | N1-W1-84A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220022DR | 2022-04-19 16:00 | 2022-04-27 10:00 | 2022-05-05 09:00 | Release
Balam So | LQR-TE223_BLSO_30 | Balam So 00473 | N1-W1-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220031DR | 2022-05-05 09:00 | 2022-05-07 17:00 | 2022-05-15 | Complete
Menggala No | MNO-P01 | Menggala No 00049 | N3-W1-14B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220194DR | 2022-05-14 | 2022-05-24 18:00 | 2022-06-10 01:30 | Complete
Menggala No | MNO-P18 | Menggala No 00051 | N3-W1-14A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/3220234DR | 2022-06-10 01:30 | 2022-06-12 12:00 | 2022-06-25 18:00 | Complete
Menggala No | MNO-P15 | Menggala No 00053 | N3-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/3220237DR | 2022-06-25 18:00 | 2022-06-30 23:45 | 2022-07-14 08:00 | Complete
Menggala No | MNO-P02 | Menggala No 00055 | N3-W1-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220195DR | 2022-07-14 08:00 | 2022-07-19 12:30 | 2022-08-05 15:00 | Complete
Menggala No | MNO-P17 | Menggala No 00057 | N3-W1-33C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220068DR | 2022-08-05 15:00 | 2022-08-08 | 2022-08-21 19:00 | Complete
Balam So | BLSO-P41 | Balam So 00485 | O-W1-15G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220317DR | 2022-08-21 19:00 | 2022-09-08 19:00 | 2022-09-15 | Release
Balam So | LQR-TE053_BLSO_15 | Balam So 00493 | N1-O-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220519DR | 2022-09-15 | 2022-09-23 05:30 | 2022-09-29 17:00 | Complete
Pematang | PMT-P05 | Pematang 00111 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220364DR | 2022-09-29 17:00 | 2022-10-20 12:00 | 2022-11-08 12:00 | Release
Pematang | PMT-P19 | Pematang 00112 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220545DR | 2022-11-08 12:00 | 2022-11-11 14:00 | 2022-12-05 13:00 | Complete
Pematang | PMT-P09 | Pematang 00114 | O-W1-26A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220420DR | 2022-12-05 13:00 | 2022-12-11 04:00 | 2023-01-13 20:00 | Complete
Pematang | PMT-P23 | Pematang 00115 | O-W1-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220658DR | 2023-01-13 20:00 | 2023-01-17 08:00 | 2023-02-07 10:00 | Complete
Pematang | PMT-P12 | Pematang 00117 | O-O-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220408DR | 2023-02-07 10:00 | 2023-03-03 06:00 | 2023-04-01 16:00 | Complete
Pematang | PMT-P22 | Pematang 00116 | O-O-52F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220371DR | 2023-04-01 | 2023-04-28 | 2023-05-19 10:00 | Complete
Pematang | PMT-P25 | Pematang 00119 | O-O-52G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220432DR | 2023-05-19 10:00 | 2023-05-22 09:00 | 2023-06-09 22:30 | Complete
Pematang | PMT-P06 | Pematang 00120 | O-O-52D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220893DR | 2023-06-09 22:30 | 2023-06-14 14:00 | 2023-07-03 12:00 | Complete
Pematang | PMT-P04 | Pematang 00121 | O-O-52H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220456DR | 2023-07-03 12:00 | 2023-07-07 18:00 | 2023-07-26 11:00 | Complete
Pematang | PMT-P16 | Pematang 00122 | O-O-52I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220659DR | 2023-07-26 11:00 | 2023-07-29 09:00 | 2023-08-12 16:00 | Complete
Pematang | PMT-P08 | Pematang 00123 | O-O-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220894DR | 2023-08-12 16:00 | 2023-08-18 04:00 | 2023-09-03 | Release
Pematang | PMT-P18 | Pematang 00124 | O-O-51B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220895DR | 2023-09-03 | 2023-09-06 17:30 | 2023-09-26 15:00 | Complete
Pematang | PMT-P24 | Pematang 00125 | O-O-51C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220896DR | 2023-09-26 15:00 | 2023-09-30 23:30 | 2023-10-19 05:00 | Complete
Pematang | PMT-P20 | Pematang 00126 | O-O-51D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220897DR | 2023-10-19 05:00 | 2023-11-30 18:00 | 2023-12-18 05:00 | Complete
Pematang | PMT-P10 | Pematang 00127 | O-O-51E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220898DR | 2023-12-18 05:00 | 2023-12-21 05:00 | 2024-01-15 18:00 | Complete
Pematang | P_PEMA24_INJ6 | Pematang 00131 | O-O-57D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230173DR | 2024-01-15 18:00 | 2024-01-25 21:00 | 2024-02-08 18:00 | Complete
Pematang | P_PEMA24_11 | Pematang 00129 | O-O-51F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230160DR | 2024-02-08 18:00 | 2024-02-15 | 2024-03-01 12:30 | Complete
Pematang | P_PEMA24_INJ1 | Pematang 00133 | N1-W1-86B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230168DR | 2024-03-01 12:30 | 2024-03-07 22:00 | 2024-03-25 08:00 | Complete
Pematang | P_PEMA24_INJ5 | Pematang 00135 | O-O-52N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230172DR | 2024-03-25 08:00 | 2024-04-04 21:30 | 2024-04-26 07:00 | Complete
Bekasap So | P_BESO24_02 | Bekasap So 00016 | S3-O-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSN2/402/3230682DR | 2024-04-26 07:00 | 2024-05-04 16:30 | 2024-05-29 15:00 | Complete
Bekasap So | P_BESO24_04 | Bekasap So 00018 | S2-O-74A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSN2/402/3230681DR | 2024-05-29 15:00 | 2024-06-16 01:30 | 2024-06-28 06:00 | Complete
Pematang | P_PEMA24_04 | Pematang 00139 | O-O-42C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220902DR | 2024-06-28 06:00 | 2024-07-06 |  | In Progress
Bangko | BNK-P3 | Bangko 00348 | N1-W2-17A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210058DR | 2021-08-02 | 2021-08-28 16:00 | 2021-09-07 17:00 | Complete
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210034DR | 2021-08-05 | 2021-08-10 23:30 | 2021-08-17 15:00 | Complete
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-18 | 2210034DR | 2021-08-17 15:00 | 2021-08-17 15:00 | 2021-08-19 | Complete
Bangko | BNK-P3 | Bangko 00348 | N1-W2-17A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-18 | GRK2/402/2210058DR | 2021-09-06 17:00 | 2021-09-06 17:00 | 2021-09-08 08:00 | Complete
Bangko | BNK-P26 | Bangko 00349 | N1-W1-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210054DR | 2021-09-08 08:00 | 2021-09-14 10:00 | 2021-09-22 05:00 | Complete
Bangko | BNK-P34 | Bangko 00351 | N1-W1-76A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210063DR | 2021-09-22 05:00 | 2021-09-28 16:00 | 2021-10-06 10:00 | Complete
Bangko | BNK-P11 | Bangko 00354 | N1-W2-77B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210040DR | 2021-10-06 10:00 | 2021-10-11 08:00 | 2021-10-18 19:00 | Complete
Bangko | BNK-P39 | Bangko 00361 | N2-W2-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210066DR | 2021-10-18 19:00 | 2021-10-23 16:00 | 2021-11-01 | Complete
Bangko | BNK-P10 | Bangko 00356 | N1-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210039DR | 2021-11-01 | 2021-11-08 10:00 | 2021-11-16 07:00 | Release
Bangko | BNK-P7 | Bangko 00365 | N1-W1-51B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210072DR | 2021-11-16 07:00 | 2021-11-18 19:30 | 2021-11-28 22:00 | Complete
Bangko | BNK-P5 | Bangko 00359 | N1-W1-22A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210070DR | 2021-11-28 22:00 | 2021-12-25 01:45 | 2022-01-02 06:00 | Complete
Bangko | BNK-P22 | Bangko 00374 | N1-W1-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210050DR | 2022-01-02 06:00 | 2022-01-04 22:00 | 2022-01-19 15:00 | Complete
Bangko | BNK-P30 | Bangko 00378 | N1-W2-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210059DR | 2022-01-19 15:00 | 2022-01-30 22:00 | 2022-02-09 14:00 | Complete
Bangko | BNK-P1 | Bangko 00382 | N1-W2-17C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220060DR | 2022-02-09 14:00 | 2022-02-12 04:00 | 2022-02-21 18:00 | Complete
Balam So | BLSO-P16 | Balam So 00454 | O-O-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220009DR | 2022-03-12 20:30 | 2022-03-12 20:30 | 2022-03-19 03:30 | Complete
Balam So | BLSO-P02 | Balam So 00459 | O-O-36C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220004DR | 2022-03-19 03:30 | 2022-03-21 | 2022-03-27 01:30 | Complete
Balam So | BLSO-P24 | Balam So 00464 | N1-W1-75A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220027DR | 2022-03-27 01:30 | 2022-04-03 01:30 | 2022-04-11 01:00 | Complete
Balam So | BLSO-P29 | Balam So 00468 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220030DR | 2022-04-11 01:00 | 2022-04-18 | 2022-04-28 | Complete
Balam So | BLSO-P33 | Balam So 00469 | S1-O-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220035DR | 2022-04-28 | 2022-04-30 07:00 | 2022-05-07 15:30 | Complete
Balam So | BLSO-P27 | Balam So 00471 | N1-W1-58B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220029DR | 2022-05-07 15:30 | 2022-05-13 03:00 | 2022-05-26 21:00 | Complete
Balam So | BLSO-P05 | Balam So 00474 | N1-O-66B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220021DR | 2022-05-26 21:00 | 2022-05-31 23:45 | 2022-06-08 05:00 | Complete
Balam So | BLSO-P10 | Balam So 00476 | N1-O-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220006DR | 2022-06-08 05:00 | 2022-06-14 | 2022-06-22 05:15 | Complete
Balam So | LQR-TE036_BLSO_10 | Balam So 00477 | N1-O-83F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220036DR | 2022-06-22 05:15 | 2022-06-24 14:00 | 2022-06-30 08:00 | Complete
Balam So | BLSO-P01 | Balam So 00479 | O-O-34D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220026DR | 2022-06-30 08:00 | 2022-07-08 04:30 | 2022-07-16 14:00 | Complete
Balam So | LQR-TE047_BLSO_53 | Balam So 00480 | S1-O-35A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220053DR | 2022-07-16 14:00 | 2022-07-21 14:00 | 2022-07-29 11:30 | Complete
Balam So | LQR-TE088_BLSO_55 | Balam So 00481 | S1-O-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220057DR | 2022-07-29 11:30 | 2022-08-02 13:00 | 2022-08-09 15:30 | Complete
Balam So | LQR-TE216_BLSO_51 | Balam So 00482 | N1-W1-62F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220047DR | 2022-08-09 15:30 | 2022-08-16 | 2022-08-22 12:00 | Complete
Balam So | LQR-TE001_BLSO_44 | Balam So 00483 | N1-W1-62E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220509DR | 2022-08-22 12:00 | 2022-08-24 21:30 | 2022-09-01 12:00 | Complete
Balam So | LQR-TE026_BLSO_9 | Balam So 00487 | O-O-33H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220323DR | 2022-08-31 12:00 | 2022-09-08 21:30 | 2022-09-15 17:30 | Complete
Balam So | BLSO-P03 | Balam So 00490 | O-O-44F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220501DR | 2022-09-25 07:00 | 2022-09-25 10:00 | 2022-10-05 09:30 | Complete
Balam So | LQR-TE029_BLSO_16 | Balam So 00495 | O-O-33I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220515DR | 2022-10-05 09:30 | 2022-10-11 12:00 | 2022-10-21 | Complete
Balam So | LQR-TE171_BLSO_54 | Balam So 00500 | S1-O-47B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220532DR | 2022-10-21 | 2022-10-25 21:00 | 2022-11-04 | Complete
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220373DR | 2022-11-04 | 2022-09-22 19:00 | 2022-11-24 18:00 | Complete
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220390DR | 2022-11-24 18:00 | 2022-10-30 02:00 | 2022-12-19 08:30 | Complete
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220450DR | 2022-12-19 08:30 | 2022-12-26 21:00 | 2023-01-04 19:00 | Release
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220407DR | 2023-01-04 19:00 | 2022-10-24 23:00 | 2023-01-16 17:30 | Release
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220440DR | 2023-01-16 17:30 | 2022-10-14 04:00 | 2023-02-02 19:00 | Release
Balam Se | P_BLSE23_P03_MN | Balam Se 00026 | O-O-32B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220577DR | 2023-02-02 19:00 | 2023-03-01 13:00 | 2023-04-23 20:30 | Complete
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220416DR | 2023-08-11 16:30 | 2023-08-11 16:30 | 2023-08-17 02:00 | Complete
Balam So | BLSO23-LQR-TE028 | Balam So 00540 | N1-W1-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230334DR | 2023-08-17 02:00 | 2023-08-25 02:00 | 2023-08-29 22:30 | Release
Balam Se | P_BLSE23_P08_PM | Balam Se 00029 | O-O-14C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220576DR | 2023-08-29 22:30 | 2023-09-08 03:30 | 2023-09-29 12:00 | Complete
Balam Se | P_BLSE23_P04_MN | Balam Se 00030 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220582DR | 2023-09-29 12:00 | 2023-10-06 16:00 | 2023-10-18 11:00 | Complete
Balam Se | P_BLSE23_P02_MN | Balam Se 00031 | O-O-32C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220581DR | 2023-10-18 11:00 | 2023-10-23 01:00 | 2023-11-04 22:00 | Complete
Balam Se | P_BLSE23_P10_PM | Balam Se 00032 | O-O-46C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230306DR | 2023-11-04 22:00 | 2023-11-11 15:30 | 2023-11-29 | Complete
Balam Se | P_BLSE23_P23_PM | Balam Se 00034 | O-O-46D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220580DR | 2023-11-29 | 2023-12-03 13:30 | 2023-12-28 13:30 | Complete
Balam So | P_BLSO24_LQR06 | Balam So 00573 | N1-W1-77D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230345DR | 2023-12-28 13:30 | 2024-01-14 22:30 | 2024-01-23 05:00 | Complete
Balam So | P_BLSO24_LQR02 | Balam So 00587 | O-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230324DR | 2024-01-22 05:00 | 2024-01-29 02:00 | 2024-02-04 12:00 | Complete
Balam Se | P_BLSE23_P06_PM | Balam Se 00037 | N1-O-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230316DR | 2024-02-04 12:00 | 2024-02-11 12:00 | 2024-02-26 06:30 | Complete
Balam Se | P_BLSE23_P07_PM | Balam Se 00038 | N1-E1-61C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230315DR | 2024-02-26 06:30 | 2024-02-28 17:00 | 2024-03-13 | Complete
Balam So | LQR-TE013_BLSO_27 | Balam So 00593 | N1-W1-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230321DR | 2024-03-13 | 2024-03-19 15:00 | 2024-03-27 15:00 | Complete
Balam So | LQR-TE138_BLSO_37 | Balam So 00594 | N1-W1-86C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230322DR | 2024-03-23 | 2024-03-30 06:00 | 2024-04-05 08:00 | Complete
Bangko | BNK_PX10E_LQR | Bangko 00440 | N2-W3-74 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220609DR | 2024-04-05 08:00 | 2024-04-13 01:00 | 2024-04-20 13:00 | Complete
Bangko | BNK_PX10D_LQR | Bangko 00441 | N2-W3-74A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220352DR | 2024-04-20 13:00 | 2024-04-24 01:00 | 2024-04-30 19:30 | Complete
Bangko | BNK_PX04D_LQR | Bangko 00442 | N2-W3-74C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220607DR | 2024-04-30 19:30 | 2024-05-04 12:00 | 2024-05-10 04:00 | Complete
Bangko | BNK_PX10_LQR | Bangko 00443 | N2-W3-74D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220610DR | 2024-05-10 04:00 | 2024-05-14 09:00 | 2024-05-21 16:00 | Complete
Bangko | BNK_PX04C_LQR | Bangko 00444 | N2-W3-74B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220606DR | 2024-05-21 16:00 | 2024-05-27 18:00 | 2024-06-03 04:00 | Complete
Bangko | BNK23_P15 | Bangko 00445 | N1-W1-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230282DR | 2024-06-03 04:00 | 2024-06-14 01:30 | 2024-06-27 | Complete
Bangko | BNK23_P14 | Bangko 00447 | N1-W2-57C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230283DR | 2024-06-27 | 2024-06-30 09:00 | 2024-07-11 14:00 | Complete
Bangko | BNK23_P13 | Bangko 00448 | N1-W2-57D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230280DR | 2024-07-11 14:00 |  |  | In Progress
Minas | P_4C-26N2 | Minas 02017 | 4C-26N2 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220523DR | 2022-10-20 13:00 | 2022-11-02 13:00 | 2022-11-21 13:00 | Complete
Minas | P_5C-58N | Minas 02020 | 5C-58N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220363DR | 2022-11-21 13:00 | 2022-11-29 18:00 | 2022-12-31 | Complete
Minas | P_7E-94E1 | Minas 02035 | 7E-94E1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220378DR | 2022-12-31 | 2023-01-09 04:00 | 2023-02-03 15:00 | Complete
Minas | P_7E-95E1 | Minas 02037 | 7E-95E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220403DR | 2023-02-03 17:00 | 2023-02-11 08:00 | 2023-03-09 09:00 | Complete
Minas | P_5C-78 | Minas 02044 | 5C-78 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220552DR | 2023-03-09 09:00 | 2023-03-18 | 2023-04-04 06:00 | Complete
Minas | P_5E-96N | Minas 02052 | 5E-96N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220636DR | 2023-04-04 06:00 | 2023-04-17 01:00 | 2023-04-27 21:00 | Complete
Minas | P_5B-21N | Minas 02056 | 5B-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220645DR | 2023-04-27 21:00 | 2023-05-09 20:00 | 2023-06-30 12:00 | Complete
Minas | P_7E-94N | Minas 02063 | 7E-94N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220449DR | 2023-06-29 12:00 |  |  | Suspended
Minas | MNS-P22 | Minas 02011 | 7E-68 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNt-TMS#01 | SSO2/402/3220630DR | 2022-08-28 12:00 | 2022-08-28 12:00 | 2022-09-12 11:00 | Complete
Minas | MNS-P03 | Minas 02014 | 9C-66 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNt-TMS#01 | SSO2/402/3220510DR | 2022-09-12 11:00 | 2022-10-04 21:30 | 2022-10-20 21:00 | Complete
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Coiled Tubing Unit | CTU-D1 | SSO2/402/3220629DR | 2024-04-05 06:00 | 2024-04-18 22:00 | 2024-05-05 15:00 | In Progress
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Coiled Tubing Unit | CTU-D1 | SSO2/402/3220629DR | 2024-05-09 08:00 | 2024-04-18 22:00 |  | In Progress
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220425DR | 2023-05-14 08:00 | 2023-05-13 02:00 | 2023-05-21 13:00 | Complete
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220419DR | 2023-05-20 11:00 | 2023-05-17 | 2023-05-26 13:00 | Complete
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220450DR | 2023-05-22 08:00 | 2023-05-15 02:00 | 2023-05-28 13:00 | Complete
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220348DR | 2023-05-26 13:00 | 2023-05-19 08:00 | 2023-06-01 13:00 | Complete
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220434DR | 2023-06-12 08:00 | 2023-06-05 14:00 | 2023-06-19 17:00 | Complete
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220437DR | 2023-06-18 11:00 | 2023-06-13 12:00 | 2023-06-24 18:00 | Complete
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220377DR | 2023-06-25 08:00 | 2023-06-15 03:00 | 2023-07-01 18:00 | Complete
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220416DR | 2024-06-06 17:00 | 2024-05-20 02:00 | 2024-06-10 16:00 | Complete
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSE2/402/3230355DR | 2024-07-09 14:00 | 2024-06-12 16:00 | 2024-07-14 17:00 | Suspended
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220407DR | 2023-07-23 08:00 | 2023-07-20 02:00 | 2023-07-28 | Complete
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220440DR | 2023-07-29 13:00 | 2023-07-27 | 2023-08-04 18:00 | Complete
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220407DR | 2023-08-05 09:00 | 2023-07-20 02:00 | 2023-08-11 18:00 | Complete
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220372DR | 2023-10-10 07:00 | 2023-09-21 20:30 |  | Complete
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220554DR | 2023-11-04 14:00 | 2023-10-29 19:00 | 2023-11-09 17:00 | Complete
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220588DR | 2024-02-17 14:00 | 2023-11-15 21:00 | 2024-02-22 16:00 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220548DR | 2024-02-27 09:00 | 2024-05-05 05:00 | 2024-04-24 19:00 | Complete
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSE2/402/3230364DR | 2024-02-28 17:00 | 2024-02-26 20:00 | 2024-03-01 10:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220383DR | 2024-06-20 18:00 | 2024-06-10 17:00 | 2024-06-26 12:00 | In Progress
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSE2/402/3230350DR | 2024-07-11 06:00 | 2024-05-25 10:00 | 2024-07-15 17:00 | Suspended
Kotabatak | KTB-X26 | Kotabatak 00488 | N1-W1-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | GRK2/402/3220188DR | 2022-09-06 21:00 | 2022-09-08 11:00 | 2022-09-17 06:00 | Complete
Kotabatak | KB_PL46 | Kotabatak 00497 | N1-W2-39 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220358DR | 2023-01-25 12:00 | 2023-01-26 16:00 | 2023-02-08 23:00 | Complete
Kotabatak | KTB-P1 | Kotabatak 00503 | S2-O-25 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220446DR | 2023-03-18 11:00 | 2023-03-19 02:00 | 2023-03-27 21:00 | Complete
Kotabatak | KB_PL48 | Kotabatak 00506 | O-E1-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220369DR | 2023-04-24 11:00 | 2023-04-24 22:00 | 2023-05-03 18:00 | Complete
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSO2/402/3220522DR | 2023-05-03 18:00 | 2023-02-23 18:00 | 2023-05-11 12:00 | Complete
Kotabatak | KB_PL24 Inj | Kotabatak 00508 | O-E1-59 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSO2/402/3220402DR | 2023-05-16 | 2023-05-16 12:00 | 2023-05-24 10:30 | Complete
Kotabatak | KB_PL31 | Kotabatak 00504 | O-E1-37 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220339DR | 2023-05-29 13:00 | 2023-05-29 22:30 | 2023-06-07 16:00 | Complete
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220360DR | 2023-06-25 | 2023-06-02 10:00 | 2023-07-02 21:00 | Complete
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220380DR | 2023-07-02 21:00 | 2023-06-21 12:00 | 2023-07-09 20:00 | Complete
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230386DR | 2023-07-09 20:00 | 2023-06-16 05:00 | 2023-07-21 17:00 | Complete
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220625DR | 2023-07-21 17:00 | 2023-06-06 11:00 | 2023-07-27 18:00 | Complete
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220627DR | 2023-07-27 18:00 | 2023-06-09 20:00 | 2023-08-05 12:00 | Complete
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230384DR | 2023-08-05 12:00 | 2023-06-13 02:00 | 2023-08-12 18:00 | Complete
Kotabatak | KB_PL17 Inj | Kotabatak 00529 | O-O-11 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSE2/402/3230390DR | 2023-08-15 18:00 | 2023-08-16 06:00 | 2023-08-23 | Complete
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230391DR | 2023-08-23 | 2023-08-23 10:00 | 2023-08-25 19:00 | Complete
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220544DR | 2023-08-28 13:00 | 2023-08-29 06:30 | 2023-08-31 16:30 | Complete
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230387DR | 2023-08-31 16:30 | 2023-09-01 | 2023-09-03 13:30 | Complete
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220544DR | 2023-09-12 04:00 | 2023-08-29 06:30 | 2023-09-17 10:30 | Complete
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230387DR | 2023-09-17 10:30 | 2023-09-01 | 2023-09-23 06:00 | Complete
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230391DR | 2023-09-23 06:00 | 2023-08-23 10:00 | 2023-09-29 | Complete
Kotabatak | KTB-X11 | Kotabatak 00511 | N1-W1-54 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220426DR | 2023-09-29 | 2023-09-29 17:00 | 2023-10-07 06:00 | Complete
Kotabatak | KTB-A267 | Kotabatak 00519 | N1-W1-49 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230388DR | 2023-10-07 06:00 | 2023-10-07 14:00 | 2023-10-13 18:00 | Complete
Kotabatak | KB_PL1 | Kotabatak 00538 | O-W2-19 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230416DR | 2023-10-13 18:00 | 2023-10-14 08:30 | 2023-10-21 14:00 | Complete
Kotabatak | KTB-A98 | Kotabatak 00537 | S1-W1-42 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230430DR | 2023-11-12 11:30 | 2023-11-13 01:00 | 2023-11-19 | Complete
Kotabatak | KB_PL9 | Kotabatak 00535 | S1-W1-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230431DR | 2023-11-28 09:00 | 2023-11-29 02:00 | 2023-12-08 17:00 | Complete
Kotabatak | KTB-A198_INJ | Kotabatak 00536 | S1-W1-43 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230434DR | 2023-12-08 17:00 | 2023-12-09 02:00 | 2023-12-18 18:00 | Complete
Kotabatak | KTB-A185_INJ | Kotabatak 00547 | O-W1-66 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230433DR | 2024-02-19 17:00 | 2024-02-20 13:30 | 2024-02-27 | Complete
Kotabatak | KTB-A010 | Kotabatak 00549 | O-W1-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230417DR | 2024-02-29 04:00 | 2024-03-01 | 2024-03-12 12:00 | Complete
Kotabatak | KTB-A146_INJ | Kotabatak 00550 | O-W1-45 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230432DR | 2024-03-12 12:00 | 2024-03-17 14:00 | 2024-03-26 09:00 | Complete
Kotabatak | KTB-A005 | Kotabatak 00548 | O-W1-40 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230407DR | 2024-03-26 09:00 | 2024-03-27 14:30 | 2024-04-03 | Complete
Minas | MNS-P1 | Minas 01995 | 8D-48S | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | GRK2/402/3220204DR | 2022-04-30 08:00 | 2022-05-01 | 2022-05-06 18:30 | Complete
Bangko | BNK-X16 | Bangko 00400 | N1-W2-68C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | SSO2/402/3220336DR | 2022-12-21 16:30 | 2022-12-26 04:00 | 2023-01-06 07:30 | Complete
Pinang | P_PINA23_P10 | Pinang 00056 | N1-W2-68B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNG2/402/3220838DR | 2023-07-07 22:00 | 2023-07-09 17:00 | 2023-07-27 | Complete
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNA2/402/3220823DR | 2023-07-27 | 2023-07-28 04:00 | 2023-08-05 16:00 | Complete
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNG2/402/3220837DR | 2023-08-27 10:00 | 2023-08-28 06:00 | 2023-09-05 04:00 | Complete
Bangko | WFE-BNK_2 | Bangko 00421 | N1-W2-75A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-07 | SSM2/402/3230279DR | 2023-10-20 11:00 | 2023-10-21 07:00 | 2023-10-22 22:00 | Complete
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-09 | GRK2/402/2210008DR | 2022-02-09 | 2022-02-11 22:00 | 2022-02-15 17:00 | Complete
Kotabatak | KTB-X36-INJ | Kotabatak 00513 | N1-W1-37 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-09 | SSO2/402/3220388DR | 2023-07-25 21:00 | 2023-07-26 09:00 | 2023-07-31 21:00 | Complete
Bangko | BNK-P10 | Bangko 00356 | N1-W1-51A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | GRK2/402/2210039DR | 2021-12-22 | 2021-12-25 14:00 | 2022-01-02 12:00 | Complete
Bangko | BNK-P6 | Bangko 00377 | N1-W2-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | GRK2/402/2220065DR | 2022-06-22 12:00 | 2022-06-24 11:00 | 2022-06-30 18:00 | Complete
Bangko | BNK_P169A_LQR | Bangko 00417 | N2-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220413DR | 2023-04-17 22:00 | 2023-04-19 09:00 | 2023-04-27 17:00 | Complete
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220394DR | 2023-05-03 19:00 | 2023-05-05 12:00 | 2023-05-14 18:00 | Complete
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220434DR | 2023-06-04 17:00 | 2023-06-05 14:00 | 2023-06-09 05:00 | Complete
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220440DR | 2023-08-06 14:30 | 2023-07-27 | 2023-08-11 | Complete
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220407DR | 2023-08-13 08:00 | 2023-07-20 02:00 | 2023-08-19 12:00 | Complete
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220390DR | 2023-08-22 12:00 | 2023-08-23 10:00 | 2023-08-26 03:00 | Complete
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220390DR | 2023-09-11 12:00 | 2023-08-23 10:00 | 2023-09-19 | Complete
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220351DR | 2023-10-23 21:30 | 2022-11-24 21:30 | 2023-11-01 04:00 | Complete
Bangko | BNK_P88B_LQR | Bangko 00426 | O-W2-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220457DR | 2023-11-11 | 2023-11-11 16:00 | 2023-11-19 20:30 | Complete
Bangko | WFE-BNK_1 | Bangko 00422 | N1-W2-86A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-12 | SSM2/402/3230276DR | 2023-12-04 06:00 | 2023-12-07 21:00 | 2023-12-09 20:00 | Complete
Bangko | WFE-BNK_6 | Bangko 00432 | N2-W1-82A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-12 | SSM2/402/3230287DR | 2023-12-22 | 2023-12-24 18:00 | 2023-12-27 | Complete
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220415DR | 2024-02-18 23:00 | 2024-02-19 15:00 | 2024-02-26 22:00 | Complete
Bangko | BNK_P55A_LQR | Bangko 00436 | N2-W2-14A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220374DR | 2024-02-29 | 2024-02-29 16:00 | 2024-03-05 23:00 | Complete
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220373DR | 2024-03-13 | 2023-09-25 14:00 | 2024-03-17 16:00 | Complete
Balam Se | P_BLSE23_P08_PM | Balam Se 00029 | O-O-14C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220576DR | 2024-03-21 18:00 | 2024-03-22 18:00 | 2024-04-03 06:00 | Complete
Balam Se | P_BLSE23_P16_PM | Balam Se 00027 | O-O-76A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220579DR | 2024-05-04 22:00 | 2024-05-07 04:00 | 2024-05-15 14:00 | Complete
Balam Se | P_BLSE23_P17_PM | Balam Se 00036 | N1-E1-61B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSE2/402/3230308DR | 2024-06-15 15:00 | 2024-06-16 12:00 | 2024-06-29 10:30 | Complete
Balam Se | P_BLSE23_P10_PM | Balam Se 00032 | O-O-46C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSE2/402/3230306DR | 2024-06-29 10:30 | 2024-07-01 02:00 | 2024-07-11 10:00 | Complete
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Complete | SQZ03 - Improve Bonding | Land Workover Unit | GBT-17 | GRK2/402/2220061DR | 2022-07-25 | 2022-07-26 04:00 | 2022-07-31 11:00 | Complete
Bangko | BNK-X01 | Bangko 00387 | O-O-21B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220067DR | 2022-07-31 11:00 | 2022-08-01 10:00 | 2022-08-09 17:30 | Complete
Ubi | UBI-X09 | Ubi 00047 | N3-O-84B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220280DR | 2022-08-19 01:00 | 2022-08-20 19:00 | 2022-09-08 22:00 | Complete
Ubi | UBI-X03 | Ubi 00048 | N4-O-84B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220279DR | 2022-09-08 22:00 | 2022-09-09 21:00 | 2022-09-23 10:30 | Complete
Ubi | UBI-X06 | Ubi 00049 | N3-O-37A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220285DR | 2022-09-23 10:30 | 2022-09-30 07:30 | 2022-10-15 | Complete
Ubi | UBI-X10 | Ubi 00051 | N2-O-24B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | SSO2/402/3220512DR | 2022-10-15 | 2022-10-17 16:00 | 2022-10-22 20:00 | Complete
Bangko | BNK_P94E_LQR | Bangko 00406 | N1-W2-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | SSO2/402/3220431DR | 2023-05-11 10:00 | 2023-05-12 13:00 | 2023-05-20 | Complete
Balam So | P_BLSO24_LQR25 | Balam So 00599 | N1-W1-72C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-336 | SSE2/402/3240403DR | 2024-06-29 23:00 | 2024-06-29 23:00 | 2024-07-10 | Complete
Balam So | P_BLSO24_LQR03 | Balam So 00603 | N1-W1-72D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-336 | SSE2/402/3230347DR | 2024-07-10 |  |  | In Progress
Balam So | P_BLSO24_LQR_P22 | Balam So 00598 | S1-O-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-337 | SSE2/402/3240402DR | 2024-06-26 | 2024-06-27 16:00 | 2024-07-07 02:30 | Complete
Balam So | P_BLSO24_P04 | Balam So 00606 | N1-W1-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-337 | SSO2/402/3240282DR | 2024-07-07 02:30 |  |  | In Progress
Balam So | P_BLSO24_LQR37 | Balam So 00600 | O-W1-35D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-338 | SSE2/402/3240415DR | 2024-06-30 23:00 | 2024-06-30 23:00 | 2024-07-11 | Complete
Balam So | P_BLSO24_LQR_P14 | Balam So 00605 | N1-W1-77G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-338 | SSE2/402/3240397DR | 2024-07-11 |  |  | In Progress
Pematang | P_PEMA24_14 | Pematang 00136 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSA2/402/3230163DR | 2024-04-20 18:00 | 2024-04-20 18:00 | 2024-05-11 | Complete
Balam Se | P_BLSE24_P02 | Balam Se 00043 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSE2/402/3240646DR | 2024-05-11 | 2024-05-24 19:00 | 2024-06-14 03:30 | Complete
Balam So | P_BLSO24_P03 | Balam So 00601 | O-O-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSO2/402/3240281DR | 2024-06-13 03:30 | 2024-06-20 06:00 | 2024-07-02 05:00 | Complete
Balam So | P_BLSO24_LQR19 | Balam So 00602 | N1-O-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSE2/402/3240401DR | 2024-07-02 05:00 | 2024-07-08 09:00 |  | In Progress
Kelok Ne | P_KENE_P02 | Kelok NE 00004 | O-O-44B | Perforation Initial | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-08 | KEN2/402/3220807DR | 2023-03-05 05:00 | 2023-03-10 02:00 | 2023-03-18 02:00 | Complete
Pager | PG22-P06 | Pager 00052 | O-O-53C | Fishing | FIS01 - Fishing Job | Land Workover Unit | IDB-09 | SSO2/402/3220331DR | 2022-12-26 | 2022-12-26 18:00 | 2022-12-29 19:00 | Complete
Pager | PG22-P06 | Pager 00052 | O-O-53C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220331DR | 2023-02-03 15:00 | 2023-02-04 15:00 | 2023-03-10 14:00 | Complete
Pager | PG22-P17 | Pager 00054 | O-O-22A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220385DR | 2023-10-08 13:00 | 2023-10-10 01:00 | 2023-10-23 22:00 | Complete
Pager | PGR23-P03 | Pager 00057 | O-O-33A | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | IDB-09 | PGR2/402/3230446DR | 2023-10-23 22:00 | 2023-10-26 21:00 | 2023-10-29 | Complete
Pager | PG22-P16 | Pager 00051 | O-O-13A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220322DR | 2023-12-15 | 2023-12-16 03:00 | 2024-01-02 01:45 | Complete
Pager | PGR23-P04 | Pager 00061 | O-O-85A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | PGR2/402/3230447DR | 2024-03-09 07:00 | 2024-03-13 19:00 | 2024-03-20 | Complete
Pager | PG22-P05 | Pager 00055 | O-O-54C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220354DR | 2024-04-30 23:00 | 2024-05-01 18:30 | 2024-05-21 12:30 | Complete
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210093DR | 2021-10-20 09:00 |  | 2021-10-22 15:00 | Complete
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210018DR | 2022-01-07 08:00 |  | 2022-01-09 18:00 | Complete
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210008DR | 2022-01-11 09:00 |  | 2022-01-13 18:00 | Complete
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210065DR | 2022-02-08 11:00 | 2022-02-10 17:00 | 2022-02-09 16:30 | Complete
Minas | MNS-P10 | Minas 01992 | 8E-83E | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3210108DR | 2022-04-01 09:00 |  | 2022-04-03 15:00 | Complete
Minas | MNS-P1 | Minas 01995 | 8D-48S | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3220204DR | 2022-04-18 08:00 |  | 2022-04-19 15:00 | Complete
Minas | MNA-P7 | Minas 01993 | 8E-61N | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3220202DR | 2022-05-12 13:30 |  | 2022-05-14 13:00 | Complete
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2220061DR | 2022-08-18 06:00 |  | 2022-08-18 18:00 | Complete
Pager | PG22-P16 | Pager 00051 | O-O-13A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck | SSO2/402/3220322DR | 2022-11-18 10:00 |  | 2022-11-19 15:30 | Complete
Pager | PG22-P06 | Pager 00052 | O-O-53C | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck | SSO2/402/3220331DR | 2022-11-30 08:30 |  | 2022-12-02 19:00 | Complete
Duri | 2J-0712B | Duri 11127 | 2J-0712B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220746DR | 2024-01-27 08:30 |  | 2024-01-28 15:30 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | Mast Truck-01 | SSO2/402/3220548DR | 2024-04-22 05:00 | 2024-05-05 05:00 | 2024-04-22 19:00 | Complete
Duri | 2J-0210B | Duri 11174 | 2J-0210B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220781DR | 2024-05-11 09:00 |  | 2024-05-12 16:00 | Complete
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | Mast Truck-01 | SSO2/402/3220416DR | 2024-06-08 13:00 | 2024-05-20 02:00 | 2024-06-09 01:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSO2/402/3220383DR | 2024-06-22 08:00 | 2024-06-10 17:00 | 2024-06-23 13:00 | In Progress
Duri | 3J-0101A | Duri 11167 | 3J-0101A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220790DR | 2024-07-01 12:45 |  | 2024-07-01 17:00 | Complete
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSE2/402/3230355DR | 2024-07-12 05:00 | 2024-06-12 16:00 | 2024-07-12 13:30 | Suspended
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSE2/402/3230350DR | 2024-07-13 07:00 | 2024-05-25 10:00 | 2024-07-13 14:00 | Suspended
Duri | 2H-0507B | Duri 11074 | 2H-0507B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220734DR | 2023-07-21 14:00 |  | 2023-07-22 18:00 | Complete
Duri | 2J-0411B | Duri 11082 | 2J-0411B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220766DR | 2023-09-15 11:30 |  | 2023-09-17 17:15 | Complete
Duri | 2J-0911A | Duri 11081 | 2J-0911A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220739DR | 2023-10-14 11:00 |  | 2023-10-21 16:30 | Complete
Duri | 2H-1111A | Duri 11117 | 2H-1111A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220792DR | 2023-11-02 13:00 |  | 2023-11-02 18:00 | Complete
Duri | 2J-0111A | Duri 11116 | 2J-0111A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220770DR | 2023-11-03 10:00 |  | 2023-11-03 18:00 | Complete
Duri | 2J-0711A | Duri 11115 | 2J-0711A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220744DR | 2023-11-04 13:00 |  | 2023-11-04 18:00 | Complete
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Logging | LOG14 - Run Temperature And CBL/ USIT Log | Mast Unit | Mast Truck-02 | SSE2/402/3230397DR | 2023-12-19 11:30 |  | 2023-12-19 17:00 | Suspended
Duri | 2J-0413B | Duri 11134 | 2J-0413B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220765DR | 2024-01-29 11:30 |  | 2024-01-30 18:00 | Complete
Duri | 2J-0812A | Duri 11133 | 2J-0812A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220747DR | 2024-01-31 10:00 |  | 2024-01-31 15:00 | Complete
Duri | 2J-0612A | Duri 11124 | 2J-0612A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220752DR | 2024-02-01 09:00 | 2024-02-01 18:00 | 2024-02-01 15:00 | Complete
Duri | 2J-0212A | Duri 11166 | 2J-0212A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220780DR | 2024-05-19 09:00 |  | 2024-05-19 15:00 | Complete
Duri | 2J-0311A | Duri 11178 | 2J-0311A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220772DR | 2024-07-11 13:00 |  | 2024-07-11 17:00 | Complete
Duri | 3J-0301A | Duri 11160 | 3J-0301A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220774DR | 2024-07-12 10:00 |  | 2024-07-12 15:00 | Complete
Duri | 3H-1101A | Duri 11159 | 3H-1101A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220785DR | 2024-07-13 10:00 |  | 2024-07-13 15:00 | Complete
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck-03 | SSM2/402/3230246DR | 2023-07-08 09:00 |  | 2023-07-10 18:00 | Complete
Duri | 2J-0511A | Duri 11144 | 2J-0511A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220760DR | 2024-04-26 09:00 |  | 2024-04-26 14:00 | Complete
Duri | 3J-0501A | Duri 11145 | 3J-0501A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220755DR | 2024-04-27 09:00 |  | 2024-04-27 14:00 | Complete
Duri | 2H-1212A | Duri 11135 | 2H-1212A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220798DR | 2024-05-01 11:00 |  | 2024-05-01 15:00 | Complete
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Logging | LOG04 - Cased Hole Formation Log | Mast Unit | Mast Truck-03 | PNE2/402/2220002EX | 2024-05-23 09:00 |  | 2024-05-24 13:30 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer |  | OMS | SSO2/402/3220383DR | 2024-06-22 05:00 | 2024-06-10 17:00 | 2024-06-22 08:00 | In Progress
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | PDSI-35.1 | MBS2/402/3230833EX | 2024-05-03 18:00 | 2024-05-16 | 2024-06-09 14:30 | Complete
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2023-07-27 12:00 | 2023-07-27 12:00 | 2023-11-10 04:00 | Release
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2023-11-10 04:00 | 2023-11-10 04:00 | 2023-12-19 05:30 | Suspended
Kelok | P01_KL17 | Kelok 00016 | O-O-61 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-42.3 | KLK2/402/2220003EX | 2023-12-19 05:30 | 2024-02-14 18:00 | 2024-05-20 10:00 | Complete
Kelok | P01_KL17 | Kelok 00016 | O-O-61 | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | KLK2/402/2220003EX | 2024-05-20 10:00 | 2024-05-20 10:00 | 2024-06-28 13:00 | Suspended
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2024-06-28 13:00 | 2024-07-14 15:00 |  | In Progress
Bangko | BNKO21-P01 | Bangko 00345 | N1-W2-68A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210036DR | 2021-08-29 13:00 | 2021-08-29 13:00 | 2021-09-13 06:30 | Complete
Bangko | BNKO21-P01 | Bangko 00345 | N1-W2-68A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210036DR | 2021-09-13 06:30 | 2021-09-13 06:30 | 2021-09-15 09:00 | Complete
Bangko | Bangko P25 | Bangko 00350 | O-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210030DR | 2021-09-15 09:00 | 2021-09-27 01:30 | 2021-10-10 05:00 | Complete
Bangko | BNK-P31 | Bangko 00355 | N1-W3-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210060DR | 2021-10-10 05:00 | 2021-10-16 12:00 | 2021-10-27 16:00 | Complete
Bangko | BNK-P32 | Bangko 00352 | N1-W3-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210061DR | 2021-10-27 16:00 | 2021-11-03 01:00 | 2021-11-14 07:00 | Release
Bangko | BNK-P14 | Bangko 00360 | N1-W1-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210042DR | 2021-11-14 07:00 | 2021-11-20 02:00 | 2021-11-29 20:00 | Complete
Bangko | BNK-P27 | Bangko 00379 | N1-W1-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210055DR | 2021-11-29 20:00 | 2021-12-08 08:00 | 2021-12-21 | Complete
Bangko | BNK-P33 | Bangko 00367 | N1-W1-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210067DR | 2021-12-21 | 2022-01-14 18:00 | 2022-01-25 07:30 | Complete
Bangko | BNK-P28 | Bangko 00373 | N1-W1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210056DR | 2022-01-25 07:30 | 2022-01-28 05:00 | 2022-02-08 10:00 | Complete
Balam So | BLSO-P28 | Balam So 00449 | N1-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220012DR | 2022-02-08 10:00 | 2022-02-17 02:00 | 2022-02-27 21:00 | Complete
Balam So | BLSO-P30 | Balam So 00453 | S1-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220018DR | 2022-02-27 21:00 | 2022-03-07 03:00 | 2022-03-14 18:00 | Complete
Balam So | BLSO-P25 | Balam So 00458 | N1-W1-67B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220019DR | 2022-03-14 18:00 | 2022-03-22 05:00 | 2022-03-30 13:00 | Complete
Balam So | BLSO-P26 | Balam So 00462 | N1-W1-67C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220024DR | 2022-03-30 13:00 | 2022-04-02 01:00 | 2022-04-10 14:00 | Release
Bangko | BNK-P29 | Bangko 00383 | N2-W2-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210057DR | 2022-04-10 14:00 | 2022-04-17 23:00 | 2022-04-29 18:00 | Complete
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220061DR | 2022-04-29 18:00 | 2022-05-05 01:00 | 2022-05-17 03:30 | Release
Puncak | PNC-P04 | Puncak 00042 | O-O-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220273DR | 2022-05-17 03:30 | 2022-05-27 08:00 | 2022-06-08 | Complete
Puncak | PNC-P05 | Puncak 00043 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220274DR | 2022-06-08 | 2022-06-10 15:30 | 2022-06-22 | Complete
Puncak | PNC-P01 | Puncak 00044 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220270DR | 2022-06-22 | 2022-06-27 22:30 | 2022-07-10 16:00 | Complete
Puncak | PNC-P02 | Puncak 00045 | O-O-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220271DR | 2022-07-10 16:00 | 2022-07-15 08:00 | 2022-07-28 03:30 | Complete
Bekasap | BKS-X14 | Bekasap 00220 | O-E1-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220275DR | 2022-07-28 03:30 | 2022-08-05 22:30 | 2022-08-16 07:00 | Release
Bekasap | BKS-X13 | Bekasap 00221 | O-E1-65B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220320DR | 2022-08-16 07:00 | 2022-08-18 16:00 | 2022-08-28 08:00 | Complete
Bekasap | BKS-X12 | Bekasap 00222 | O-O-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220332DR | 2022-08-28 08:00 | 2022-09-02 07:00 | 2022-10-06 11:30 | Release
Bekasap | BKS-X09 | Bekasap 00223 | O-O-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220343DR | 2022-10-06 11:30 | 2022-10-10 23:30 | 2022-10-31 | Complete
Bekasap | BKS-X01 | Bekasap 00224 | O-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220365DR | 2022-10-31 | 2022-11-05 19:00 | 2022-11-21 03:00 | Complete
Bekasap | BKS-X05 | Bekasap 00225 | O-E1-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220611DR | 2022-11-21 03:00 | 2022-11-25 18:00 | 2022-12-11 10:00 | Complete
Bekasap | P_BK22_S1 | Bekasap 00226 | S1-E2-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SOB2/402/3220815DR | 2022-12-11 10:00 | 2022-12-18 14:00 | 2023-01-06 22:30 | Complete
Bekasap | BKS-X07 | Bekasap 00227 | S1-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220613DR | 2023-01-06 22:30 | 2023-01-12 12:00 | 2023-01-25 21:00 | Complete
Puncak | PNC-P03 | Puncak 00046 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220546DR | 2023-01-25 21:00 | 2023-02-02 11:00 | 2023-02-23 03:00 | Complete
Puncak | PNC-P06 | Puncak 00047 | O-O-34C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220410DR | 2023-02-23 03:00 | 2023-03-06 23:00 | 2023-03-18 11:00 | Complete
Puncak | PNC-P07 | Puncak 00048 | O-O-24A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220428DR | 2023-03-18 11:00 | 2023-03-24 06:30 | 2023-04-05 02:30 | Complete
Pinang | P_PINA23_P10 | Pinang 00056 | N1-W2-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220838DR | 2023-04-05 02:30 | 2023-04-20 23:00 | 2023-05-06 05:00 | Release
Pinang | P_PINA23_P03 | Pinang 00057 | N1-W2-68C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNA2/402/3220822DR | 2023-05-06 05:00 | 2023-05-09 18:00 | 2023-05-25 05:00 | Complete
Pinang | P_PINA23_P88 | Pinang 00058 | N1-W2-68D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220843DR | 2023-05-25 05:00 | 2023-05-28 18:30 | 2023-06-12 13:00 | Complete
Pinang | P_PINA23_P02 | Pinang 00060 | N1-W2-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220836DR | 2023-06-12 13:00 | 2023-06-17 08:00 | 2023-07-04 18:30 | Complete
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220837DR | 2023-07-03 18:30 | 2023-07-08 23:00 | 2023-07-25 11:00 | Release
Balam So | BLSO23-LQR-TE010 | Balam So 00541 | O-O-11A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220530DR | 2023-07-25 11:00 | 2023-08-05 18:00 | 2023-08-10 23:00 | Complete
Balam Se | P_BLSE23_P16_PM | Balam Se 00027 | O-O-76A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220579DR | 2023-08-10 23:00 | 2023-08-17 06:00 | 2023-08-30 07:00 | Complete
Balam Se | P_BLSE23_P24_PM | Balam Se 00028 | O-O-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220578DR | 2023-08-30 07:00 | 2023-09-03 03:30 | 2023-09-15 20:00 | Complete
Bangko | BNK23_P24 | Bangko 00427 | N1-W2-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSM2/402/3230274DR | 2023-09-15 20:00 | 2023-09-24 16:30 | 2023-10-03 16:00 | Release
Bangko | BNK23_P01 | Bangko 00431 | O-O-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSM2/402/3230268DR | 2023-10-03 16:00 | 2023-10-10 13:30 | 2023-10-20 22:00 | Complete
Balam So | LQR-TE212_BLSO_52 | Balam So 00558 | N1-W1-66D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230368DR | 2023-10-20 22:00 | 2023-10-28 19:00 | 2023-11-04 05:00 | Complete
Balam So | LQR-TE012_BLSO_34 | Balam So 00559 | N1-W1-66E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220357DR | 2023-11-04 05:00 | 2023-11-08 | 2023-11-13 13:00 | Complete
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230314DR | 2023-11-13 13:00 | 2023-11-22 17:00 | 2023-12-24 21:00 | Release
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNE2/402/2220002EX | 2023-12-24 21:00 | 2024-03-14 23:30 | 2023-12-29 | Complete
Balam So | BLSO23-LQR-TE018 | Balam So 00577 | N1-W1-88B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230354DR | 2023-12-29 17:00 | 2024-01-25 14:00 | 2024-01-30 10:45 | Complete
Balam So | BLSO23-LQR-TE058 | Balam So 00578 | N1-W1-88C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230352DR | 2024-01-30 10:45 | 2024-02-02 06:00 | 2024-02-06 14:00 | Complete
Balam So | BLSO23-LQR-TE008 | Balam So 00579 | N1-W1-88D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230353DR | 2024-02-06 14:00 | 2024-02-10 | 2024-02-16 05:00 | Complete
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNE2/402/2220002EX | 2024-02-16 05:00 | 2024-03-14 23:30 | 2024-04-03 | Complete
Benar | P_BENA22-P04 | Benar 00074 | O-W1-87 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SBN2/402/3220845DR | 2024-05-23 20:00 | 2024-05-23 20:00 | 2024-05-31 16:00 | Release
Bangko | BNK_PX04F_LQR | Bangko 00446 | N2-W3-85 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220608DR | 2024-05-31 16:00 | 2024-06-08 12:00 | 2024-06-15 | Complete
Bangko | BNK_PX05A_LQR | Bangko 00450 | N2-W3-85C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240903DR | 2024-06-15 | 2024-06-20 | 2024-06-27 10:30 | Complete
Bangko | BNK_PX04E_LQR | Bangko 00449 | N2-W3-85B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240902DR | 2024-06-27 10:30 | 2024-07-02 14:00 | 2024-07-09 02:00 | Complete
Bangko | BNK_PX05_LQR | Bangko 00451 | N2-W3-85D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240901DR | 2024-07-09 02:00 | 2024-07-13 12:30 |  | In Progress
Balam So | BLSO23-LQR-TE070 | Balam So 00524 | N1-O-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220417DR | 2023-05-13 | 2023-05-13 | 2023-05-25 12:00 | Complete
Balam So | BLSO23-LQR-TE034 | Balam So 00528 | N1-O-83F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220535DR | 2023-05-25 12:00 | 2023-05-31 23:30 | 2023-06-11 14:30 | Complete
Balam So | BLSO23-LQR-TE019 | Balam So 00532 | O-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220587DR | 2023-06-11 15:30 | 2023-06-21 11:00 | 2023-07-03 17:00 | Complete
Balam So | BLSO23-LQR-TE024 | Balam So 00537 | O-O-75A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220439DR | 2023-07-03 17:00 | 2023-07-15 11:00 | 2023-07-22 05:00 | Release
Balam So | BLSO23-LQR-TE068 | Balam So 00536 | O-O-75B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220406DR | 2023-07-22 05:00 | 2023-07-25 23:00 | 2023-07-31 11:00 | Complete
Bangko | WFE-BNK_2 | Bangko 00421 | N1-W2-75A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230279DR | 2023-07-31 11:00 | 2023-08-09 17:30 | 2023-08-22 17:00 | Complete
Bangko | WFE-BNK_1 | Bangko 00422 | N1-W2-86A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230276DR | 2023-08-22 17:00 | 2023-08-27 03:00 | 2023-09-06 12:30 | Complete
Bangko | WFE-BNK_5 | Bangko 00423 | N2-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230286DR | 2023-09-06 12:30 | 2023-09-12 20:00 | 2023-09-29 12:00 | Complete
Bangko | WFE-BNK_4 | Bangko 00429 | O-O-33B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230284DR | 2023-09-29 12:00 | 2023-10-11 11:00 | 2023-10-21 21:00 | Complete
Bangko | BNK23_P07 | Bangko 00434 | O-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230271DR | 2023-10-21 21:00 | 2023-10-27 08:00 | 2023-11-14 | Complete
Bangko | BNK_P55A_LQR | Bangko 00436 | N2-W2-14A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220374DR | 2023-11-14 | 2023-11-28 14:00 | 2023-12-07 06:00 | Complete
Balam So | LQR-TE211_BLSO_22 | Balam So 00569 | N1-W1-66C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230367DR | 2023-12-07 06:00 | 2023-12-18 05:00 | 2023-12-27 12:00 | Complete
Balam So | LQR-TE014_BLSO_25 | Balam So 00570 | N1-W1-66F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230369DR | 2023-12-27 12:00 | 2023-12-30 23:00 | 2024-01-07 17:00 | Complete
Balam So | LQR-TE021_BLSO_23 | Balam So 00580 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220538DR | 2024-01-07 17:00 | 2024-01-21 06:00 | 2024-02-07 10:00 | Complete
Balam So | LQR-TE133_BLSO_31 | Balam So 00581 | N1-O-61B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230373DR | 2024-02-07 10:00 | 2024-02-10 16:00 | 2024-02-21 05:30 | Complete
Balam So | LQR-TE023_BLSO_24 | Balam So 00582 | N1-O-61C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220330DR | 2024-02-21 05:30 | 2024-02-28 14:15 | 2024-03-07 18:00 | Complete
Balam So | P_BLSO24_P06 | Balam So 00591 | N1-W1-61C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3240283DR | 2024-03-07 18:00 | 2024-03-17 09:00 | 2024-03-25 14:00 | Complete
Balam So | BLSO23-P01 | Balam So 00592 | N1-W1-61D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220596DR | 2024-03-25 14:00 | 2024-03-29 | 2024-04-07 | Complete
Balam So | LQR-TE215_BLSO_45 | Balam So 00595 | N1-W1-74F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230328DR | 2024-06-12 06:00 | 2024-06-22 13:00 | 2024-06-30 17:00 | Complete
Balam So | LQR-TE214_BLSO_49 | Balam So 00596 | N1-W1-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230325DR | 2024-06-30 17:00 | 2024-07-03 21:00 | 2024-07-10 18:00 | Complete
Balam So | P_BLSO24_P20 | Balam So 00597 | N1-W1-74J | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3240289DR | 2024-07-10 18:00 |  |  | In Progress
Bangko | BNKO21-P06 | Bangko 00346 | S1-O-11B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210037DR | 2021-08-23 22:00 | 2021-08-23 23:00 | 2021-09-08 13:00 | Complete
Bangko | BNKO21-P06 | Bangko 00346 | S1-O-11B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210037DR | 2021-09-08 13:00 | 2021-09-08 13:00 | 2021-09-10 13:30 | Complete
Seruni | SERU21-P01 | Seruni 00050 | N2-W3-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210159DR | 2021-09-10 13:30 | 2021-09-19 15:00 | 2021-10-02 10:00 | Complete
Bangko | BNK-P25 | Bangko 00353 | N1-W1-11A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210053DR | 2021-10-02 10:00 | 2021-10-11 05:00 | 2021-10-23 01:30 | Complete
Bangko | BNK-P9 | Bangko 00363 | N1-W2-45A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210074DR | 2021-10-23 01:30 | 2021-10-29 05:00 | 2021-11-10 16:30 | Complete
Bangko | BNK-P20 | Bangko 00357 | O-O-85A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210048DR | 2021-11-10 16:30 | 2021-11-17 04:00 | 2021-11-29 04:00 | Complete
Bangko | BNK-P15 | Bangko 00368 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210043DR | 2021-11-29 04:00 | 2021-12-04 03:30 | 2021-12-15 22:00 | Complete
Bangko | BNK-P18 | Bangko 00372 | O-O-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210046DR | 2021-12-15 22:00 | 2022-01-15 02:00 | 2022-01-26 23:00 | Complete
Bangko | BNK-P16 | Bangko 00376 | O-O-74C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210044DR | 2022-01-26 23:00 | 2022-01-31 23:30 | 2022-02-12 15:00 | Complete
Bangko | BNK-P23 | Bangko 00384 | N1-W2-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220059DR | 2022-02-12 15:00 | 2022-02-20 03:30 | 2022-03-04 02:30 | Complete
Balam So | BLSO-P31 | Balam So 00455 | S1-O-45C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220023DR | 2022-03-04 02:30 | 2022-03-12 18:00 | 2022-03-20 12:00 | Release
Balam So | BLSO-P07 | Balam So 00461 | O-O-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220003DR | 2022-03-20 12:00 | 2022-03-25 23:00 | 2022-04-02 13:30 | Complete
Balam So | BLSO-P12 | Balam So 00465 | N1-O-76A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220013DR | 2022-04-02 13:30 | 2022-04-08 04:15 | 2022-04-16 | Complete
Bangko | BNK-P19 | Bangko 00375 | O-O-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210047DR | 2022-04-16 | 2022-04-23 01:00 | 2022-05-05 02:30 | Complete
Bangko | BNK-X08 | Bangko 00386 | O-W1-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220062DR | 2022-05-05 02:30 | 2022-05-11 | 2022-05-22 21:00 | Complete
Bangko | BNK-X10 | Bangko 00388 | S1-E1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220064DR | 2022-05-22 21:00 | 2022-05-30 13:45 | 2022-06-10 16:00 | Complete
Bangko | BNK-X11 | Bangko 00390 | S1-E2-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220066DR | 2022-06-10 16:00 | 2022-06-17 13:00 | 2022-07-03 14:00 | Complete
Bangko | BNK-X13 | Bangko 00392 | S1-E2-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220076DR | 2022-07-03 14:00 | 2022-07-07 02:00 | 2022-07-20 07:00 | Complete
Bangko | BNK-X12 | Bangko 00394 | S1-E2-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220074DR | 2022-07-20 07:00 | 2022-07-25 18:00 | 2022-08-05 12:00 | Complete
Bangko | BNK-X17 | Bangko 00396 | O-W1-37A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220503DR | 2022-08-05 12:00 | 2022-08-11 | 2022-08-23 02:30 | Complete
Bangko | BNK-X15 | Bangko 00398 | N1-W2-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220517DR | 2022-08-23 02:30 | 2022-08-30 | 2022-09-11 13:00 | Complete
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220351DR | 2022-09-11 13:00 | 2022-09-20 20:00 | 2022-10-01 02:00 | Release
Bangko | BNK-X16 | Bangko 00400 | N1-W2-68C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220336DR | 2022-10-01 02:00 | 2022-10-10 15:00 | 2022-10-21 18:30 | Release
Bangko | BNK-X09 | Bangko 00401 | O-O-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220353DR | 2022-10-21 18:30 | 2022-10-28 14:00 | 2022-11-09 | Complete
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220425DR | 2022-11-09 | 2022-11-15 23:30 | 2022-11-25 14:00 | Release
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220434DR | 2022-11-25 14:00 | 2022-12-01 22:30 | 2022-12-10 12:00 | Release
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220415DR | 2022-12-10 12:00 | 2022-10-20 19:00 | 2022-12-27 18:30 | Complete
Bangko | BNK_P277B_LQR | Bangko 00409 | N1-W4-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220366DR | 2022-12-27 18:30 | 2023-01-02 12:00 | 2023-01-11 18:00 | Complete
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220419DR | 2023-01-11 18:00 | 2023-01-16 12:00 | 2023-01-25 22:00 | Release
Bangko | BNK_P244A_LQR | Bangko 00414 | N1-W3-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220398DR | 2023-01-25 22:00 | 2023-02-02 15:00 | 2023-02-21 09:00 | Release
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220383DR | 2023-02-21 09:00 | 2023-02-28 02:30 | 2023-03-10 | Release
Benar | P_BENA23B_P01 | Benar 00068 | N2-O-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220506DR | 2023-03-10 | 2023-03-20 18:00 | 2023-03-30 02:30 | Complete
Ubi | UBI-X05 | Ubi 00052 | N4-O-84C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220918DR | 2023-03-30 02:30 | 2023-04-08 18:30 | 2023-04-23 05:00 | Release
Ubi | UBI-X11 | Ubi 00053 | N3-O-34A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220919DR | 2023-04-23 05:00 | 2023-05-01 02:30 | 2023-05-25 01:00 | Release
Benar | P_BENA22-P03 | Benar 00071 | O-E1-32B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220844DR | 2023-05-25 01:00 | 2023-06-04 15:30 | 2023-06-26 12:00 | Release
Benar | P_BENA23B_P02 | Benar 00072 | N2-O-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220850DR | 2023-06-26 12:00 | 2023-07-03 14:00 | 2023-07-13 15:30 | Complete
Benar | P_BENA23B_P03 | Benar 00073 | N2-O-58A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220851DR | 2023-07-13 15:30 | 2023-07-19 10:30 | 2023-07-28 18:00 | Complete
Ubi | UBI-X13 | Ubi 00054 | N1-W1-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220920DR | 2023-07-28 18:00 | 2023-08-12 03:00 | 2023-08-24 08:00 | Complete
Pager | PGR23-P03 | Pager 00057 | O-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230446DR | 2023-08-24 08:00 | 2023-09-07 17:30 | 2023-09-22 15:00 | Complete
Pager | PGR23-P05 | Pager 00058 | O-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230448DR | 2023-09-22 15:00 | 2023-09-27 15:00 | 2023-10-13 12:00 | Complete
Pager | PGR23-P01 | Pager 00059 | N1-O-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230444DR | 2023-10-13 12:00 | 2023-10-18 20:00 | 2023-11-03 01:30 | Complete
Pager | PGR23-P02 | Pager 00060 | N1-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230445DR | 2023-11-03 01:30 | 2023-11-08 09:00 | 2023-11-23 05:30 | Complete
Pager | PGR23-P04 | Pager 00061 | O-O-85A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230447DR | 2023-11-23 05:30 | 2023-11-29 20:00 | 2023-12-12 18:30 | Complete
Pager | P_PAGE24_01 | Pager 00062 | O-O-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230451DR | 2023-12-12 18:30 | 2023-12-22 17:30 | 2024-02-22 16:00 | Complete
Pager | PGR23-P06 | Pager 00063 | O-O-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230449DR | 2024-02-22 16:00 | 2024-02-28 18:30 | 2024-03-15 12:00 | Complete
Pager | P_PAGE24_03 | Pager 00064 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230453DR | 2024-03-15 12:00 | 2024-03-21 09:00 | 2024-04-04 13:00 | Complete
Pager | PGR23-P07 | Pager 00065 | N1-O-61B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230450DR | 2024-04-04 13:00 | 2024-04-08 10:30 | 2024-04-22 14:30 | Complete
Pager | P_PAGE24_02 | Pager 00066 | N1-O-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230452DR | 2024-06-21 01:00 | 2024-06-21 01:00 | 2024-07-07 21:00 | Complete
Balam So | P_BLSO24_P19 | Balam So 00608 | O-O-15E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3240288DR | 2024-07-07 21:00 |  |  | In Progress
Bekasap | P01_BK21 | Bekasap 00196 | O-O-84D | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210001DR | 2021-02-20 | 2021-08-27 19:00 | 2021-08-30 14:00 | Complete
Bekasap | P01_BK21 | Bekasap 00196 | O-O-84D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210001DR | 2021-08-15 22:00 | 2021-08-15 22:00 | 2021-08-27 19:00 | Complete
Pungut | Pungut P01 | Pungut 00047 | S2-E1-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210132DR | 2021-08-30 14:00 | 2021-09-13 16:00 | 2021-10-03 23:00 | Complete
Seruni | SERU21-P07 | Seruni 00051 | N2-W3-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210160DR | 2021-10-03 23:00 | 2021-10-14 05:00 | 2021-10-26 06:00 | Complete
Seruni | SRN-P2 | Seruni 00052 | N2-W3-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210162DR | 2021-10-26 06:00 | 2021-10-30 02:00 | 2021-11-12 10:00 | Complete
Seruni | SRN-P4 | Seruni 00053 | N1-W2-41C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210164DR | 2021-11-12 10:00 | 2021-11-19 09:00 | 2021-12-03 18:00 | Complete
Seruni | SRN-P1 | Seruni 00054 | N2-W3-47A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210161DR | 2021-12-03 18:00 | 2021-12-08 19:00 | 2021-12-18 13:00 | Release
Seruni | SRN-P3 | Seruni 00055 | N2-W3-34A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210163DR | 2021-12-18 13:00 | 2021-12-31 16:30 | 2022-01-10 14:00 | Release
Seruni | SRN-P06 | Seruni 00056 | N1-W2-41D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220278DR | 2022-01-10 14:00 | 2022-01-20 20:00 | 2022-02-03 | Complete
Seruni | SRN-P14 | Seruni 00057 | N1-W2-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220276DR | 2022-02-03 | 2022-02-08 12:00 | 2022-02-21 15:00 | Complete
Balam So | BLSO-P13 | Balam So 00452 | N1-O-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220001DR | 2022-02-21 15:00 | 2022-03-02 19:00 | 2022-03-11 13:00 | Complete
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220028DR | 2022-03-11 13:00 | 2022-03-17 23:00 | 2022-03-27 13:00 | Release
Seruni | SRN-P13 | Seruni 00058 | N1-W2-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220277DR | 2022-03-27 13:00 | 2022-04-03 06:00 | 2022-04-18 13:00 | Complete
Seruni | SRN-P05 | Seruni 00059 | N2-W3-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210038DR | 2022-04-18 13:00 | 2022-04-26 23:00 | 2022-05-07 | Canceled
Ubi | UBI-X09 | Ubi 00047 | N3-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220280DR | 2022-05-07 | 2022-05-16 15:00 | 2022-06-17 16:00 | Release
Ubi | UBI-X03 | Ubi 00048 | N4-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220279DR | 2022-06-17 16:00 | 2022-06-24 07:00 | 2022-07-08 11:00 | Release
Ubi | UBI-X06 | Ubi 00049 | N3-O-37A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220285DR | 2022-07-08 11:00 | 2022-07-15 07:00 | 2022-07-30 16:00 | Release
Ubi | UBI-X08 | Ubi 00050 | N3-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220282DR | 2022-07-30 16:00 | 2022-08-05 08:00 | 2022-08-21 14:00 | Complete
Ubi | UBI-X10 | Ubi 00051 | N2-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220512DR | 2022-08-21 14:00 | 2022-08-27 01:00 | 2022-09-09 01:00 | Release
Seruni | SRN-P05_Ext | Seruni 00059-01 | N2-W3-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210038DR | 2022-09-09 01:00 | 2022-09-21 02:00 | 2022-10-09 14:00 | Complete
Bangko | BNK_P169A_LQR | Bangko 00417 | N2-W2-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220413DR | 2022-10-09 14:00 | 2022-10-18 03:00 | 2022-10-31 02:30 | Release
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220359DR | 2022-10-31 14:00 | 2022-11-06 03:30 | 2022-11-17 | Release
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220394DR | 2022-11-17 | 2022-10-02 03:00 | 2022-12-04 12:00 | Complete
Bangko | BNK_P94E_LQR | Bangko 00406 | N1-W2-24A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220431DR | 2022-12-04 12:00 | 2022-12-11 15:00 | 2022-12-23 04:30 | Release
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220348DR | 2022-12-23 04:30 | 2022-12-31 15:00 | 2023-01-10 10:00 | Complete
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220377DR | 2023-01-10 10:00 | 2023-01-16 | 2023-01-25 05:00 | Release
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220437DR | 2023-01-25 05:00 | 2023-02-02 08:00 | 2023-02-20 22:00 | Release
Sikladi | SKL23_P05 | Sikladi 00030 | N1-O-14A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220925DR | 2023-02-20 22:00 | 2023-03-04 21:00 | 2023-03-15 19:00 | Release
Sikladi | SKL23_P01 | Sikladi 00031 | O-O-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220921DR | 2023-03-15 19:00 | 2023-03-28 | 2023-04-11 14:00 | Complete
Sikladi | SKL23_P02 | Sikladi 00032 | O-O-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220922DR | 2023-04-11 14:00 | 2023-04-15 15:00 | 2023-05-05 16:00 | Complete
Sikladi | SIKL23_P06 | Sikladi 00033 | O-O-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3230174DR | 2023-05-05 16:00 | 2023-05-11 02:00 | 2023-06-03 10:00 | Complete
Sikladi | SKL23_P03 | Sikladi 00034 | O-O-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220924DR | 2023-06-03 10:00 | 2023-06-09 18:30 | 2023-07-03 | Complete
Sikladi | SKL23_P04 | Sikladi 00035 | N1-O-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220923DR | 2023-07-03 | 2023-07-10 10:00 | 2023-07-28 03:00 | Release
Balam So | BLSO23-LQR-TE077 | Balam So 00542 | N1-W1-87B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230366DR | 2023-07-28 03:00 | 2023-08-09 12:00 | 2023-08-14 12:00 | Complete
Balam So | BLSO23-LQR-TE065 | Balam So 00545 | N1-O-21A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230343DR | 2023-08-14 12:00 | 2023-08-20 14:30 | 2023-08-26 | Complete
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230355DR | 2023-08-26 | 2023-08-31 23:30 | 2023-09-06 | Complete
Balam So | BLSO23-LQR-TE043 | Balam So 00551 | N1-O-71B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230333DR | 2023-09-06 | 2023-09-11 01:00 | 2023-09-15 20:00 | Complete
Balam So | BLSO23-LQR-TE046 | Balam So 00552 | O-O-73A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230351DR | 2023-09-15 20:00 | 2023-09-20 21:00 | 2023-09-25 12:00 | Complete
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230350DR | 2023-09-25 12:00 | 2023-09-30 03:00 | 2023-10-04 12:00 | Release
Balam So | BLSO23-LQR-TE076 | Balam So 00556 | N1-O-81A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230365DR | 2023-10-04 12:00 | 2023-10-11 12:00 | 2023-10-16 | Complete
Balam So | BLSO23-LQR-TE074 | Balam So 00557 | N1-W1-26C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230335DR | 2023-10-16 | 2023-10-21 21:00 | 2023-10-26 | Complete
Balam So | BLSO23-LQR-TE005 | Balam So 00561 | O-W1-35C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230342DR | 2023-10-26 | 2023-11-02 03:30 | 2023-11-06 17:00 | Complete
Balam So | BLSO23-LQR-TE075 | Balam So 00563 | N1-W1-35 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230356DR | 2023-11-06 17:00 | 2023-11-16 | 2023-11-20 07:00 | Complete
Balam So | BLSO23-LQR-TE035 | Balam So 00567 | N1-W1-34B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230337DR | 2023-11-20 07:00 | 2023-12-01 10:30 | 2023-12-05 17:00 | Complete
Balam Se | P_BLSE23_P11_PM | Balam Se 00035 | N1-E1-61A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230307DR | 2023-12-05 17:00 | 2023-12-17 18:00 | 2023-12-31 03:00 | Complete
Balam Se | P_BLSE23_P17_PM | Balam Se 00036 | N1-E1-61B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230308DR | 2023-12-31 03:00 | 2024-01-05 17:00 | 2024-01-18 06:30 | Complete
Balam So | BLSO23-P09 | Balam So 00576 | S1-O-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220604DR | 2024-01-18 06:30 | 2024-01-31 23:00 | 2024-02-15 16:00 | Complete
Balam Se | P_BLSE23_P12_PM | Balam Se 00039 | N1-E1-61C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230309DR | 2024-02-15 16:00 | 2024-02-24 03:00 | 2024-03-07 13:00 | Complete
Balam Se | P_BLSE23_P14_PM | Balam Se 00041 | N1-E1-61D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230310DR | 2024-03-07 13:00 | 2024-03-12 | 2024-03-26 | Complete
Balam Se | P_BLSE23_P18_PM | Balam Se 00042 | N1-E1-61E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230311DR | 2024-03-26 | 2024-03-31 15:00 | 2024-04-12 21:00 | Complete
Pinang | P_PINA24_02 | Pinang 00065 | N1-W1-51 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SPT2/402/3240823DR | 2024-06-16 10:00 | 2024-06-16 10:00 | 2024-07-06 03:00 | Complete
Pinang | P_PINA24_05 | Pinang 00066 | N1-W2-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SPT2/402/3240825DR | 2024-07-06 03:00 | 2024-07-12 17:00 |  | In Progress
Pudu | PDU23_P08 | Pudu 00022 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-53.2 | SSN2/402/3230698DR | 2024-06-27 17:00 | 2024-06-27 17:00 |  | In Progress
Pukat | P_PUKA23_P03 | Pukat 00007 | S1-O-41A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-54.2 | SPS2/402/3240894DR | 2024-06-13 20:00 | 2024-06-13 20:00 | 2024-07-04 20:30 | Complete
Pukat | P_PUKA23_P04 | Pukat 00008 | S1-O-41B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-54.2 | SPS2/402/3240896DR | 2024-07-04 20:30 | 2024-07-11 21:00 | 2024-07-11 21:00 | In Progress
Bangko | BNK-X02 | Bangko 00389 | O-O-21C | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-02 | GRK2/402/2220069DR | 2023-01-14 14:00 |  | 2023-01-14 17:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-02 | SSO2/402/3220383DR | 2023-08-13 16:00 |  | 2023-08-13 20:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-03 | SSO2/402/3220383DR | 2023-03-30 13:00 |  | 2023-03-30 17:00 | Complete
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Surface Systems Maintenance | SRF04 - Well Head Repair/ Change/ Modify | Mast Unit | PHW-03 | PNA2/402/3220823DR | 2023-07-06 14:00 |  | 2023-07-06 19:00 | Complete
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-03 | PNG2/402/3220837DR | 2023-08-09 13:00 |  | 2023-08-09 18:00 | Complete
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSO2/402/3220588DR | 2024-02-17 14:00 | 2023-11-15 21:00 | 2024-02-22 16:00 | Complete
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSE2/402/3230364DR | 2024-02-28 12:00 | 2024-02-26 20:00 | 2024-03-01 10:00 | Complete
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSO2/402/3220548DR | 2024-04-21 14:00 | 2024-05-05 05:00 | 2024-04-24 19:00 | Complete
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSO2/402/3220383DR | 2024-06-21 09:00 | 2024-06-10 17:00 | 2024-06-25 15:00 | In Progress
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSE2/402/3230355DR | 2024-07-11 14:00 | 2024-06-12 16:00 | 2024-07-14 17:00 | Suspended
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSE2/402/3230350DR | 2024-07-11 14:00 | 2024-05-25 10:00 | 2024-07-15 17:00 | Suspended
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-021 | SSO2/402/3220416DR | 2024-06-06 19:00 | 2024-05-20 02:00 | 2024-06-10 16:00 | Complete
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Swabbing Unit | WCT-025 | MBS2/402/3230833EX | 2024-06-21 16:30 | 2024-05-16 | 2024-06-25 16:30 | Complete

## Present
Pematang | Pematang P11 | Pematang 00108 | S1-E1-43B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210093DR | 2021-07-26 21:00 | 2021-07-26 21:00 | 2021-08-23 21:30 | COMPLETE
Pematang | Pematang P11 | Pematang 00108 | S1-E1-43B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ABI-88 | GRK2/402/2210093DR | 2021-08-23 21:30 | 2021-07-26 21:00 | 2021-08-26 15:00 | COMPLETE
Petani | Petani P01 | Petani 00130 | O-O-76B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210139DR | 2021-08-26 15:00 | 2021-09-04 04:00 | 2021-09-22 22:30 | COMPLETE
Petani | Petani P03 | Petani 00131 | O-O-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210140DR | 2021-09-21 22:30 | 2021-09-26 02:30 | 2021-10-13 04:00 | COMPLETE
Petani | PTN-P3 | Petani 00132 | O-O-77B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210143DR | 2021-10-13 04:00 | 2021-10-18 09:00 | 2021-11-05 21:30 | COMPLETE
Petani | PTN-P4 | Petani 00133 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210144DR | 2021-11-05 21:30 | 2021-11-10 21:30 | 2021-11-30 | COMPLETE
Petani | PTN-P1 | Petani 00134 | N1-W1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210141DR | 2021-11-30 | 2021-12-05 | 2021-12-25 09:00 | COMPLETE
Petani | PTN-X10 | Petani 00135 | S1-O-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2210142DR | 2021-12-25 09:00 | 2021-12-31 | 2022-02-02 13:00 | COMPLETE
Petani | PTN-P2 | Petani 00137 | S1-O-14D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220243DR | 2022-02-02 13:00 | 2022-02-07 21:00 | 2022-02-25 14:00 | COMPLETE
Petani | PTN-X09 | Petani 00139 | O-O-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220245DR | 2022-02-25 14:00 | 2022-03-02 18:00 | 2022-03-21 03:00 | RELEASE
Petani | PTN-X08 | Petani 00140 | O-O-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220247DR | 2022-03-21 03:00 | 2022-03-27 11:30 | 2022-04-11 | COMPLETE
Petani | PTN-X12 | Petani 00143 | O-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220248DR | 2022-04-11 | 2022-04-15 14:00 | 2022-04-30 | COMPLETE
Petani | PTN-X13 | Petani 00146 | O-O-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220252DR | 2022-04-30 | 2022-05-05 | 2022-05-20 16:00 | COMPLETE
Petani | PETA22-P23 | Petani 00147 | O-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220255DR | 2022-05-20 16:00 | 2022-05-30 03:00 | 2022-06-14 21:30 | COMPLETE
Petani | PETA22-P04 | Petani 00150 | O-O-32D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220256DR | 2022-06-14 21:30 | 2022-06-20 21:00 | 2022-07-16 05:00 | COMPLETE
Petani | PETA22-P06 | Petani 00152 | O-O-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | GRK2/402/2220254DR | 2022-07-16 05:00 | 2022-07-22 07:00 | 2022-08-12 | COMPLETE
Petani | PETA22-INJ4 | Petani 00156 | N1-W1-25A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220505DR | 2022-08-12 | 2022-08-17 12:00 | 2022-09-04 03:30 | COMPLETE
Pematang | PMT-P02 | Pematang 00110 | O-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220520DR | 2022-09-04 03:30 | 2022-09-14 00:30 | 2022-11-08 22:00 | COMPLETE
Pematang | PMT-P17 | Pematang 00113 | O-O-52E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220344DR | 2022-11-08 22:00 | 2022-11-21 12:00 | 2022-12-14 02:00 | RELEASE
Petani | PETA22-P28 | Petani 00165 | O-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTK2/402/3220811DR | 2022-12-14 02:00 | 2022-12-24 14:00 | 2023-01-14 19:00 | COMPLETE
Petani | PETA23-P32 | Petani 00166 | O-O-54D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTL2/402/3220812DR | 2023-01-14 19:00 | 2023-01-21 01:30 | 2023-02-09 12:00 | COMPLETE
Petani | PETA23_P14 | Petani 00167 | O-O-85G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220903DR | 2023-02-09 12:00 | 2023-02-24 | 2023-03-18 | COMPLETE
Petani | PETA22-P19 | Petani 00168 | O-O-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220913DR | 2023-03-18 | 2023-04-09 08:00 | 2023-04-30 19:00 | COMPLETE
Petani | PETA23-P34 | Petani 00173 | O-O-85D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220914DR | 2023-04-30 19:00 | 2023-05-04 14:30 | 2023-05-28 05:00 | COMPLETE
Petani | PETA23-P30 | Petani 00174 | O-O-85E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220912DR | 2023-05-28 05:00 | 2023-05-31 18:00 | 2023-06-20 | COMPLETE
Petani | PETA23_P12 | Petani 00178 | O-O-85F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230291DR | 2023-06-20 | 2023-06-23 10:00 | 2023-07-10 16:00 | COMPLETE
Petani | PETA23-P33 | Petani 00181 | O-O-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230298DR | 2023-07-10 16:00 | 2023-07-15 14:00 | 2023-08-01 | COMPLETE
Petani | PETA23_P10 | Petani 00182 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | PTH2/402/3220808DR | 2023-08-01 | 2023-08-04 22:00 | 2023-08-22 07:00 | COMPLETE
Petani | PT22_P21 | Petani 00187 | O-O-63D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230300DR | 2023-08-22 07:00 | 2023-08-25 12:30 | 2023-09-12 14:00 | COMPLETE
Petani | PETA22-INJ3 | Petani 00189 | S1-O-15C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSA2/402/3220917DR | 2023-09-12 14:00 | 2023-09-17 21:00 | 2023-10-12 | COMPLETE
Petani | PETA23B-P03 | Petani 00192 | O-O-63E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230301DR | 2023-10-12 | 2023-10-16 14:00 | 2023-10-30 19:00 | COMPLETE
Petani | PETA23_P07 | Petani 00196 | O-O63F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSM2/402/3230302DR | 2023-10-30 19:00 | 2023-11-04 01:00 | 2023-11-20 13:30 | COMPLETE
Kopar | KPR-X20 | Kopar 00040 | O-O-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220622DR | 2023-11-20 13:30 | 2023-11-28 13:30 | 2023-12-22 10:30 | RELEASE
Kopar | KPR-X18 | Kopar 00042 | Kopar O-O-86A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220621DR | 2023-12-22 10:30 | 2024-03-26 05:30 | 2024-04-21 22:00 | COMPLETE
Pudu | PDU23_P02 | Pudu 00021 | O-O-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSN2/402/3230693DR | 2024-01-31 17:00 | 2024-02-15 04:00 | 2024-03-13 15:00 | COMPLETE
Kopar | KPR-X09 | Kopar 00044 | O-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ABI-88 | SSO2/402/3220618DR | 2024-04-21 22:00 | 2024-04-29 06:00 | 2024-05-19 13:00 | COMPLETE
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210093DR | 2021-11-04 16:00 | 2021-11-08 03:00 | 2021-11-13 20:00 | COMPLETE
Bangko | BNK-P25 | Bangko 00353 | N1-W1-11A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210053DR | 2021-12-02 22:00 | 2021-12-04 02:00 | 2021-12-10 17:00 | COMPLETE
Bangko | BNK-P32 | Bangko 00352 | N1-W3-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ACS-005 | GRK2/402/2210061DR | 2021-12-18 02:30 | 2021-12-21 22:00 | 2021-12-27 16:00 | COMPLETE
Bangko | BNK-P1 | Bangko 00382 | N1-W2-17C | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | ACS-005 | GRK2/402/2220060DR | 2022-05-08 05:00 | 2022-05-09 21:00 | 2022-05-10 07:00 | COMPLETE
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ACS-005 | GRK2/402/2210123DR | 2022-05-27 22:00 | 2022-05-28 16:00 | 2022-06-05 11:00 | COMPLETE
Minas | MINAHW23_P08 | Minas 02124 | 6C-19A | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | ACS-006 | SSM2/402/3230251DR | 2024-07-07 | 2024-07-07 22:00 | 2024-07-09 12:00 | COMPLETE
Pematang | Pematang P05 | Pematang 00107 | O-O-32B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210093DR | 2021-07-18 22:30 | 2021-07-18 22:30 | 2021-08-15 21:30 | COMPLETE
Pematang | Pematang P05 | Pematang 00107 | O-O-32B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210093DR | 2021-08-15 21:30 | 2021-07-18 22:30 | 2021-08-19 01:00 | COMPLETE
Pemburu | PEMB21-P04 | Pemburu 00034 | S1-W1-38B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210121DR | 2021-08-16 | 2021-09-05 05:00 | 2021-09-06 17:00 | COMPLETE
Pemburu | PEMB21-P04 | Pemburu 00034 | S1-W1-38B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210121DR | 2021-08-19 01:00 | 2021-08-28 14:00 | 2021-09-06 17:00 | COMPLETE
Pemburu | PEMB21-P05 | Pemburu 00035 | S1-W1-37E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210122DR | 2021-09-06 17:00 | 2021-09-13 13:00 | 2021-09-23 | COMPLETE
Pemburu | PEMB21-P05 | Pemburu 00035 | S1-W1-37E | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-009 | GRK2/402/2210122DR | 2021-09-21 | 2021-09-21 | 2021-09-23 | COMPLETE
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210123DR | 2021-09-23 | 2021-09-27 05:00 | 2021-10-05 18:00 | COMPLETE
Pemburu | PEMB21-P01 | Pemburu 00037 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210124DR | 2021-10-05 18:00 | 2021-10-09 15:00 | 2021-10-19 | COMPLETE
Pemburu | PEMB21-P03 | Pemburu 00038 | O-O-65D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210125DR | 2021-10-19 | 2021-10-24 16:00 | 2021-11-02 | COMPLETE
Bangko | BNK-P38 | Bangko 00366 | N1-W2-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210062DR | 2021-11-02 | 2021-11-13 20:00 | 2021-11-25 22:00 | COMPLETE
Bangko | BNK-P24 | Bangko 00362 | N2-W1-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210052DR | 2021-11-25 22:00 | 2021-11-30 15:00 | 2021-12-10 22:00 | COMPLETE
Bangko | BNK-P35 | Bangko 00370 | N1-W1-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210064DR | 2021-12-10 22:00 | 2021-12-29 19:00 | 2022-01-17 15:00 | COMPLETE
Bangko | BNK-P13 | Bangko 00358 | N1-W2-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2210041DR | 2022-01-17 15:00 | 2022-01-29 19:00 | 2022-02-10 10:30 | COMPLETE
Duri | 6R-88B | Duri 10913 | 6R-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220098DR | 2022-02-10 10:30 | 2022-02-24 23:30 | 2022-03-13 10:00 | COMPLETE
Duri | 3H-53C | Duri 10925 | 3H-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220105DR | 2022-03-13 10:00 | 2022-03-23 23:30 | 2022-04-06 16:00 | COMPLETE
Duri | 3G-0502B | Duri 10932 | 3G-0502B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220110DR | 2022-04-06 16:00 | 2022-04-10 23:00 | 2022-05-02 19:00 | COMPLETE
Duri | 3G-1002C | Duri 10938 | 3G-1002C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220117DR | 2022-05-02 19:00 | 2022-05-08 06:00 | 2022-05-20 19:00 | COMPLETE
Duri | 5L-74D | Duri 10945 | 5L-74D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220123DR | 2022-05-20 19:00 | 2022-05-25 21:00 | 2022-06-05 07:00 | COMPLETE
Duri | 4N-11C | Duri 10951 | 4N-11C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220127DR | 2022-06-05 07:00 | 2022-06-09 11:00 | 2022-06-20 21:00 | COMPLETE
Duri | 3N-26B | Duri 10954 | 3N-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220132DR | 2022-06-20 21:00 | 2022-06-28 13:00 | 2022-07-09 04:00 | COMPLETE
Duri | 3N-35G | Duri 10958 | 3N-35G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220137DR | 2022-07-09 04:00 | 2022-07-11 19:00 | 2022-07-30 21:00 | COMPLETE
Duri | 6N-62D | Duri 10964 | 6N-62D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | GRK2/402/2220142DR | 2022-07-30 21:00 | 2022-08-03 07:00 | 2022-08-13 08:30 | COMPLETE
Pager | PG22-P16 | Pager 00051 | O-O-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220322DR | 2022-08-13 08:30 | 2022-08-29 16:00 | 2022-09-13 19:00 | RELEASE
Pager | PG22-P06 | Pager 00052 | O-O-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220331DR | 2022-09-13 19:00 | 2022-09-19 07:00 | 2022-10-06 12:00 | RELEASE
Sintong | SIN-P06 | Sintong 00052 | O-W1-67A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220661DR | 2022-10-06 12:00 | 2022-10-26 20:00 | 2022-11-09 17:30 | COMPLETE
Sintong | SIN-P03 | Sintong 00053 | S1-O-13B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220421DR | 2022-11-09 17:30 | 2022-11-16 18:00 | 2022-11-28 16:00 | COMPLETE
Sintong | SIN-P04 | Sintong 00054 | O-O-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220375DR | 2022-11-28 16:00 | 2022-12-05 10:00 | 2022-12-25 05:30 | COMPLETE
Sintong | SIN-P02 | Sintong 00055 | O-O-71B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220395DR | 2022-12-25 05:30 | 2022-12-28 10:00 | 2023-01-14 | COMPLETE
Sintong | SIN-P01 | Sintong 00056 | S1-O-34A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220444DR | 2023-01-14 | 2023-01-20 | 2023-02-09 | COMPLETE
Sintong | SIN-P05 | Sintong 00057 | O-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220349DR | 2023-02-09 | 2023-02-28 | 2023-03-16 10:00 | COMPLETE
Benar | BNR-X17 | Benar 00067 | O-O-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220846DR | 2023-03-16 10:00 | 2023-03-27 18:00 | 2023-04-07 14:00 | COMPLETE
Benar | BNR-X18 | Benar 00069 | O-O-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220847DR | 2023-04-07 14:00 | 2023-04-13 21:00 | 2023-04-24 | COMPLETE
Benar | BNR-X24 | Benar 00070 | O-O-46D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SBN2/402/3220848DR | 2023-04-24 | 2023-05-01 | 2023-05-11 05:00 | COMPLETE
Bekasap | BKS-X02 | Bekasap 00228 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220452DR | 2023-05-11 05:00 | 2023-05-27 10:00 | 2023-06-06 02:00 | COMPLETE
Bekasap | BKS-X06 | Bekasap 00229 | S1-O-27D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSO2/402/3220614DR | 2023-06-06 02:00 | 2023-06-11 03:00 | 2023-06-23 09:00 | COMPLETE
Bekasap | BKS-X03 | Bekasap 00230 | S1-O-27C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230153DR | 2023-06-23 09:00 | 2023-06-27 07:00 | 2023-07-08 12:30 | COMPLETE
Bekasap | BKS-X04 | Bekasap 00231 | S1-O-27E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3220886DR | 2023-07-08 12:30 | 2023-07-13 | 2023-07-23 13:00 | COMPLETE
Pungut | PUNG23_D01 | Pungut 00050 | S2-E1-11B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230199DR | 2023-07-23 13:00 | 2023-08-03 10:00 | 2023-08-14 15:30 | COMPLETE
Pungut | PUNG23_P16 | Pungut 00051 | S2-E1-23A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230202DR | 2023-08-14 15:30 | 2023-08-20 08:30 | 2023-09-02 | COMPLETE
Pungut | PUNG23_D02A | Pungut 00052 | S1-E1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSM2/402/3230197DR | 2023-09-02 | 2023-09-07 | 2023-09-17 22:00 | COMPLETE
Duri | 3H-65C | Duri 11118 | 3H-65C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230106DR | 2023-09-17 22:00 | 2023-09-28 11:00 | 2023-11-05 13:00 | COMPLETE
Duri | 3L-18D | Duri 11131 | 3L-18D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230110DR | 2023-11-05 13:00 | 2023-11-13 16:00 | 2023-11-29 19:00 | COMPLETE
Duri | 5G-1101A | Duri 11155 | 5G-1101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230108DR | 2023-11-29 19:00 | 2023-12-25 10:30 | 2024-03-11 10:30 | COMPLETE
Duri | 5S-88B | Duri 11163 | 5S-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230111DR | 2023-12-31 10:00 | 2024-01-23 16:00 | 2024-02-04 10:30 | COMPLETE
Duri | 7S-22B | Duri 11176 | 7S-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230109DR | 2024-02-04 10:30 | 2024-02-11 01:15 | 2024-02-27 09:30 | COMPLETE
Duri | 4G-70D | Duri 11190 | 4G-70D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230107DR | 2024-03-11 10:30 | 2024-03-16 22:00 | 2024-03-28 22:30 | COMPLETE
Duri | 3J-33B | Duri 11195 | 3J-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2230105DR | 2024-03-28 22:30 | 2024-04-02 07:30 | 2024-04-18 05:00 | COMPLETE
Duri | 4H-54C | Duri 11200 | 4H-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | RHT2/402/2240033DR | 2024-04-18 05:00 | 2024-04-22 18:00 | 2024-05-05 20:00 | COMPLETE
Bekasap So | P_BESO24_03 | Bekasap So 00017 | S3-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSN2/402/3230683DR | 2024-05-05 20:00 | 2024-05-14 13:00 | 2024-05-30 13:00 | COMPLETE
Pematang | P_PEMA24_10 | Pematang 00137 | O-O-52M | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230159DR | 2024-05-30 13:00 | 2024-06-04 17:00 | 2024-06-22 06:00 | COMPLETE
Pematang | P_PEMA24_08 | Pematang 00138 | O-O-52L | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230157DR | 2024-06-22 06:00 | 2024-06-25 12:00 | 2024-07-11 07:00 | COMPLETE
Pematang | P_PEMA24_07 | Pematang 00140 | O-O-52K | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-009 | SSA2/402/3230156DR | 2024-07-11 07:00 |  |  | IN_PROGRESS
Minas | MNA-P3 | Minas 01988 | 8D-67N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220197DR | 2022-01-01 | 2022-01-01 | 2022-01-17 | COMPLETE
Minas | MNA-P8 | Minas 01990 | 8D-66N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220199DR | 2022-01-17 | 2022-01-19 20:00 | 2022-02-01 13:00 | COMPLETE
Minas | MNS-P16 | Minas 01991 | 8E-53E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3210109DR | 2022-02-01 13:00 | 2022-02-08 05:00 | 2022-02-27 | COMPLETE
Minas | MNA-P7 | Minas 01993 | 8E-61N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220202DR | 2022-02-27 | 2022-03-05 | 2022-03-15 12:00 | RELEASE
Minas | MNS-P4 | Minas 01994 | 8E-51E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220205DR | 2022-03-15 12:00 | 2022-03-19 13:00 | 2022-03-30 17:00 | COMPLETE
Minas | MNA-P9 | Minas 01996 | 8E-41N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220207DR | 2022-03-30 17:00 | 2022-04-04 17:00 | 2022-04-18 01:00 | COMPLETE
Minas | MNA-P15 | Minas 01999 | 8E-36E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220206DR | 2022-04-18 01:00 | 2022-05-03 05:00 | 2022-05-14 19:30 | COMPLETE
Minas | MNS-P23 | Minas 02001 | 7E-88E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220203DR | 2022-05-14 19:30 | 2022-05-19 19:00 | 2022-05-30 08:00 | COMPLETE
Minas | P_5D-92E | Minas 02004 | 5D-92E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220215DR | 2022-05-30 08:00 | 2022-06-04 | 2022-06-15 06:30 | COMPLETE
Minas | P_7D-17S | Minas 02006 | 7D-17S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220219DR | 2022-06-15 06:30 | 2022-06-19 03:30 | 2022-06-29 05:00 | COMPLETE
Minas | P_6C-28E | Minas 02008 | 6C-28E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220230DR | 2022-06-29 05:00 | 2022-07-09 03:00 | 2022-07-17 19:30 | RELEASE
Minas | P_10D-24N | Minas 02012 | 10D-24N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220220DR | 2022-07-17 19:30 | 2022-07-23 17:00 | 2022-08-05 05:00 | COMPLETE
Minas | P_8E-54E | Minas 02015 | 8E-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | GRK2/402/3220222DR | 2022-08-05 05:00 | 2022-08-09 10:30 | 2022-08-21 22:00 | COMPLETE
Minas | P_6C-21N | Minas 02018 | 6C-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220514DR | 2022-08-21 22:00 | 2022-08-29 | 2022-09-05 18:30 | RELEASE
Minas | MNS-P08 | Minas 02021 | 9C-38 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220326DR | 2022-09-05 18:30 | 2022-09-14 02:00 | 2022-09-25 | COMPLETE
Minas | P_3D-74E | Minas 02023 | 3D-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220333DR | 2022-09-25 | 2022-10-03 02:15 | 2022-10-14 17:00 | COMPLETE
Minas | P_3D-73E | Minas 02026 | 3D-73E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220368DR | 2022-10-14 17:00 | 2022-10-18 19:00 | 2022-10-28 15:30 | COMPLETE
Minas | P_3D-64E | Minas 02027 | 3D-64E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220347DR | 2022-10-28 15:30 | 2022-11-01 01:00 | 2022-11-12 03:00 | COMPLETE
Minas | P_3D-34E1 | Minas 02030 | 3D-34E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220409DR | 2022-11-12 03:00 | 2022-11-23 10:00 | 2022-12-15 22:00 | COMPLETE
Minas | P_6C-89E | Minas 02034 | 6C-89E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220387DR | 2022-12-15 21:00 | 2022-12-31 23:00 | 2023-01-14 02:00 | RELEASE
Minas | P_4D-71E | Minas 02042 | 4D-71E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220448DR | 2023-01-14 02:00 | 2023-01-24 16:30 | 2023-02-06 19:00 | COMPLETE
Minas | P_3A-26N | Minas 02046 | 3A-26N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220633DR | 2023-02-06 19:00 | 2023-02-24 14:00 | 2023-03-13 15:45 | COMPLETE
Minas | P_10C-26 | Minas 02050 | 10C-26 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220646DR | 2023-03-13 15:45 | 2023-03-25 10:00 | 2023-04-06 05:00 | COMPLETE
Minas | P_7C-16N | Minas 02055 | 7C-16N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220644DR | 2023-04-06 05:00 | 2023-04-14 15:00 | 2023-04-23 05:00 | COMPLETE
Minas | P_7C-17S | Minas 02060 | 7C-17S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220650DR | 2023-04-23 05:00 | 2023-05-01 | 2023-05-11 03:00 | COMPLETE
Minas | P_5C-63 | Minas 02065 | 5C-63 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSO2/402/3220647DR | 2023-05-11 03:00 | 2023-05-17 | 2023-05-28 22:00 | COMPLETE
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230246DR | 2023-05-28 22:00 | 2023-06-03 08:00 | 2023-06-16 10:00 | COMPLETE
Minas | P_8E-46N | Minas 02073 | 8E-46N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230239DR | 2023-06-16 10:00 | 2023-06-23 02:30 | 2023-07-04 16:30 | COMPLETE
Minas | MNS-P21 | Minas 02075 | 9D-48E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230216DR | 2023-07-04 16:30 | 2023-07-10 05:30 | 2023-07-20 03:00 | RELEASE
Minas | MNS-P20 | Minas 02081 | 9D-28N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230214DR | 2023-07-20 03:00 | 2023-07-24 07:00 | 2023-08-03 04:30 | COMPLETE
Minas | P_7D-32E | Minas 02085 | 7D-32E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230224DR | 2023-08-03 04:30 | 2023-08-08 | 2023-08-19 03:30 | COMPLETE
Minas | P_7D-42E | Minas 02089 | 7D-42E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230218DR | 2023-08-19 03:30 | 2023-08-21 21:30 | 2023-08-31 09:30 | COMPLETE
Minas | P_7D-43N | Minas 02093 | 7D-43N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230221DR | 2023-08-31 09:30 | 2023-09-02 22:00 | 2023-09-11 12:00 | COMPLETE
Minas | P_MINA24_7E-93E | Minas 02094 | 7E-93E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230510DR | 2023-09-11 12:00 | 2023-09-16 11:30 | 2023-09-24 09:00 | COMPLETE
Minas | P_MINA24_3D-13N | Minas 02096 | 3D-13N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230512DR | 2023-09-24 09:00 | 2023-09-30 10:00 | 2023-10-07 21:00 | COMPLETE
Minas | P_3D-12N | Minas 02099 | 3D-12N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230229DR | 2023-10-07 21:00 | 2023-10-11 00:30 | 2023-10-18 05:00 | COMPLETE
Minas | P_2D-85N | Minas 02103 | 2D-85N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230241DR | 2023-10-18 05:00 | 2023-10-22 14:30 | 2023-10-30 15:00 | COMPLETE
Minas | P_MINA24_8E-44E | Minas 02106 | 8E-44E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230506DR | 2023-10-30 15:00 | 2023-11-06 16:30 | 2023-11-16 05:00 | COMPLETE
Minas | P_3A-92E | Minas 02109 | 3A-92E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230219DR | 2023-11-16 05:00 | 2023-11-23 10:00 | 2023-12-04 10:00 | RELEASE
Minas | P_MINA24_3D-55N | Minas 02112 | 3D-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230491DR | 2023-12-04 10:00 | 2023-12-12 14:00 | 2023-12-22 21:30 | COMPLETE
Minas | P_MINA24_6B-29N | Minas 02116 | 6B-29N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230514DR | 2023-12-22 21:30 | 2024-02-06 00:30 | 2024-02-14 19:00 | COMPLETE
Minas | P_MINA24_8C-77E | Minas 02120 | 8C-77E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-010 | SSM2/402/3230500DR | 2024-02-14 19:00 | 2024-02-28 15:00 | 2024-03-09 | COMPLETE
Balam So | BLSO-P28 | Balam So 00449 | N1-W1-46B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | ACS-015 | GRK2/402/2220012DR | 2022-06-07 21:30 | 2022-06-09 19:00 | 2022-06-11 | COMPLETE
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210065DR | 2021-11-18 12:00 | 2021-11-18 12:00 | 2021-12-12 16:00 | RELEASE
Bangko | BNK-P37 | Bangko 00371 | N1-W1-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210068DR | 2021-12-12 16:00 | 2021-12-16 04:00 | 2021-12-29 16:30 | COMPLETE
Balam So | BLSO-P14 | Balam So 00448 | O-O-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2210003DR | 2021-12-29 16:30 | 2022-01-19 05:00 | 2022-01-28 17:00 | COMPLETE
Duri | 5G-0812B | Duri 10916 | 5G-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220108DR | 2022-01-28 17:00 | 2022-02-08 | 2022-02-14 | COMPLETE
Duri | 4H-1113B | Duri 10915 | 4H-1113B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220100DR | 2022-02-14 | 2022-02-17 09:00 | 2022-02-23 08:00 | COMPLETE
Duri | 5F-1012B | Duri 10914 | 5F-1012B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220104DR | 2022-02-23 08:00 | 2022-02-26 05:00 | 2022-03-03 17:00 | COMPLETE
Duri | 5F-1212B | Duri 10918 | 5F-1212B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220107DR | 2022-03-03 17:00 | 2022-03-05 20:00 | 2022-03-11 12:00 | COMPLETE
Duri | 5H-0704B | Duri 10921 | 5H-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220115DR | 2022-03-11 12:00 | 2022-03-14 11:00 | 2022-03-20 02:00 | COMPLETE
Duri | 6G-0703B | Duri 10924 | 6G-0703B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220118DR | 2022-03-20 02:00 | 2022-03-22 18:00 | 2022-03-28 05:00 | COMPLETE
Duri | 6G-0101B | Duri 10928 | 6G-0101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220113DR | 2022-03-28 05:00 | 2022-03-30 17:00 | 2022-04-04 18:00 | COMPLETE
Duri | 5E-1007B | Duri 10933 | 5E-1007B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220119DR | 2022-04-04 18:00 | 2022-04-06 15:00 | 2022-04-11 09:00 | COMPLETE
Duri | 5E-0809B | Duri 10935 | 5E-0809B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220150DR | 2022-04-11 09:00 | 2022-04-18 12:00 | 2022-04-27 16:00 | COMPLETE
Balam So | BLSO-P06 | Balam So 00466 | O-O-35F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220007DR | 2022-04-27 15:00 | 2022-05-05 16:00 | 2022-05-14 07:00 | COMPLETE
Balam So | BLSO-P17 | Balam So 00472 | O-O-35G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220025DR | 2022-05-14 17:00 | 2022-05-17 04:00 | 2022-05-24 11:00 | RELEASE
Balam So | BLSO-P20 | Balam So 00478 | O-O-16C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220020DR | 2022-05-24 11:00 | 2022-05-28 21:30 | 2022-06-05 17:00 | COMPLETE
Balam So | BLSO-P18 | Balam So 00475 | O-O-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220014DR | 2022-06-05 17:00 | 2022-06-07 16:00 | 2022-06-14 13:00 | COMPLETE
Balam So | LQR-TE195_BLSO_39 | Balam So 00488 | N1-W1-78A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220050DR | 2022-06-14 13:00 | 2022-06-19 06:00 | 2022-06-27 03:00 | COMPLETE
Balam So | LQR-TE017_BLSO_38 | Balam So 00484 | N1-W1-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220033DR | 2022-06-27 03:00 | 2022-06-29 06:00 | 2022-07-06 10:00 | COMPLETE
Balam So | LQR-TE073_BLSO_1 | Balam So 00492 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220034DR | 2022-07-06 10:00 | 2022-07-09 03:00 | 2022-07-16 09:30 | COMPLETE
Balam So | LQR-TE031_BLSO_6 | Balam So 00506 | O-O-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220052DR | 2022-07-16 09:30 | 2022-07-18 14:00 | 2022-07-26 17:00 | COMPLETE
Balam So | LQR-TE041_BLSO_3 | Balam So 00496 | O-O-44G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/2220042DR | 2022-07-26 17:00 | 2022-07-28 17:00 | 2022-08-05 | COMPLETE
Balam So | BLSO-P48 | Balam So 00503 | BLSO O-O-44H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | GRK2/402/3220221DR | 2022-08-05 | 2022-08-07 12:00 | 2022-08-14 06:45 | COMPLETE
Balam So | BLSO-P43 | Balam So 00509 | O-O-44I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220318DR | 2022-08-14 06:45 | 2022-08-16 06:45 | 2022-08-24 05:00 | COMPLETE
Balam So | LQR-TE197_BLSO_40 | Balam So 00486 | N1-O-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220324DR | 2022-08-24 05:00 | 2022-08-28 19:00 | 2022-09-06 08:30 | COMPLETE
Balam So | BLSO-P47 | Balam So 00489 | O-O-44M | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220328DR | 2022-09-06 08:30 | 2022-09-11 01:30 | 2022-09-20 07:30 | COMPLETE
Balam So | BLSO-P36 | Balam So 00491 | O-O-44N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220529DR | 2022-09-20 07:30 | 2022-09-22 05:00 | 2022-10-01 09:30 | COMPLETE
Balam So | BLSO-P42 | Balam So 00499 | N1-W1-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220329DR | 2022-10-01 09:30 | 2022-10-07 03:00 | 2022-10-16 18:00 | COMPLETE
Balam So | BLSO-P40 | Balam So 00507 | N1-O-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220404DR | 2022-10-16 18:00 | 2022-10-21 01:00 | 2022-11-01 19:00 | COMPLETE
Balam So | LQR-TE142_BLSO_4 | Balam So 00508 | N1-O-76D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220540DR | 2022-11-01 19:00 | 2022-11-05 06:00 | 2022-11-15 | COMPLETE
Balam So | LQR-TE081_BLSO_14 | Balam So 00510 | O-O-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220543DR | 2022-11-15 | 2022-11-19 21:00 | 2022-11-30 04:00 | COMPLETE
Balam So | LQR-TE002_BLSO_42 | Balam So 00512 | N1-W1-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220362DR | 2022-11-30 04:00 | 2022-12-04 02:00 | 2022-12-11 05:00 | COMPLETE
Balam So | BLSO23-P11 | Balam So 00513 | N1-O-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220590DR | 2022-12-11 05:00 | 2022-12-21 05:00 | 2023-01-01 03:00 | COMPLETE
Balam So | BLSO23-P06 | Balam So 00515 | O-O-44L | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220592DR | 2023-01-01 03:00 | 2023-01-07 02:00 | 2023-01-16 08:00 | COMPLETE
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220554DR | 2023-01-16 08:00 | 2023-01-19 14:00 | 2023-01-24 21:00 | COMPLETE
Balam So | BLSO23-LQR-TE015 | Balam So 00519 | O-O-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | SSO2/402/3220399DR | 2023-01-24 21:00 | 2023-01-30 09:00 | 2023-02-08 | COMPLETE
Duri | 6G-0903B | Duri 11035 | 6G-0903B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220574DR | 2023-02-08 | 2023-02-25 01:00 | 2023-03-03 08:00 | COMPLETE
Duri | 6L-87B | Duri 11036 | 6L-87B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220492DR | 2023-03-03 08:00 | 2023-03-08 23:30 | 2023-03-16 18:00 | COMPLETE
Duri | 7M-59D | Duri 11037 | 7M-59D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220575DR | 2023-03-16 18:00 | 2023-03-20 16:30 | 2023-03-28 12:00 | COMPLETE
Duri | 6G-1001B | Duri 11049 | 6G-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220856DR | 2023-03-28 12:00 | 2023-04-01 19:00 | 2023-04-07 09:00 | COMPLETE
Duri | 6G-1003C | Duri 11041 | 6G-1003C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220875DR | 2023-04-07 09:00 | 2023-04-09 16:00 | 2023-04-15 18:00 | COMPLETE
Duri | 5G-0704B | Duri 11054 | 5G-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220854DR | 2023-04-15 18:00 | 2023-04-18 09:00 | 2023-04-24 17:00 | COMPLETE
Duri | 6G-0702B | Duri 11025 | 6G-0702B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230057DR | 2023-04-24 17:00 | 2023-04-26 21:00 | 2023-05-03 21:00 | COMPLETE
Duri | 5H-0306B | Duri 11056 | 5H-0306B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220859DR | 2023-05-03 21:00 | 2023-05-07 02:30 | 2023-05-12 09:00 | COMPLETE
Duri | 6G-0502B | Duri 11065 | 6G-0502B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | ADH2/402/2220860DR | 2023-05-12 09:00 | 2023-05-14 17:00 | 2023-05-20 10:30 | COMPLETE
Duri | 6G-0502C | Duri 11066 | 6G-0502C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230112DR | 2023-05-20 10:30 | 2023-05-22 15:00 | 2023-05-28 06:00 | COMPLETE
Duri | 6G-0203B | Duri 11032 | 6G-0203B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | DRI2/402/3220827DR | 2023-05-28 06:00 | 2023-05-31 02:00 | 2023-06-06 14:00 | COMPLETE
Duri | 6G-0203C | Duri 11058 | 6G-0203C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230069DR | 2023-06-06 14:00 | 2023-06-08 13:00 | 2023-06-15 03:00 | COMPLETE
Duri | 2J-0911A | Duri 11081 | 2J-0911A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220739DR | 2023-06-15 03:00 | 2023-06-19 03:00 | 2023-06-26 19:00 | COMPLETE
Duri | 2H-0507B | Duri 11074 | 2H-0507B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220734DR | 2023-06-26 19:00 | 2023-07-01 10:00 | 2023-07-13 06:00 | COMPLETE
Duri | 2J-0411B | Duri 11082 | 2J-0411B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220766DR | 2023-07-13 06:00 | 2023-07-16 02:30 | 2023-07-22 10:00 | COMPLETE
Duri | 5G-0213B | Duri 11088 | 5G-0213B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230062DR | 2023-07-22 10:00 | 2023-07-25 03:30 | 2023-08-01 07:00 | COMPLETE
Duri | 5F-0210C | Duri 11089 | 5F-0210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230063DR | 2023-08-01 07:00 | 2023-08-02 22:30 | 2023-08-08 20:00 | COMPLETE
Duri | 5F-0208B | Duri 11098 | 5F-0208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230064DR | 2023-08-08 20:00 | 2023-08-10 22:30 | 2023-08-17 17:00 | COMPLETE
Duri | 5E-1107D | Duri 11099 | 5E-1107D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230065DR | 2023-08-17 17:00 | 2023-08-20 04:00 | 2023-08-26 11:00 | COMPLETE
Duri | 5F-0810B | Duri 11101 | 5F-0810B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230081DR | 2023-08-26 11:00 | 2023-08-29 12:00 | 2023-09-04 18:00 | COMPLETE
Duri | 5G-0210B | Duri 11102 | 5G-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230082DR | 2023-09-04 18:00 | 2023-09-07 07:00 | 2023-09-13 12:00 | COMPLETE
Duri | 2J-0711A | Duri 11115 | 2J-0711A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220744DR | 2023-09-13 12:00 | 2023-09-16 02:00 | 2023-09-21 18:00 | COMPLETE
Duri | 2J-0111A | Duri 11116 | 2J-0111A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220770DR | 2023-09-21 18:00 | 2023-09-23 22:00 | 2023-09-30 | COMPLETE
Duri | 2H-1111A | Duri 11117 | 2H-1111A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220792DR | 2023-09-30 | 2023-10-01 10:00 | 2023-10-07 14:00 | COMPLETE
Duri | 2J-0612A | Duri 11124 | 2J-0612A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220752DR | 2023-10-07 14:00 | 2023-10-08 22:00 | 2023-10-14 14:30 | COMPLETE
Duri | 2J-0712B | Duri 11127 | 2J-0712B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220746DR | 2023-10-14 14:30 | 2023-10-15 20:00 | 2023-10-23 13:30 | COMPLETE
Duri | 2J-0812A | Duri 11133 | 2J-0812A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220747DR | 2023-10-23 13:30 | 2023-10-25 00:30 | 2023-10-31 18:00 | COMPLETE
Duri | 2J-0413B | Duri 11134 | 2J-0413B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220765DR | 2023-10-31 18:00 | 2023-11-03 12:00 | 2023-11-09 05:00 | COMPLETE
Duri | 2H-1212A | Duri 11135 | 2H-1212A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220798DR | 2023-11-09 05:00 | 2023-11-11 08:30 | 2023-11-18 18:00 | COMPLETE
Duri | 2J-0511A | Duri 11144 | 2J-0511A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220760DR | 2023-11-18 18:00 | 2023-11-21 03:00 | 2023-11-27 17:00 | COMPLETE
Duri | 3J-0501A | Duri 11145 | 3J-0501A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220755DR | 2023-11-27 17:00 | 2023-11-29 12:00 | 2023-12-06 18:00 | COMPLETE
Duri | 3H-1101A | Duri 11159 | 3H-1101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220785DR | 2023-12-06 18:00 | 2023-12-10 09:00 | 2023-12-16 | COMPLETE
Duri | 3J-0301A | Duri 11160 | 3J-0301A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220774DR | 2023-12-16 | 2023-12-24 20:00 | 2023-12-31 12:00 | COMPLETE
Duri | 2J-0212A | Duri 11166 | 2J-0212A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220780DR | 2023-12-31 12:00 | 2024-01-14 10:00 | 2024-01-24 06:00 | COMPLETE
Duri | 2J-0610A | Duri 11173 | 2J-0610A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220749DR | 2024-01-24 06:00 | 2024-01-30 05:00 | 2024-02-06 05:00 | COMPLETE
Duri | 2J-0210B | Duri 11174 | 2J-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220781DR | 2024-02-06 05:00 | 2024-02-10 13:00 | 2024-02-19 21:00 | COMPLETE
Duri | 2J-0311A | Duri 11178 | 2J-0311A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220772DR | 2024-02-19 21:00 | 2024-02-21 13:00 | 2024-02-28 06:00 | COMPLETE
Duri | 3J-0101A | Duri 11167 | 3J-0101A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220790DR | 2024-02-28 06:00 | 2024-03-01 17:00 | 2024-03-07 08:00 | COMPLETE
Duri | 2J-0412A | Duri 11179 | 2J-0412A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHO2/402/2220759DR | 2024-03-07 08:00 | 2024-03-12 22:30 | 2024-03-19 15:00 | COMPLETE
Duri | 4H-0912C | Duri 11193 | 4H-0912C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240066DR | 2024-03-19 15:00 | 2024-03-22 06:00 | 2024-03-28 22:00 | COMPLETE
Duri | 6G-0504B | Duri 11194 | 6G-0504B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240068DR | 2024-03-28 22:00 | 2024-03-31 | 2024-04-06 22:00 | COMPLETE
Duri | 3F-0402A | Duri 11203 | 3F-0402A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240069DR | 2024-04-06 22:00 | 2024-04-10 21:00 | 2024-04-18 19:00 | COMPLETE
Duri | 4K-20F | Duri 11204 | 4K-20F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240070DR | 2024-04-18 19:00 | 2024-04-21 02:00 | 2024-04-28 20:00 | COMPLETE
Duri | 5K-48F | Duri 11205 | 5K-48F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240071DR | 2024-04-28 20:00 | 2024-04-30 23:30 | 2024-05-07 18:00 | COMPLETE
Duri | 5G-1012C | Duri 11213 | 5G-1012C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240075DR | 2024-05-07 18:00 | 2024-05-09 15:00 | 2024-05-16 06:00 | COMPLETE
Duri | 5G-1012D | Duri 11217 | 5G-1012D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240072DR | 2024-05-16 06:00 | 2024-05-17 14:30 | 2024-05-26 | COMPLETE
Duri | 6F-1203C | Duri 11220 | 6F-1203C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240073DR | 2024-05-26 | 2024-05-28 21:00 | 2024-06-04 10:00 | COMPLETE
Duri | 5F-0606C | Duri 11221 | 5F-0606C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240074DR | 2024-06-04 10:00 | 2024-06-06 18:00 | 2024-06-13 12:00 | COMPLETE
Duri | 9M-102A | Duri 11235 | 9M-102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230734DR | 2024-06-13 12:00 | 2024-06-16 02:00 | 2024-06-20 19:30 | COMPLETE
Duri | 8L-54A | Duri 11237 | 8L-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2230733DR | 2024-06-20 19:30 | 2024-06-23 13:00 | 2024-06-27 21:00 | COMPLETE
Duri | 5E-1209C | Duri 11247 | 5E-1209C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240883DR | 2024-06-27 21:00 | 2024-06-30 18:00 | 2024-07-06 21:00 | COMPLETE
Duri | 5E-0810B | Duri 11251 | 5E-0810B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240041DR | 2024-07-06 21:00 | 2024-07-08 03:30 | 2024-07-14 18:00 | COMPLETE
Duri | 5F-0407B | Duri 11257 | 5F-0407B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-017 | RHT2/402/2240042DR | 2024-07-14 18:00 |  |  | IN_PROGRESS
Duri | P_3Q39C | Duri 10855 | 3Q-39C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210093DR | 2021-08-03 21:00 | 2021-08-05 20:00 | 2021-08-09 16:00 | COMPLETE
Duri | P_3R33E | Duri 10856 | 3R-33E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210025DR | 2021-08-09 16:00 | 2021-08-11 02:30 | 2021-08-14 22:00 | COMPLETE
Duri | P_3R52B | Duri 10857 | 3R-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210026DR | 2021-08-14 22:00 | 2021-08-16 04:00 | 2021-08-20 03:30 | COMPLETE
Duri | P_6M53C | Duri 10861 | 6M-53C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210028DR | 2021-08-20 03:30 | 2021-08-21 21:30 | 2021-08-25 05:00 | COMPLETE
Duri | P_3P61E | Duri 10862 | 3P-61E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210027DR | 2021-08-25 05:00 | 2021-08-26 13:00 | 2021-08-31 06:00 | COMPLETE
Duri | 6G-1004B | Duri 10863 | 6G-1004B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210153DR | 2021-08-31 06:00 | 2021-09-02 | 2021-09-06 06:00 | COMPLETE
Duri | 5H-0504B | Duri 10864 | 5H-0504B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210092DR | 2021-09-06 06:00 | 2021-09-07 21:30 | 2021-09-11 16:30 | COMPLETE
Duri | 5K-19B | Duri 10867 | 5K-19B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210090DR | 2021-09-11 16:30 | 2021-09-13 03:00 | 2021-09-17 11:30 | COMPLETE
Duri | 5J-88C | Duri 10868 | 5J-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210091DR | 2021-09-17 11:30 | 2021-09-18 12:00 | 2021-09-23 10:00 | COMPLETE
Duri | 5G-0212B | Duri 10869 | 5G-0212B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210089DR | 2021-09-23 10:00 | 2021-09-26 14:00 | 2021-09-30 20:00 | COMPLETE
Duri | 6G-0201B | Duri 10872 | 6G-0201B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210079DR | 2021-09-30 20:00 | 2021-10-02 08:00 | 2021-10-06 07:00 | COMPLETE
Duri | 6G-0404B | Duri 10873 | 6G-0404B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210080DR | 2021-10-06 07:00 | 2021-10-07 08:00 | 2021-10-11 05:00 | COMPLETE
Duri | 6G-0401B | Duri 10876 | 6G-0401B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210081DR | 2021-10-11 05:00 | 2021-10-12 05:00 | 2021-10-16 | COMPLETE
Duri | 6G-0401C | Duri 10877 | 6G-0401C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210073DR | 2021-10-16 | 2021-10-17 12:00 | 2021-10-21 20:00 | COMPLETE
Duri | 5H-0507B | Duri 10880 | 5H-0507B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2210088DR | 2021-10-21 20:00 | 2021-10-24 19:00 | 2021-10-29 08:00 | COMPLETE
Duri | 5K-65D | Duri 10881 | 5K-65D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210106DR | 2021-10-29 08:00 | 2021-10-31 | 2021-11-04 19:30 | COMPLETE
Duri | 7Q-25B | Duri 10884 | 7Q-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210107DR | 2021-11-04 19:30 | 2021-11-06 16:00 | 2021-11-12 | COMPLETE
Duri | 4K-27D | Duri 10885 | 4K-27D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210115DR | 2021-11-12 | 2021-11-15 03:30 | 2021-11-20 05:15 | COMPLETE
Duri | 4K-21D | Duri 10886 | 4K-21D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210110DR | 2021-11-20 05:15 | 2021-11-21 23:30 | 2021-11-27 16:00 | COMPLETE
Duri | 7Q-16B | Duri 10889 | 7Q-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210113DR | 2021-11-27 16:00 | 2021-11-29 18:30 | 2021-12-06 03:30 | COMPLETE
Duri | 7Q-13D | Duri 10890 | 7Q-13D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210111DR | 2021-12-06 03:30 | 2021-12-08 03:00 | 2021-12-13 17:30 | COMPLETE
Duri | 6S-62B | Duri 10893 | 6S-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210116DR | 2021-12-13 17:30 | 2021-12-16 19:30 | 2021-12-21 16:30 | COMPLETE
Duri | 6T-34D | Duri 10894 | 6T-34D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210117DR | 2021-12-21 16:30 | 2021-12-24 06:00 | 2021-12-29 | COMPLETE
Duri | 3N-29F | Duri 10897 | 3N-29F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/3210120DR | 2021-12-29 | 2022-01-02 02:00 | 2022-01-11 20:00 | COMPLETE
Duri | 3S-78D | Duri 10898 | 3S-78D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220088DR | 2022-01-11 20:00 | 2022-01-14 17:00 | 2022-01-19 13:00 | COMPLETE
Duri | 4K-32C | Duri 10901 | 4K-32C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220090DR | 2022-01-19 13:00 | 2022-01-23 23:00 | 2022-01-29 10:00 | COMPLETE
Duri | 5K-25C | Duri 10902 | 5K-25C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220092DR | 2022-01-29 10:00 | 2022-01-31 16:00 | 2022-02-05 16:30 | COMPLETE
Duri | 5K-26D | Duri 10906 | 5K-26D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220094DR | 2022-02-05 16:30 | 2022-02-08 18:00 | 2022-02-18 | COMPLETE
Duri | 5H-0604B | Duri 10909 | 5H-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220099DR | 2022-02-18 | 2022-02-20 10:00 | 2022-02-24 12:00 | COMPLETE
Duri | 5H-0405B | Duri 10910 | 5H-0405B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220101DR | 2022-02-24 12:00 | 2022-02-26 13:30 | 2022-03-02 19:30 | COMPLETE
Duri | 5G-0613B | Duri 10917 | 5G-0613B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220111DR | 2022-03-20 20:00 | 2022-03-20 20:00 | 2022-03-26 02:00 | COMPLETE
Duri | 5G-0604B | Duri 10922 | 5G-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220106DR | 2022-03-26 02:00 | 2022-03-28 03:00 | 2022-04-01 20:30 | COMPLETE
Duri | 5F-0410C | Duri 10920 | 5F-0410C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220109DR | 2022-04-01 20:30 | 2022-04-04 | 2022-04-08 11:00 | COMPLETE
Duri | 5J-86B | Duri 10926 | 5J-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220120DR | 2022-04-08 11:00 | 2022-04-12 18:00 | 2022-04-18 10:00 | COMPLETE
Duri | 6K-20F | Duri 10936 | 6K-20F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220138DR | 2022-04-18 11:00 | 2022-04-22 09:00 | 2022-04-27 10:00 | COMPLETE
Duri | 5K-24E | Duri 10929 | 5K-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220122DR | 2022-04-27 10:00 | 2022-04-28 20:30 | 2022-05-04 13:00 | COMPLETE
Duri | 6K-11C | Duri 10944 | 6K-11C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220140DR | 2022-05-04 13:00 | 2022-05-09 04:15 | 2022-05-14 05:00 | COMPLETE
Duri | 5J-88D | Duri 10943 | 5J-88D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220133DR | 2022-05-14 05:00 | 2022-05-16 12:30 | 2022-05-21 22:15 | COMPLETE
Duri | 5K-17C | Duri 10934 | 5K-17C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220135DR | 2022-05-21 22:15 | 2022-05-23 07:00 | 2022-05-28 05:00 | COMPLETE
Duri | 6J-82C | Duri 10948 | 6J-82C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220143DR | 2022-05-28 05:00 | 2022-05-29 14:00 | 2022-06-05 03:00 | COMPLETE
Duri | 5K-37B | Duri 10931 | 5K-37B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220125DR | 2022-06-05 03:00 | 2022-06-06 13:30 | 2022-06-11 06:00 | COMPLETE
Duri | 6K-20E | Duri 10946 | 6K-20E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220145DR | 2022-06-11 06:00 | 2022-06-13 15:30 | 2022-06-18 09:00 | COMPLETE
Duri | 5J-75C | Duri 10953 | 5J-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220128DR | 2022-06-18 09:00 | 2022-06-19 22:00 | 2022-06-24 21:00 | COMPLETE
Duri | 4Q-12C | Duri 10957 | 4Q-12C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220155DR | 2022-06-24 21:00 | 2022-06-28 03:00 | 2022-07-01 23:00 | COMPLETE
Duri | 5J-77C | Duri 10955 | 5J-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220130DR | 2022-07-01 23:00 | 2022-07-04 18:00 | 2022-07-09 10:30 | COMPLETE
Duri | 6M-72D | Duri 10959 | 6M-72D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220153DR | 2022-07-09 10:30 | 2022-07-12 | 2022-07-15 20:00 | COMPLETE
Duri | 7M-27B | Duri 10961 | 7M-27B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220149DR | 2022-07-15 20:00 | 2022-07-17 22:00 | 2022-07-23 05:00 | COMPLETE
Duri | 6M-16B | Duri 10963 | 6M-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220151DR | 2022-07-23 05:00 | 2022-07-24 19:00 | 2022-07-28 14:30 | COMPLETE
Duri | 6G-0603C | Duri 10966 | 6G-0603C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220147DR | 2022-07-28 14:30 | 2022-07-31 06:00 | 2022-08-04 06:00 | COMPLETE
Duri | 4H-1011C | Duri 10974 | 4H-1011C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | GRK2/402/2220131DR | 2022-08-04 06:00 | 2022-08-06 06:00 | 2022-08-10 11:00 | COMPLETE
Duri | 4H-1111C | Duri 10970 | 4H-1111C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220563DR | 2022-08-10 11:00 | 2022-08-12 18:00 | 2022-08-16 21:00 | COMPLETE
Duri | 5H-1001B | Duri 10973 | 5H-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220477DR | 2022-08-16 21:00 | 2022-08-19 02:30 | 2022-08-23 22:00 | COMPLETE
Duri | 6F-0702C | Duri 10976 | 6F-0702C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220564DR | 2022-08-23 22:00 | 2022-08-26 01:00 | 2022-08-30 18:00 | COMPLETE
Duri | 4H-1111B | Duri 10972 | 4H-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220565DR | 2022-08-30 18:00 | 2022-09-06 09:00 | 2022-09-06 09:00 | COMPLETE
Duri | 5H-1005B | Duri 10977 | 5H-1005B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220479DR | 2022-09-06 09:00 | 2022-09-09 04:30 | 2022-09-13 16:00 | COMPLETE
Duri | 5H-0903B | Duri 10979 | 5H-0903B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220480DR | 2022-09-13 16:00 | 2022-09-16 05:00 | 2022-09-21 09:00 | COMPLETE
Duri | 5F-0907B | Duri 10981 | 5F-0907B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220465DR | 2022-09-21 09:00 | 2022-09-24 02:30 | 2022-09-29 12:15 | COMPLETE
Duri | 5F-0910C | Duri 10984 | 5F-0910C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220466DR | 2022-09-29 12:15 | 2022-10-01 06:00 | 2022-10-05 20:00 | COMPLETE
Duri | 5H-0307B | Duri 10986 | 5H-0307B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220484DR | 2022-10-05 20:00 | 2022-10-07 22:00 | 2022-10-12 23:00 | COMPLETE
Duri | 5H-0303B | Duri 10989 | 5H-0303B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220483DR | 2022-10-12 23:00 | 2022-10-15 16:00 | 2022-10-20 | COMPLETE
Duri | 5H-0310B | Duri 10990 | 5H-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220485DR | 2022-10-20 | 2022-10-22 02:00 | 2022-10-26 12:30 | COMPLETE
Duri | 5F-1110B | Duri 10992 | 5F-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220472DR | 2022-10-26 12:30 | 2022-10-28 21:00 | 2022-11-02 13:30 | COMPLETE
Duri | 6F-1002B | Duri 10988 | 6F-1002B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220469DR | 2022-11-02 01:30 | 2022-11-05 02:00 | 2022-11-09 19:00 | COMPLETE
Duri | 5G-1110B | Duri 10997 | 5G-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220488DR | 2022-11-09 19:00 | 2022-11-15 22:00 | 2022-11-20 13:00 | COMPLETE
Duri | 5G-1113C | Duri 11001 | 5G-1113C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220489DR | 2022-11-20 13:00 | 2022-11-22 19:30 | 2022-11-27 20:00 | COMPLETE
Duri | 6G-1103B | Duri 11003 | 6G-1103B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220490DR | 2022-11-27 20:00 | 2022-11-30 18:00 | 2022-12-05 17:00 | COMPLETE
Duri | 5G-1012B | Duri 11006 | 5G-1012B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220491DR | 2022-12-05 17:00 | 2022-12-07 17:00 | 2022-12-12 06:30 | COMPLETE
Duri | 5G-0913B | Duri 11002 | 5G-0913B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220566DR | 2022-12-12 06:30 | 2022-12-19 18:00 | 2022-12-26 | COMPLETE
Duri | 5G-0804B | Duri 11007 | 5G-0804B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220567DR | 2022-12-26 | 2023-01-01 | 2023-01-06 | COMPLETE
Duri | 6G-0604B | Duri 11010 | 6G-0604B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220568DR | 2023-01-06 | 2023-01-08 | 2023-01-12 21:00 | COMPLETE
Duri | 5F-0512C | Duri 11013 | 5F-0512C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220569DR | 2023-01-12 21:00 | 2023-01-14 23:00 | 2023-01-20 18:30 | COMPLETE
Duri | 6F-0602C | Duri 11018 | 6F-0602C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220570DR | 2023-01-20 18:30 | 2023-01-22 10:00 | 2023-01-27 19:15 | COMPLETE
Duri | 5H-0202B | Duri 11020 | 5H-0202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220571DR | 2023-01-27 19:15 | 2023-01-30 02:30 | 2023-02-03 11:00 | COMPLETE
Duri | 5H-0401B | Duri 11021 | 5H-0401B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220572DR | 2023-02-03 11:00 | 2023-02-05 | 2023-02-09 11:00 | COMPLETE
Duri | 5I-0101B | Duri 11023 | 5I-0101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | DRI2/402/3220824DR | 2023-02-09 11:00 | 2023-02-19 | 2023-02-25 | COMPLETE
Duri | 6G-0803B | Duri 11024 | 6G-0803B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220852DR | 2023-02-25 | 2023-02-27 06:00 | 2023-03-04 05:00 | COMPLETE
Duri | 5G-0713C | Duri 11026 | 5G-0713C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220853DR | 2023-03-04 05:00 | 2023-03-23 | 2023-03-28 02:30 | COMPLETE
Duri | 4H-1112B | Duri 11043 | 4H-1112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220861DR | 2023-03-28 02:30 | 2023-03-30 | 2023-04-04 04:00 | COMPLETE
Duri | 5G-0811B | Duri 11044 | 5G-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220865DR | 2023-04-04 04:00 | 2023-04-06 | 2023-04-10 21:00 | COMPLETE
Duri | 6G-0701C | Duri 11046 | 6G-0701C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230094DR | 2023-04-10 21:00 | 2023-04-12 16:00 | 2023-04-18 03:00 | COMPLETE
Duri | 5G-0908B | Duri 11048 | 5G-0908B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220867DR | 2023-04-18 03:00 | 2023-04-20 02:00 | 2023-04-26 18:00 | COMPLETE
Duri | 6G-0902B | Duri 11061 | 6G-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220855DR | 2023-04-26 18:00 | 2023-04-28 21:00 | 2023-05-04 02:30 | COMPLETE
Duri | 5H-0802B | Duri 11062 | 5H-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230093DR | 2023-05-03 03:00 | 2023-05-05 10:00 | 2023-05-10 12:00 | COMPLETE
Duri | 6F-1101C | Duri 11063 | 6F-1101C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230060DR | 2023-05-10 12:00 | 2023-05-13 05:00 | 2023-05-17 06:00 | COMPLETE
Duri | 6F-1101D | Duri 11064 | 6F-1101D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230114DR | 2023-05-17 06:00 | 2023-05-18 15:00 | 2023-05-23 09:00 | COMPLETE
Duri | 5F-0107B | Duri 11068 | 5F-0107B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230119DR | 2023-05-23 09:00 | 2023-05-25 09:00 | 2023-05-30 09:00 | COMPLETE
Duri | 5F-0912B | Duri 11070 | 5F-0912B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230099DR | 2023-05-30 09:00 | 2023-05-31 23:30 | 2023-06-06 23:00 | COMPLETE
Duri | 6F-0801C | Duri 11069 | 6F-0801C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230098DR | 2023-06-06 23:00 | 2023-06-08 14:30 | 2023-06-14 04:00 | COMPLETE
Duri | 6F-0701C | Duri 11071 | 6F-0701C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230100DR | 2023-06-14 04:00 | 2023-06-16 02:00 | 2023-06-22 06:00 | COMPLETE
Duri | 5F-0411B | Duri 11079 | 5F-0411B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230086DR | 2023-06-22 06:00 | 2023-06-24 06:00 | 2023-06-30 02:30 | COMPLETE
Duri | 5F-1210B | Duri 11080 | 5F-1210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230075DR | 2023-06-30 02:30 | 2023-07-02 08:30 | 2023-07-07 20:00 | COMPLETE
Duri | 5F-1210C | Duri 11083 | 5F-1210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230079DR | 2023-07-07 20:00 | 2023-07-09 00:30 | 2023-07-15 15:00 | COMPLETE
Duri | 5F-0909B | Duri 11084 | 5F-0909B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230074DR | 2023-07-15 15:00 | 2023-07-17 03:00 | 2023-07-24 | COMPLETE
Duri | 5H-0209B | Duri 11095 | 5H-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220858DR | 2023-07-24 | 2023-07-25 16:00 | 2023-07-30 14:00 | COMPLETE
Duri | 5G-0512C | Duri 11096 | 5G-0512C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | ADH2/402/2220874DR | 2023-07-30 14:00 | 2023-08-01 06:00 | 2023-08-06 06:00 | COMPLETE
Duri | 5K-36B | Duri 11085 | 5K-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230125DR | 2023-08-06 06:00 | 2023-08-07 20:15 | 2023-08-16 12:30 | COMPLETE
Duri | 4K-62E | Duri 11097 | 4K-62E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230122DR | 2023-08-16 12:30 | 2023-08-18 09:00 | 2023-08-25 | COMPLETE
Duri | 5F-0811B | Duri 11105 | 5F-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230078DR | 2023-08-25 | 2023-08-27 12:00 | 2023-09-02 | COMPLETE
Duri | 5F-0811C | Duri 11106 | 5F-0811C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230072DR | 2023-09-02 | 2023-09-03 09:30 | 2023-09-09 05:00 | COMPLETE
Duri | 5F-0610B | Duri 11112 | 5F-0610B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230080DR | 2023-09-09 05:00 | 2023-09-10 14:00 | 2023-09-16 02:00 | COMPLETE
Duri | 5F-0508C | Duri 11120 | 5F-0508C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230087DR | 2023-09-16 02:00 | 2023-09-17 06:00 | 2023-09-22 08:00 | COMPLETE
Duri | 5F-0410D | Duri 11114 | 5F-0410D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230088DR | 2023-09-22 08:00 | 2023-09-23 18:00 | 2023-09-29 03:00 | COMPLETE
Duri | 5F-1108C | Duri 11123 | 5F-1108C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230089DR | 2023-09-29 03:00 | 2023-09-30 12:00 | 2023-10-05 18:00 | COMPLETE
Duri | 5F-0206B | Duri 11125 | 5F-0206B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230090DR | 2023-10-05 18:00 | 2023-10-07 06:00 | 2023-10-12 12:00 | COMPLETE
Duri | 5F-0908B | Duri 11130 | 5F-0908B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230104DR | 2023-10-12 12:00 | 2023-10-14 | 2023-10-20 10:00 | COMPLETE
Duri | 5E-1206B | Duri 11113 | 5E-1206B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230129DR | 2023-10-20 10:00 | 2023-10-22 20:00 | 2023-10-29 | COMPLETE
Duri | 5E-0910C | Duri 11141 | 5E-0910C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230101DR | 2023-10-29 | 2023-10-30 16:00 | 2023-11-05 | COMPLETE
Duri | 3F-0104B | Duri 11142 | 3F-0104B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230066DR | 2023-11-05 | 2023-11-07 12:00 | 2023-11-12 20:00 | COMPLETE
Duri | 8L-25A | Duri 11143 | 8L-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230127DR | 2023-11-12 20:00 | 2023-11-16 | 2023-11-20 13:00 | COMPLETE
Duri | 2J-0611A | Duri 11152 | 2J-0611A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220751DR | 2023-11-20 13:00 | 2023-11-22 22:00 | 2023-11-28 16:00 | COMPLETE
Duri | 2J-0712A | Duri 11153 | 2J-0712A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220748DR | 2023-11-28 16:00 | 2023-11-29 19:00 | 2023-12-06 | COMPLETE
Duri | 2J-0713A | Duri 11154 | 2J-0713A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220750DR | 2023-12-06 | 2023-12-07 10:00 | 2023-12-16 02:00 | COMPLETE
Duri | 5F-0311B | Duri 11161 | 5F-0311B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230084DR | 2023-12-16 02:00 | 2023-12-22 01:30 | 2023-12-28 19:30 | COMPLETE
Duri | 9M-126A | Duri 11151 | 9M-126A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230128DR | 2023-12-28 19:30 | 2024-01-28 22:00 | 2024-02-02 13:00 | COMPLETE
Duri | 5F-0211B | Duri 11162 | 5F-0211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2230085DR | 2023-12-30 13:30 | 2024-01-03 07:00 | 2024-01-09 03:00 | COMPLETE
Duri | 5H-0902B | Duri 11177 | 5H-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240053DR | 2024-01-12 13:00 | 2024-01-19 22:00 | 2024-01-25 12:00 | COMPLETE
Duri | 5F-0109C | Duri 11170 | 5F-0109C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240054DR | 2024-02-02 13:00 | 2024-02-07 10:30 | 2024-02-13 | COMPLETE
Duri | 6G-0104B | Duri 11180 | 6G-0104B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240037DR | 2024-02-13 | 2024-02-15 02:30 | 2024-02-21 05:00 | COMPLETE
Duri | 2J-0313A | Duri 11184 | 2J-0313A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220771DR | 2024-02-21 05:00 | 2024-02-24 16:00 | 2024-02-29 19:00 | COMPLETE
Duri | 2J-0710A | Duri 11186 | 2J-0710A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220742DR | 2024-02-29 19:00 | 2024-03-02 21:00 | 2024-03-09 09:00 | COMPLETE
Duri | 3J-0102B | Duri 11197 | 3J-0102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHO2/402/2220793DR | 2024-03-09 09:00 | 2024-03-12 17:00 | 2024-03-18 23:00 | COMPLETE
Duri | 6G-0704B | Duri 11198 | 6G-0704B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240057DR | 2024-03-18 23:00 | 2024-03-21 11:00 | 2024-03-27 15:00 | COMPLETE
Duri | 5G-0813B | Duri 11199 | 5G-0813B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240058DR | 2024-03-27 15:00 | 2024-03-29 09:00 | 2024-04-03 23:00 | COMPLETE
Duri | 5G-0911B | Duri 11201 | 5G-0911B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240059DR | 2024-04-03 03:00 | 2024-04-05 23:00 | 2024-04-16 22:00 | COMPLETE
Duri | 4V-46B | Duri 11208 | 4V-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240060DR | 2024-04-16 22:00 | 2024-04-19 11:00 | 2024-04-26 06:00 | COMPLETE
Duri | 4K-11D | Duri 11211 | 4K-11D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240064DR | 2024-04-26 06:00 | 2024-04-28 05:00 | 2024-05-07 12:00 | COMPLETE
Duri | 4K-22E | Duri 11214 | 4K-22E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240062DR | 2024-05-07 12:00 | 2024-05-09 | 2024-05-17 12:00 | COMPLETE
Duri | 6F-1003B | Duri 11222 | 6F-1003B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240079DR | 2024-05-17 12:00 | 2024-05-19 16:00 | 2024-05-25 07:30 | COMPLETE
Duri | 5F-0706B | Duri 11224 | 5F-0706B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240080DR | 2024-05-25 07:30 | 2024-05-26 19:00 | 2024-06-01 14:00 | COMPLETE
Duri | 5G-0808B | Duri 11227 | 5G-0808B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240077DR | 2024-06-01 14:00 | 2024-06-03 02:00 | 2024-06-08 10:00 | COMPLETE
Duri | 5F-0306B | Duri 11230 | 5F-0306B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240056DR | 2024-06-08 10:00 | 2024-06-11 10:30 | 2024-06-18 | COMPLETE
Duri | 5F-0406B | Duri 11233 | 5F-0406B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240842DR | 2024-06-18 | 2024-06-19 03:00 | 2024-06-25 22:00 | COMPLETE
Duri | 5E-1207B | Duri 11239 | 5E-1207B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240837DR | 2024-06-25 22:00 | 2024-06-27 04:00 | 2024-07-02 16:00 | COMPLETE
Duri | 5G-0311B | Duri 11242 | 5G-0311B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240886DR | 2024-07-02 16:00 | 2024-07-04 03:00 | 2024-07-09 11:00 | COMPLETE
Duri | 5G-0912C | Duri 11250 | 5G-0912C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-019 | RHT2/402/2240884DR | 2024-07-09 11:00 | 2024-07-10 22:00 |  | IN_PROGRESS
Duri | P_7M37C | Duri 10850 | 7M-37C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210093DR | 2021-08-02 08:00 | 2021-08-06 14:15 | 2021-08-11 21:00 | COMPLETE
Duri | P_8M75B | Duri 10851 | 8M-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210029DR | 2021-08-11 21:00 | 2021-08-15 08:00 | 2021-08-20 | COMPLETE
Duri | P_8M20C | Duri 10858 | 8M-20C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3210154DR | 2021-08-20 | 2021-08-22 08:00 | 2021-08-31 12:00 | COMPLETE
Bekasap | P02_BK21 | Bekasap 00197 | O-O-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210002DR | 2021-08-31 12:00 | 2021-09-07 06:00 | 2021-09-18 07:00 | COMPLETE
Bekasap | BKS-P2 | Bekasap 00198 | O-E1-51C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210014DR | 2021-09-18 07:00 | 2021-09-22 16:00 | 2021-10-02 06:30 | COMPLETE
Pematang | Pematang P02 | Pematang 00109 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210126DR | 2021-10-02 06:30 | 2021-10-05 21:00 | 2021-10-21 19:00 | COMPLETE
Bekasap | BKS-P3 | Bekasap 00200 | O-E1-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210015DR | 2021-10-21 19:00 | 2021-10-27 | 2021-11-05 08:00 | COMPLETE
Bekasap | BKS-P7 | Bekasap 00201 | O-E1-43C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210019DR | 2021-11-05 08:00 | 2021-11-07 15:00 | 2021-11-15 14:00 | COMPLETE
Bekasap | BKS-P10 | Bekasap 00203 | S1-O-16J | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210004DR | 2021-11-15 14:00 | 2021-11-19 04:00 | 2021-11-26 11:00 | COMPLETE
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210018DR | 2021-11-26 11:00 | 2021-11-29 05:00 | 2021-12-07 19:00 | RELEASE
Bekasap | BKS-P12 | Bekasap 00207 | O-O-66B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210006DR | 2021-12-07 19:00 | 2021-12-11 16:30 | 2021-12-21 05:00 | COMPLETE
Bekasap | BKS-P16 | Bekasap 00208 | O-O-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210017DR | 2021-12-21 05:00 | 2021-12-27 09:00 | 2022-01-04 07:30 | RELEASE
Bekasap | BKS-P18 | Bekasap 00209 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2210012DR | 2022-01-04 07:30 | 2022-01-08 18:00 | 2022-01-19 18:00 | COMPLETE
Bekasap | BKS-P5 | Bekasap 00211 | S1-O-16G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220082DR | 2022-01-19 18:00 | 2022-01-23 19:00 | 2022-02-01 18:00 | COMPLETE
Duri | 4H-0811B | Duri 10908 | 4H-0811B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220095DR | 2022-02-01 18:00 | 2022-02-14 | 2022-02-20 09:30 | COMPLETE
Duri | 5J-85C | Duri 10905 | 5J-85C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220096DR | 2022-02-20 09:30 | 2022-02-23 17:00 | 2022-03-01 03:00 | COMPLETE
Bekasap | BKS-P9 | Bekasap 00214 | O-E1-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220083DR | 2022-03-01 03:00 | 2022-03-07 21:00 | 2022-03-18 | COMPLETE
Bekasap | BKS-P13 | Bekasap 00216 | S1-O-36C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220086DR | 2022-03-18 | 2022-03-23 11:30 | 2022-04-04 | COMPLETE
Bekasap | BKS-X10 | Bekasap 00218 | O-E1-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220286DR | 2022-04-04 | 2022-04-07 22:00 | 2022-04-20 | COMPLETE
Bekasap | BKS-X11 | Bekasap 00219 | O-E1-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220284DR | 2022-04-26 | 2022-04-26 | 2022-05-05 20:00 | COMPLETE
Menggala No | MNO-P05 | Menggala No 00048 | N3-W1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220196DR | 2022-05-05 20:00 | 2022-05-22 15:00 | 2022-06-05 09:30 | COMPLETE
Menggala No | MNO-P13 | Menggala No 00050 | N3-W1-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220236DR | 2022-06-05 09:30 | 2022-06-09 | 2022-06-21 05:00 | COMPLETE
Menggala No | MNO-P16 | Menggala No 00052 | N3-W1-36E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/2220239DR | 2022-06-21 05:00 | 2022-06-25 18:00 | 2022-07-08 | COMPLETE
Menggala No | MNO-P14 | Menggala No 00054 | N3-W1-36D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220208DR | 2022-07-08 | 2022-07-10 20:00 | 2022-07-22 22:00 | COMPLETE
Menggala No | MNO-P20 | Menggala No 00056 | N4-W1-83A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | GRK2/402/3220212DR | 2022-07-22 22:00 | 2022-07-27 18:00 | 2022-08-09 19:00 | COMPLETE
Menggala No | MNO-P21 | Menggala No 00058 | N4-W1-83B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220316DR | 2022-08-09 19:00 | 2022-08-14 11:00 | 2022-08-29 11:00 | COMPLETE
Menggala No | MNO-P19 | Menggala No 00059 | N4-W1-83C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220518DR | 2022-08-29 11:00 | 2022-09-06 02:00 | 2022-09-19 16:00 | COMPLETE
Balam So | LQR-TE049_BLSO_57 | Balam So 00494 | S1-O-74A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220528DR | 2022-09-19 16:00 | 2022-10-04 14:00 | 2022-10-13 06:00 | COMPLETE
Balam So | LQR-TE180_BLSO_56 | Balam So 00498 | S1-O-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220536DR | 2022-10-13 06:00 | 2022-10-20 04:00 | 2022-10-30 18:00 | COMPLETE
Balam So | BLSO-P44 | Balam So 00501 | N1-W1-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220342DR | 2022-10-30 18:00 | 2022-11-07 03:00 | 2022-11-15 20:00 | COMPLETE
Balam So | LQR-TE016_BLSO_35 | Balam So 00504 | N1-W1-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220340DR | 2022-11-15 20:00 | 2022-11-24 | 2022-12-01 21:00 | COMPLETE
Minas | P_4C-24E | Minas 02032 | 4C-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220553DR | 2022-12-01 21:00 | 2023-01-06 06:00 | 2023-01-19 08:00 | COMPLETE
Minas | P_4C-25N1 | Minas 02036 | 4C-25N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220542DR | 2023-01-19 08:00 | 2023-01-28 17:45 | 2023-02-26 18:00 | COMPLETE
Minas | P_4C-25N2 | Minas 02047 | 4C-25N2 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220430DR | 2023-02-26 18:00 | 2023-03-23 20:00 | 2023-04-04 12:00 | COMPLETE
Minas | P_5C-95N | Minas 02054 | 5C-95N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220651DR | 2023-04-04 12:00 | 2023-04-11 13:30 | 2023-04-21 10:00 | COMPLETE
Minas | P_4A-22 | Minas 02059 | 4A-22 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230211DR | 2023-04-21 10:00 | 2023-04-29 | 2023-05-10 15:00 | COMPLETE
Minas | P_4A-23E | Minas 02062 | 4A-23E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220655DR | 2023-05-10 15:00 | 2023-05-14 05:00 | 2023-05-23 18:00 | COMPLETE
Minas | P_7D-12N | Minas 02069 | 7D-12N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230244DR | 2023-05-23 18:00 | 2023-05-30 16:00 | 2023-06-09 08:30 | COMPLETE
Minas | P_3D-33E | Minas 02072 | 3D-33E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220638DR | 2023-06-09 08:30 | 2023-06-19 18:00 | 2023-06-26 20:00 | COMPLETE
Minas | P_5B-87E | Minas 02076 | 5B-87E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230227DR | 2023-06-26 20:00 | 2023-07-06 16:00 | 2023-07-15 07:00 | COMPLETE
Minas | P_3B-34 | Minas 02082 | 3B-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220433DR | 2023-07-15 07:00 | 2023-07-20 21:00 | 2023-07-27 05:00 | COMPLETE
Minas | P_6D-84E | Minas 02084 | 6D-84E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230238DR | 2023-07-27 05:00 | 2023-08-02 20:00 | 2023-08-10 17:00 | COMPLETE
Minas | P_6D-96N | Minas 02088 | 6D-96N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230234DR | 2023-08-10 17:00 | 2023-08-13 10:30 | 2023-08-23 06:00 | COMPLETE
Minas | P_4A-29 | Minas 02090 | 4A-29 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230249DR | 2023-08-22 06:00 | 2023-08-26 12:00 | 2023-09-13 22:00 | COMPLETE
Minas | MNS-P11 | Minas 02095 | 8D-31E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230217DR | 2023-09-13 22:00 | 2023-09-20 12:00 | 2023-10-01 | COMPLETE
Minas | Minas P03 | Minas 02097 | 8D-43N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220458DR | 2023-10-01 | 2023-10-04 10:00 | 2023-10-11 10:00 | RELEASE
Minas | P_MINA24_8D-42N | Minas 02100 | 8D-42N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230503DR | 2023-10-11 10:00 | 2023-10-13 12:00 | 2023-10-21 18:30 | COMPLETE
Minas | P_MINA24_6E-58N | Minas 02102 | 6E-58N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230497DR | 2023-10-21 18:30 | 2023-10-26 03:00 | 2023-11-01 21:00 | RELEASE
Minas | P_MINA24_4A-43E | Minas 02105 | 4A-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230492DR | 2023-11-01 21:00 | 2023-11-08 13:00 | 2023-11-17 04:00 | COMPLETE
Minas | P_MINA24_8D-12N1 | Minas 02108 | 8D-12N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230501DR | 2023-11-17 04:00 | 2023-11-23 10:00 | 2023-12-02 16:00 | COMPLETE
Minas | P_MINA24_6E-57 | Minas 02111 | 6E-57 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230496DR | 2023-12-02 16:00 | 2023-12-17 16:00 | 2023-12-28 12:00 | COMPLETE
Minas | P_MINA24_8D-23N1 | Minas 02115 | 8D-23N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230502DR | 2023-12-28 12:00 | 2024-06-29 11:00 | 2024-01-29 | COMPLETE
Minas | P_3A-75N1 | Minas 02117 | 3A-75N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSO2/402/3220634DR | 2024-01-29 | 2024-02-03 23:00 | 2024-02-14 | COMPLETE
Minas | P_MINA24_6F-83 | Minas 02119 | 6F-83 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230508DR | 2024-02-14 | 2024-02-21 19:30 | 2024-03-05 12:45 | COMPLETE
Minas | P_MINA24_7E-82N | Minas 02121 | 7E-82N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230520DR | 2024-03-05 12:45 | 2024-03-10 22:00 | 2024-03-20 18:00 | COMPLETE
Minas | P_MINA24_8E-63N | Minas 02122 | 8E-63N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230505DR | 2024-03-20 18:00 | 2024-03-27 13:30 | 2024-04-08 09:30 | COMPLETE
Minas | P_MINA24_8E-55N | Minas 02123 | 8E-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230504DR | 2024-04-08 09:30 | 2024-04-11 14:30 | 2024-04-22 22:00 | COMPLETE
Minas | P_MINA24_10C-16 | Minas 02127 | 10C-16 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230507DR | 2024-04-22 22:00 | 2024-05-04 16:00 | 2024-05-17 08:30 | COMPLETE
Minas | P_MINA24_7D-95N | Minas 02129 | 7D-95N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230517DR | 2024-05-17 08:30 | 2024-05-29 02:00 | 2024-06-09 11:00 | COMPLETE
Minas | P_MINA24_5C-33 | Minas 02132 | 5C-33 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230521DR | 2024-06-09 11:00 | 2024-06-18 05:00 | 2024-06-28 09:00 | COMPLETE
Minas | P_MINA24_6F-91 | Minas 02134 | 6F-91 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-020 | SSM2/402/3230509DR | 2024-06-28 09:00 | 2024-07-08 12:00 |  | IN_PROGRESS
Hitam | Hitam P04 | Hitam 00011 | O-O-22A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/2210093DR | 2021-08-02 14:00 | 2021-08-06 | 2021-09-01 05:00 | COMPLETE
Hitam | Hitam P04 | Hitam 00011 | O-O-22A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | ACS-021 | GRK2/402/2210093DR | 2021-09-01 05:00 | 2021-09-01 05:00 | 2021-09-03 18:00 | COMPLETE
Kotabatak | KOTA21_P_TE_2A | Kotabatak 00457 | N1-W1-42A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210100DR | 2021-09-03 18:00 | 2021-09-17 14:00 | 2021-10-01 03:00 | COMPLETE
Kotabatak | KOTA21_P_TE_INJ_1 | Kotabatak 00458 | N1-W1-46A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210102DR | 2021-10-01 03:00 | 2021-10-05 19:00 | 2021-10-15 09:00 | COMPLETE
Kotabatak | KOTA21_P_TE_B2 | Kotabatak 00459 | N1-W1-84E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210098DR | 2021-10-15 09:00 | 2021-10-21 10:00 | 2021-11-02 | COMPLETE
Petapahan | PTP-P4 | Petapahan 00152 | N2-W1-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210151DR | 2021-11-02 | 2021-11-10 22:00 | 2021-11-24 16:30 | COMPLETE
Kotabatak | KTB-P2 | Kotabatak 00463 | S1-E1-72 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210104DR | 2021-11-24 16:30 | 2021-12-01 09:00 | 2021-12-18 17:00 | COMPLETE
Kotabatak | KTB-X04 | Kotabatak 00467 | N1-O-73A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/2210131DR | 2021-12-18 17:00 | 2021-12-26 11:30 | 2022-01-05 03:30 | COMPLETE
Kotabatak | KTB-X18 | Kotabatak 00470 | O-O-13 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220165DR | 2022-01-05 03:30 | 2022-01-10 19:00 | 2022-01-20 08:30 | COMPLETE
Kotabatak | KTB-X03 | Kotabatak 00473 | N1-O-32A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3210103DR | 2022-01-20 08:30 | 2022-01-25 08:00 | 2022-02-09 04:00 | COMPLETE
Kotabatak | KTB-X05 | Kotabatak 00476 | O-O-18 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220173DR | 2022-02-09 04:00 | 2022-02-14 13:30 | 2022-02-24 13:00 | COMPLETE
Kotabatak | KTB-X06 | Kotabatak 00479 | S1-O-12A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220170DR | 2022-02-24 13:00 | 2022-03-02 01:00 | 2022-03-12 15:30 | COMPLETE
Kotabatak | KTB-X07 | Kotabatak 00481 | N1-W1-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220176DR | 2022-03-12 15:30 | 2022-03-21 21:00 | 2022-04-01 09:00 | COMPLETE
Petapahan | PETP21_HW_P07_Ext | Petapahan 00156 | N2-W1-34B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220268DR | 2022-04-01 09:00 | 2022-04-12 01:00 | 2022-06-01 13:00 | SUSPENDED
Kotabatak | KTB-X17 | Kotabatak 00485 | O-O-39 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220180DR | 2022-07-04 09:00 | 2022-07-12 22:00 | 2022-07-23 05:00 | COMPLETE
Kotabatak | KTB-X02 | Kotabatak 00489 | N1-E1-73 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | GRK2/402/3220182DR | 2022-07-23 05:00 | 2022-07-26 03:00 | 2022-08-08 04:00 | COMPLETE
Petapahan | PTP-P2R | Petapahan 00158 | N2-W1-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220511DR | 2022-08-08 04:00 | 2022-08-24 16:45 | 2022-09-10 02:00 | COMPLETE
Petapahan | PTP-P6 | Petapahan 00159 | N2-W1-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220524DR | 2022-09-10 02:00 | 2022-09-14 11:00 | 2022-09-30 16:00 | COMPLETE
Petapahan | P_PETP_INF13_S01 | Petapahan 00160 | N1-W1-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220335DR | 2022-09-30 16:00 | 2022-10-07 06:00 | 2022-12-10 21:00 | COMPLETE
Petapahan | PTPBL1-P13 | Petapahan 00161 | O-E1-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220356DR | 2022-12-09 20:00 | 2022-12-24 23:30 | 2023-01-11 20:00 | COMPLETE
Petapahan | PTPBL1-P14 | Petapahan 00163 | O-E1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220381DR | 2023-01-11 20:00 | 2023-01-17 22:00 | 2023-02-03 15:00 | COMPLETE
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220624DR | 2023-02-03 15:00 | 2023-02-11 01:00 | 2023-03-02 | COMPLETE
Kotabatak | KTB-A271 | Kotabatak 00514 | S1-E1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230385DR | 2023-03-02 | 2023-03-08 22:00 | 2023-03-21 12:00 | COMPLETE
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSO2/402/3220544DR | 2023-03-21 12:00 | 2023-04-12 17:00 | 2023-04-23 03:00 | COMPLETE
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230387DR | 2023-04-23 03:00 | 2023-04-29 06:00 | 2023-05-12 | COMPLETE
Kotabatak | KTB-A128 | Kotabatak 00524 | S1-E1-18 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230383DR | 2023-05-12 | 2023-05-17 | 2023-05-27 | COMPLETE
Kotabatak | KTB-X33-INJ | Kotabatak 00530 | O-W2-29 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230382DR | 2023-05-27 | 2023-06-01 09:00 | 2023-06-10 19:00 | COMPLETE
Kotabatak | KB_PL34 | Kotabatak 00531 | O-W1-13 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230392DR | 2023-06-10 19:00 | 2023-06-14 09:00 | 2023-06-30 | COMPLETE
Kotabatak | KTB-X34-INJ | Kotabatak 00532 | O-W1-20 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSE2/402/3230389DR | 2023-06-30 | 2023-07-03 01:00 | 2023-07-14 01:00 | COMPLETE
Kotabatak | KB_PL1 | Kotabatak 00538 | O-W2-19 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230416DR | 2023-07-14 01:00 | 2023-07-17 23:00 | 2023-07-27 03:30 | COMPLETE
Kotabatak | KTB-X24 | Kotabatak 00539 | N1-W2-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230426DR | 2023-07-27 03:30 | 2023-07-30 | 2023-08-09 07:00 | RELEASE
Kotabatak | KB_PL3 | Kotabatak 00540 | O-W2-25 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SKB2/402/3230420DR | 2023-08-09 07:00 | 2023-08-12 09:00 | 2023-08-23 12:00 | COMPLETE
Topaz | P_TOPA23_P10 | Topaz 00012 | O-O-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230680DR | 2023-08-23 12:00 | 2023-08-29 22:00 | 2023-09-11 11:00 | COMPLETE
Libo Se | LISE23_CC16 | Libo Se 00058 | S1-E4-86 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230628DR | 2023-09-11 11:00 | 2023-09-23 13:00 | 2023-10-20 07:00 | COMPLETE
Libo Se | LISE23_SC03 | Libo Se 00059 | S2-W3-67A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230657DR | 2023-10-20 07:00 | 2023-10-25 19:00 | 2023-11-11 23:00 | COMPLETE
Libo Se | LISE23_SO01 | Libo Se 00060 | S3-E5-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230659DR | 2023-11-11 23:00 | 2023-11-17 04:30 | 2023-12-06 05:00 | COMPLETE
Libo Se | LISE23_CC15 | Libo Se 00061 | S2-E5-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230627DR | 2023-12-06 05:00 | 2023-12-28 | 2024-01-16 | COMPLETE
Libo Se | LISE23_CC09 | Libo Se 00062 | S2-E4-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230621DR | 2024-01-16 | 2024-02-01 09:00 | 2024-02-18 12:00 | COMPLETE
Libo Se | LISE23_CC08 | Libo Se 00063 | S2-E4-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | SSV2/402/3230620DR | 2024-02-18 12:00 | 2024-02-21 19:00 | 2024-03-07 07:00 | COMPLETE
Petani | P_PETA24_31 | Petani 00202 | O-O-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-021 | PTO2/402/3230894DR | 2024-03-07 07:00 | 2024-03-20 02:00 | 2024-04-06 13:30 | COMPLETE
Benar | BNR-X02 | Benar 00056 | N1-W1-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | GRK2/402/2220240DR | 2022-07-21 11:00 | 2022-07-21 11:00 | 2022-08-03 08:00 | COMPLETE
Benar | BNR-X19 | Benar 00057 | O-E1-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | GRK2/402/2220087DR | 2022-08-03 08:00 | 2022-08-08 17:00 | 2022-08-18 05:00 | COMPLETE
Benar | BNR-X20 | Benar 00058 | S1-O-15A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220521DR | 2022-08-18 05:00 | 2022-08-28 20:00 | 2022-09-15 05:00 | COMPLETE
Benar | BNR-X04 | Benar 00059 | N1-E1-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220533DR | 2022-09-15 05:00 | 2022-09-25 03:00 | 2022-10-06 | COMPLETE
Benar | BNR-X05 | Benar 00060 | N2-0-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220355DR | 2022-10-06 | 2022-10-15 | 2022-10-24 03:30 | RELEASE
Benar | BNR-X15 | Benar 00061 | N1-O-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220379DR | 2022-10-24 03:30 | 2022-10-31 | 2022-11-12 21:30 | COMPLETE
Benar | P_BENA22-P09 | Benar 00062 | N2-E1-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220422DR | 2022-11-12 21:30 | 2022-11-22 03:30 | 2022-12-06 06:00 | COMPLETE
Benar | P_BENA22-P06 | Benar 00063 | N1-O-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220441DR | 2022-12-06 06:00 | 2022-12-14 14:00 | 2022-12-24 05:00 | COMPLETE
Benar | BNR-X23 | Benar 00064 | O-O-58A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220397DR | 2022-12-24 05:00 | 2022-12-31 20:00 | 2023-01-10 18:30 | COMPLETE
Benar | BNR-X16 | Benar 00065 | O-E1-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220615DR | 2023-01-10 18:30 | 2023-01-15 16:30 | 2023-01-28 22:30 | COMPLETE
Benar | P_BENA23_P04 | Benar 00066 | N1-O-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SBN2/402/3220849DR | 2023-01-28 22:30 | 2023-02-03 14:00 | 2023-02-27 01:00 | COMPLETE
Menggala No | MNO-P12 | Menggala No 00060 | N3-W1-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230204DR | 2023-02-27 01:00 | 2023-03-14 07:00 | 2023-04-12 01:30 | COMPLETE
Menggala No | MNO-P23 | Menggala No 00061 | N3-W1-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230205DR | 2023-04-12 01:30 | 2023-04-23 12:00 | 2023-05-08 | COMPLETE
Menggala No | MNO-P25 | Menggala No 00062 | N4-W1-83D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230208DR | 2023-05-08 | 2023-05-18 20:00 | 2023-05-31 15:00 | COMPLETE
Menggala No | MNO-P22 | Menggala No 00063 | N4-W1-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230206DR | 2023-05-31 15:00 | 2023-06-07 | 2023-06-23 07:00 | COMPLETE
Menggala No | MNO-P24 | Menggala No 00064 | N4-W2-25 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230207DR | 2023-06-23 07:00 | 2023-07-01 02:30 | 2023-07-16 21:00 | COMPLETE
Menggala No | MNO-P26 | Menggala No 00065 | N4-W2-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230209DR | 2023-07-16 21:00 | 2023-07-31 22:30 | 2023-08-14 12:00 | RELEASE
Balam So | BLSO23-LQR-TE033 | Balam So 00546 | N1-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220585DR | 2023-08-14 12:00 | 2023-08-22 22:00 | 2023-08-30 | COMPLETE
Balam So | BLSO23-LQR-TE050 | Balam So 00549 | N1-W1-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230336DR | 2023-08-30 | 2023-09-05 18:00 | 2023-09-11 10:00 | RELEASE
Balam So | BLSO23-LQR-TE069 | Balam So 00550 | N1-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230358DR | 2023-09-11 10:00 | 2023-09-16 03:00 | 2023-09-23 10:00 | COMPLETE
Balam So | LQR-TE003_BLSO_41 | Balam So 00553 | N1-W1-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220583DR | 2023-09-23 10:00 | 2023-09-28 02:00 | 2023-10-05 13:00 | COMPLETE
Balam So | LQR-TE217_BLSO_43 | Balam So 00555 | N1-W1-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSO2/402/3220584DR | 2023-10-05 13:00 | 2023-10-08 09:00 | 2023-10-15 15:00 | COMPLETE
Kulin | KLN23-P01 | Kulin 00093 | S2-E1-32 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | KLN2/402/3230009DR | 2023-10-15 15:00 | 2023-10-25 12:00 | 2023-11-03 21:00 | COMPLETE
Kulin | KLN23-P02 | Kulin 00094 | S2-0-38 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | KLN2/402/3230010DR | 2023-11-03 21:00 | 2023-11-09 | 2023-11-21 05:00 | COMPLETE
Bekasap | BKS23-P01 | Bekasap 00232 | S1-E2-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SAB2/402/3230478DR | 2023-11-21 05:00 | 2023-11-30 19:30 | 2023-12-21 10:30 | COMPLETE
Pematang | P_PEMA24_13 | Pematang 00128 | O-O-42B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230162DR | 2023-12-21 10:30 | 2023-12-29 12:00 | 2024-01-18 | COMPLETE
Pematang | P_PEMA24_INJ3 | Pematang 00130 | O-O-23B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230170DR | 2024-01-18 | 2024-01-28 12:00 | 2024-02-16 | COMPLETE
Pematang | P_PEMA24_INJ4 | Pematang 00132 | O-W1-36A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230171DR | 2024-02-16 | 2024-02-23 | 2024-03-18 07:00 | COMPLETE
Pematang | P_PEMA24_INJ2 | Pematang 00134 | O-O-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSA2/402/3230169DR | 2024-03-18 07:00 | 2024-03-25 12:00 | 2024-04-18 | COMPLETE
Pungut | PUNG23_D02B | Pungut 00058 | S1-0-48D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230200DR | 2024-04-18 | 2024-04-27 03:00 | 2024-05-10 09:00 | COMPLETE
Pungut | PUNG23_D02C | Pungut 00059 | S1-0-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230203DR | 2024-05-10 09:00 | 2024-05-16 13:00 | 2024-05-29 | COMPLETE
Pungut | PUNG23_D13 | Pungut 00060 | S2-E1-54F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230193DR | 2024-05-29 | 2024-06-04 04:00 | 2024-06-23 12:00 | COMPLETE
Pungut | PUNG23_D14 | Pungut 00061 | S2-E1-54G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSM2/402/3230195DR | 2024-06-23 12:00 | 2024-06-28 01:00 | 2024-07-10 08:00 | COMPLETE
Balam So | P_BLSO24_LQR09 | Balam So 00604 | N1-W1-44C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-023 | SSE2/402/3230360DR | 2024-07-10 08:00 |  |  | IN_PROGRESS
Minas | P_4A-44 | Minas 02025 | 4A-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220527DR | 2022-10-29 | 2022-10-29 | 2022-11-13 20:00 | COMPLETE
Minas | P_7D-91N | Minas 02031 | 7D-91N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220346DR | 2022-11-13 20:00 | 2022-12-12 10:00 | 2022-12-31 14:00 | COMPLETE
Minas | P_6F-82 | Minas 02039 | 6F-82 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220454DR | 2022-12-31 14:00 | 2023-01-07 04:00 | 2023-01-20 02:00 | COMPLETE
Minas | P_7E-14 | Minas 02041 | 7E-14 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220637DR | 2023-01-20 02:00 | 2023-01-25 16:00 | 2023-02-12 05:00 | RELEASE
Minas | MNS-P07 | Minas 02045 | 9D-79N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220632DR | 2023-02-12 05:00 | 2023-02-26 04:00 | 2023-03-18 05:00 | COMPLETE
Minas | P_8E-77N | Minas 02051 | 8E-77N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220643DR | 2023-03-18 05:00 | 2023-03-27 14:30 | 2023-04-10 08:30 | COMPLETE
Minas | P_5C-57N | Minas 02057 | 5C-57N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230212DR | 2023-04-10 08:30 | 2023-04-18 20:30 | 2023-05-02 05:00 | COMPLETE
Minas | P_6D-64N | Minas 02061 | 6D-64N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSO2/402/3220652DR | 2023-05-02 05:00 | 2023-05-09 01:30 | 2023-05-18 18:30 | COMPLETE
Minas | P_5C-57 | Minas 02066 | 5C-57 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230213DR | 2023-05-18 18:30 | 2023-05-25 20:00 | 2023-06-09 | COMPLETE
Minas | P_5E-64N | Minas 02071 | 5E-64N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230230DR | 2023-06-09 | 2023-06-21 03:00 | 2023-06-30 06:30 | RELEASE
Minas | P_4C-35E | Minas 02074 | 4C-35E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230220DR | 2023-06-30 06:30 | 2023-07-07 11:00 | 2023-07-17 17:00 | RELEASE
Minas | P_4C-45N1 | Minas 02079 | 4C-45N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230225DR | 2023-07-17 17:00 | 2023-07-20 19:00 | 2023-07-29 21:00 | RELEASE
Minas | P_4C-46 | Minas 02080 | 4C-46 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230222DR | 2023-07-29 21:00 | 2023-08-01 23:00 | 2023-08-13 17:00 | COMPLETE
Minas | P_6B-24E | Minas 02087 | 6B-24E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230236DR | 2023-08-13 17:00 | 2023-08-20 17:00 | 2023-08-31 12:30 | COMPLETE
Minas | P_MINA24_7E-67 | Minas 02091 | 7E-67 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230498DR | 2023-08-31 12:30 | 2023-09-10 03:00 | 2023-09-23 05:00 | COMPLETE
Minas | P_MINA24_7E-67E | Minas 02092 | 7E-67E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230499DR | 2023-09-23 05:00 | 2023-09-26 08:00 | 2023-10-05 22:00 | COMPLETE
Minas | P_8D-66N1 | Minas 02098 | 8D-66N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230536DR | 2023-10-05 22:00 | 2023-10-09 19:00 | 2023-10-20 08:00 | COMPLETE
Minas | P_MINA24_8C-79E | Minas 02101 | 8C-79E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230511DR | 2023-10-20 08:00 | 2023-10-23 21:00 | 2023-11-02 04:00 | COMPLETE
Minas | P_5D-93E | Minas 02104 | 5D-93E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230240DR | 2023-11-02 04:00 | 2023-11-06 18:00 | 2023-11-15 23:59 | COMPLETE
Minas | P_6D-18E | Minas 02107 | 6D-18E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230243DR | 2023-11-16 | 2023-11-19 08:00 | 2023-11-29 13:00 | COMPLETE
Minas | P_MINA24_5C-27N | Minas 02110 | 5C-27N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230494DR | 2023-11-29 13:00 | 2023-12-06 20:00 | 2023-12-18 21:30 | COMPLETE
Minas | P_8E-42E | Minas 02113 | 8E-42E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230235DR | 2023-12-18 21:30 | 2024-01-13 03:30 | 2024-01-24 04:00 | COMPLETE
Bangko | P_BNKO24_P01 | Bangko 00437 | N1-W2-77C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230597DR | 2024-01-24 04:00 | 2024-02-12 07:00 | 2024-03-02 10:00 | COMPLETE
Balam So | P_BLSO24_LQR_P15 | Balam So 00590 | O-W1-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSE2/402/3240398DR | 2024-03-02 10:00 | 2024-03-10 07:30 | 2024-03-19 23:00 | COMPLETE
Bangko | P_BNKO24_P04 | Bangko 00439 | S1-E1-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230599DR | 2024-03-19 23:00 | 2024-03-27 10:00 | 2024-04-11 04:00 | COMPLETE
Minas | P_MINA24_2D-96N | Minas 02125 | 2D-96N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230490DR | 2024-04-11 04:00 |  | 2024-04-24 | SUSPENDED
Minas | P_MINA24_4E-95 | Minas 02126 | 4E-95 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230519DR | 2024-04-24 | 2024-05-07 10:00 | 2024-05-22 13:00 | COMPLETE
Minas | P_MINA24_3D-91N | Minas 02130 | 3D-91N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230513DR | 2024-05-22 13:00 | 2024-06-04 04:00 | 2024-06-14 16:30 | COMPLETE
Minas | P_MINA24_8D-23N1 | Minas 02115 | 8D-23N1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230502DR | 2024-06-14 16:30 | 2024-06-29 11:00 | 2024-07-14 17:00 | COMPLETE
Minas | P_MINA24_6D-43E | Minas 02133 | 6D-43E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-024 | SSM2/402/3230518DR | 2024-07-14 17:00 |  |  | IN_PROGRESS
Petapahan | PTP BL2-P19 | Petapahan 00162 | N1-W1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220660DR | 2022-12-31 23:00 | 2022-12-31 23:00 | 2023-01-25 13:00 | RELEASE
Petapahan | PTP BL2-P24 | Petapahan 00164 | N1-W1-42 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220436DR | 2023-01-25 13:00 | 2023-02-05 02:00 | 2023-03-16 13:00 | COMPLETE
Kotabatak | KB_PL44 | Kotabatak 00520 | N1-W1-41 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220392DR | 2023-03-16 13:00 | 2023-03-31 05:00 | 2023-04-17 09:00 | RELEASE
Kotabatak | KB_PL39 | Kotabatak 00521 | N1-W1-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220393DR | 2023-04-17 09:00 | 2023-04-25 | 2023-05-19 10:00 | RELEASE
Kotabatak | KTB-X35-INJ | Kotabatak 00533 | N1-O-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220455DR | 2023-05-19 10:00 | 2023-05-31 21:00 | 2023-06-15 15:00 | COMPLETE
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220628DR | 2023-06-15 15:00 | 2023-06-18 16:30 | 2023-07-03 05:00 | COMPLETE
Kotabatak | KB_PL33 Inj | Kotabatak 00522 | N1-W1-64 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220424DR | 2023-07-03 05:00 | 2023-07-10 15:00 | 2023-07-23 16:00 | COMPLETE
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSO2/402/3220623DR | 2023-07-23 16:00 | 2023-07-27 17:30 | 2023-08-10 15:00 | COMPLETE
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSE2/402/3230394DR | 2023-08-10 15:00 | 2023-08-16 21:00 | 2023-08-30 02:00 | COMPLETE
Kotabatak | KB_PL38 | Kotabatak 00542 | O-O-73 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230429DR | 2023-08-30 02:00 | 2023-09-01 21:00 | 2023-09-15 19:30 | COMPLETE
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SSE2/402/3230397DR | 2023-09-15 19:30 | 2023-09-19 15:30 | 2023-10-02 08:00 | COMPLETE
Kotabatak | KTB-A223 | Kotabatak 00544 | O-E1-51 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230412DR | 2023-10-02 08:00 | 2023-10-04 18:00 | 2023-10-18 04:00 | COMPLETE
Kotabatak | KB_PL41 | Kotabatak 00545 | O-E1-80 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230410DR | 2023-10-18 04:00 | 2023-10-21 13:00 | 2023-11-10 20:00 | COMPLETE
Kotabatak | KTB-A005 | Kotabatak 00548 | O-W1-40 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230407DR | 2023-11-10 20:00 | 2023-11-16 16:00 | 2023-11-28 21:30 | RELEASE
Kotabatak | KTB-A010 | Kotabatak 00549 | O-W1-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230417DR | 2023-11-28 21:30 | 2023-12-03 12:00 | 2023-12-21 06:30 | RELEASE
Kotabatak | KTB-A146_INJ | Kotabatak 00550 | O-W1-45 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230432DR | 2023-12-21 06:30 | 2024-01-13 17:00 | 2024-01-27 11:30 | COMPLETE
Kotabatak | KTB-A232_INJ | Kotabatak 00551 | O-E1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230437DR | 2024-01-27 11:30 | 2024-02-10 16:00 | 2024-02-27 14:00 | COMPLETE
Kotabatak | KTB-A254 | Kotabatak 00552 | O-O-27 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230414DR | 2024-02-27 14:00 | 2024-03-02 18:00 | 2024-03-14 08:00 | COMPLETE
Kotabatak | KTB-A268_INJ | Kotabatak 00553 | N1-W1-15B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230438DR | 2024-03-14 08:00 | 2024-03-20 21:00 | 2024-04-01 | COMPLETE
Kotabatak | KTB-A125 | Kotabatak 00554 | O-E1-79 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230421DR | 2024-04-01 | 2024-04-07 16:00 | 2024-04-19 02:00 | COMPLETE
Kotabatak | KTB-A207_INJ | Kotabatak 00555 | O-E1-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230436DR | 2024-04-19 02:00 | 2024-04-22 11:00 | 2024-05-03 06:00 | COMPLETE
Kotabatak | KTB-A235 | Kotabatak 00557 | O-E1-14 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230423DR | 2024-05-03 06:00 | 2024-05-10 15:00 | 2024-05-31 07:00 | RELEASE
Kotabatak | KTB-A264 | Kotabatak 00558 | N1-W1-23 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230427DR | 2024-05-31 07:00 | 2024-06-05 22:30 | 2024-06-22 21:00 | RELEASE
Kotabatak | KTB-A250 | Kotabatak 00559 | N1-W1-43 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230413DR | 2024-06-22 21:00 | 2024-06-26 14:00 | 2024-07-09 10:00 | RELEASE
Kotabatak | KTB-A052 | Kotabatak 00560 | N1-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ACS-026 | SKB2/402/3230409DR | 2024-07-09 10:00 | 2024-07-14 07:00 |  | IN_PROGRESS
Pungut | PUNG21_P04 | Pungut 00048 | S2-E1-54C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210134DR | 2021-09-07 18:00 | 2021-09-07 18:00 | 2021-09-23 14:00 | COMPLETE
Pungut | PUNG21_P03 | Pungut 00049 | S1-O-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210133DR | 2021-09-23 14:00 | 2021-09-30 21:00 | 2021-10-19 | COMPLETE
Bekasap | BKS-P17 | Bekasap 00199 | S1-O-14D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210011DR | 2021-10-19 | 2021-10-27 14:30 | 2021-11-06 14:00 | COMPLETE
Bekasap | BKS-P15 | Bekasap 00202 | O-O-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210009DR | 2021-11-06 14:00 | 2021-11-10 14:00 | 2021-11-21 | COMPLETE
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210008DR | 2021-11-21 | 2021-11-26 04:00 | 2021-12-08 19:00 | RELEASE
Bekasap | BKS-P4 | Bekasap 00206 | O-O-75C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210016DR | 2021-12-08 19:00 | 2022-01-08 20:15 | 2022-01-18 15:00 | COMPLETE
Bekasap | BKS-P11 | Bekasap 00210 | S1-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210005DR | 2022-01-18 15:00 | 2022-01-23 22:30 | 2022-02-06 | COMPLETE
Bekasap | BKS-P1 | Bekasap 00212 | O-E1-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220080DR | 2022-02-06 | 2022-02-11 03:30 | 2022-02-21 15:00 | COMPLETE
Bekasap | BKS-P8 | Bekasap 00213 | O-E1-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220081DR | 2022-02-21 15:00 | 2022-02-24 19:15 | 2022-03-07 10:00 | COMPLETE
Bekasap | BKS-X15 | Bekasap 00215 | O-E1-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220085DR | 2022-03-07 10:00 | 2022-03-13 16:00 | 2022-03-26 20:00 | COMPLETE
Bekasap | BKS-X08 | Bekasap 00217 | S1–O–35A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220084DR | 2022-03-26 20:00 | 2022-03-31 03:00 | 2022-04-13 15:00 | COMPLETE
Bangko | BNK-P4 | Bangko 00380 | N1-W1-11B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2210069DR | 2022-04-13 15:00 | 2022-04-21 01:30 | 2022-05-03 | COMPLETE
Bangko | BNK-P6 | Bangko 00377 | N1-W2-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220065DR | 2022-05-03 | 2022-05-08 15:00 | 2022-05-28 | RELEASE
Bangko | BNK-X01 | Bangko 00387 | O-O-21B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220067DR | 2022-05-28 | 2022-06-02 08:00 | 2022-06-16 08:00 | RELEASE
Bangko | BNK-X02 | Bangko 00389 | O-O-21C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220069DR | 2022-06-16 08:00 | 2022-06-20 10:30 | 2022-07-04 | COMPLETE
Bangko | BNK-X06 | Bangko 00395 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220077DR | 2022-07-04 | 2022-07-10 18:30 | 2022-07-23 10:00 | COMPLETE
Bangko | BNK-X07 | Bangko 00397 | O-O-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | GRK2/402/2220079DR | 2022-07-23 10:00 | 2022-07-28 18:00 | 2022-08-09 01:30 | COMPLETE
Bangko | BNK-X04 | Bangko 00391 | O-O-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220504DR | 2022-08-09 01:30 | 2022-08-14 01:00 | 2022-08-26 02:00 | COMPLETE
Bangko | BNK-X05 | Bangko 00393 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220516DR | 2022-08-25 02:00 | 2022-08-30 13:00 | 2022-09-10 14:00 | COMPLETE
Bangko | BNK_P5A_LQR | Bangko 00415 | N2-W1-85A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220389DR | 2022-09-10 14:00 | 2022-09-15 16:00 | 2022-09-25 10:00 | COMPLETE
Balam So | BLSO-P45 | Balam So 00497 | O-W1-15F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220321DR | 2022-09-25 10:00 | 2022-10-11 16:00 | 2022-10-24 20:30 | COMPLETE
Balam So | BLSO-P46 | Balam So 00502 | N1-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220341DR | 2022-10-24 20:30 | 2022-10-31 | 2022-11-07 12:00 | RELEASE
Balam So | BLSO-P38 | Balam So 00505 | N1-O-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220361DR | 2022-11-07 12:00 | 2022-11-15 12:00 | 2022-11-29 22:00 | COMPLETE
Balam So | BLSO23-P13 | Balam So 00511 | O-O-34E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220593DR | 2022-11-28 22:00 | 2022-12-06 03:00 | 2022-12-20 | COMPLETE
Balam So | BLSO23-P12 | Balam So 00514 | O-O-34F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220595DR | 2022-12-20 | 2022-12-24 21:00 | 2023-01-06 | COMPLETE
Balam So | BLSO23-P04 | Balam So 00516 | O-O-36D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220589DR | 2023-01-06 | 2023-01-10 16:30 | 2023-01-18 21:00 | COMPLETE
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220372DR | 2023-01-18 21:00 | 2023-01-25 10:00 | 2023-01-30 17:00 | RELEASE
Balam So | BLSO23-LQR-TE025 | Balam So 00520 | O-W1-24C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220429DR | 2023-01-30 17:00 | 2023-02-06 16:00 | 2023-02-25 | COMPLETE
Balam So | BLSO23-LQR-TE062 | Balam So 00521 | O-O-64B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220396DR | 2023-02-25 | 2023-03-04 | 2023-03-12 08:00 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220548DR | 2023-03-12 08:00 | 2023-03-16 10:00 | 2023-03-21 15:45 | COMPLETE
Balam So | BLSO23-LQR-TE037 | Balam So 00523 | O-O-34G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220453DR | 2023-03-21 15:45 | 2023-03-27 13:00 | 2023-04-04 04:00 | COMPLETE
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230364DR | 2023-04-04 04:00 | 2023-04-09 12:00 | 2023-04-14 18:00 | COMPLETE
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220588DR | 2023-04-14 18:00 | 2023-04-18 12:00 | 2023-04-23 07:00 | COMPLETE
Balam So | BLSO23-P02 | Balam So 00527 | N1-W1-74G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220594DR | 2023-04-23 07:00 | 2023-04-29 23:00 | 2023-05-07 17:30 | COMPLETE
Balam So | BLSO23-P03 | Balam So 00529 | N1-W1-74H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220597DR | 2023-05-07 17:30 | 2023-05-10 20:30 | 2023-05-19 02:00 | COMPLETE
Balam So | LQR-TE089_BLSO_2 | Balam So 00530 | O-O-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220550DR | 2023-05-19 02:00 | 2023-05-23 03:00 | 2023-05-30 15:00 | COMPLETE
Balam So | BLSO23-LQR-TE040 | Balam So 00531 | N1-W1-34A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220586DR | 2023-05-30 15:00 | 2023-06-03 15:00 | 2023-06-09 12:30 | COMPLETE
Balam So | BLSO23-P05 | Balam So 00533 | O-O-45B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220598DR | 2023-06-09 14:30 | 2023-06-13 13:30 | 2023-06-21 08:00 | COMPLETE
Balam So | BLSO23-P08 | Balam So 00534 | O-O-45C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220603DR | 2023-06-21 08:00 | 2023-06-24 | 2023-07-02 | COMPLETE
Balam So | LQR-TE155_BLSO_7 | Balam So 00538 | O-O-56D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220549DR | 2023-07-02 | 2023-07-13 23:00 | 2023-07-26 09:00 | COMPLETE
Balam So | BLSO23-LQR-TE042 | Balam So 00539 | O-O-77B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230349DR | 2023-07-26 09:00 | 2023-07-30 01:00 | 2023-08-04 05:00 | COMPLETE
Balam So | BLSO23-LQR-TE030 | Balam So 00543 | N1-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230332DR | 2023-08-04 05:00 | 2023-08-09 01:30 | 2023-08-14 02:00 | COMPLETE
Balam So | BLSO23-P16 | Balam So 00544 | O-O-56E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220602DR | 2023-08-14 02:00 | 2023-08-18 11:00 | 2023-08-25 21:00 | COMPLETE
Balam So | BLSO23-LQR-TE048 | Balam So 00547 | N1-W1-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230357DR | 2023-08-25 21:00 | 2023-08-30 10:00 | 2023-09-07 | COMPLETE
Bangko | BNK23_P22 | Bangko 00425 | N1-W2-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230289DR | 2023-09-07 | 2023-09-14 17:00 | 2023-09-28 18:00 | COMPLETE
Bangko | BNK23_P23 | Bangko 00428 | O-O-21D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230290DR | 2023-09-28 18:00 | 2023-10-02 17:00 | 2023-10-17 16:00 | COMPLETE
Bangko | BNK23_P09 | Bangko 00433 | O-O-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSM2/402/3230272DR | 2023-10-17 16:00 | 2023-10-21 02:30 | 2023-11-01 19:00 | COMPLETE
Balam So | LQR-TE200_BLSO_5 | Balam So 00562 | O-O-23I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230330DR | 2023-11-01 19:00 | 2023-11-08 06:30 | 2023-11-15 14:00 | COMPLETE
Balam So | P_BLSO24_LQR05 | Balam So 00564 | N1-W1-67D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230344DR | 2023-11-15 14:00 | 2023-11-20 05:00 | 2023-11-27 | COMPLETE
Balam So | BLSO23-LQR-TE032 | Balam So 00565 | N1-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230340DR | 2023-11-27 | 2023-12-16 17:00 | 2023-12-26 | COMPLETE
Balam So | BLSO23-LQR-TE055 | Balam So 00566 | N1-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230341DR | 2023-12-26 | 2023-12-30 14:15 | 2024-01-07 03:00 | COMPLETE
Balam So | BLSO23-LQR-TE027 | Balam So 00574 | N1-W1-87B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230370DR | 2024-01-07 03:00 | 2024-01-12 18:00 | 2024-01-19 14:00 | COMPLETE
Balam So | BLSO23-P14 | Balam So 00575 | N1-W1-87C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220600DR | 2024-01-19 14:00 | 2024-01-21 22:00 | 2024-01-29 05:00 | COMPLETE
Balam So | BLSO-P09 | Balam So 00583 | N1-O-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSO2/402/3220447DR | 2024-01-29 05:00 | 2024-02-07 05:00 | 2024-02-14 06:00 | COMPLETE
Balam So | P_BLSO24_LQR07 | Balam So 00589 | N1-W1-73G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230361DR | 2024-02-14 06:00 | 2024-02-23 06:00 | 2024-03-02 06:00 | COMPLETE
Balam So | LQR-TE213_BLSO_46 | Balam So 00584 | N1-W1-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230376DR | 2024-03-02 06:00 | 2024-03-09 13:30 | 2024-03-18 | COMPLETE
Balam So | P_BLSO24_LQR10 | Balam So 00585 | N1-W1-64C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230363DR | 2024-03-18 | 2024-03-20 13:00 | 2024-03-27 16:30 | COMPLETE
Balam So | BLSO23-LQR-TE067 | Balam So 00586 | N1-W1-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-55 | SSE2/402/3230338DR | 2024-03-27 16:30 | 2024-03-31 21:00 | 2024-04-08 09:00 | COMPLETE
Minas | MINA21_P01 | Minas 01984 | 4C-55N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210118DR | 2021-09-22 | 2021-09-22 | 2021-10-15 21:30 | COMPLETE
Minas | MINA21_P02 | Minas 01985 | 2D-72E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210119DR | 2021-10-15 21:30 | 2021-10-31 21:15 | 2021-11-13 05:00 | COMPLETE
Minas | MNS-P5 | Minas 01986 | 8E-52N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210112DR | 2021-11-13 05:00 | 2021-11-21 04:00 | 2021-12-04 03:30 | COMPLETE
Minas | MNS-P2 | Minas 01987 | 8D-18N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/2210020DR | 2021-12-04 03:30 | 2021-12-28 12:00 | 2022-01-14 13:00 | COMPLETE
Minas | MNS-P6 | Minas 01989 | 8E-32N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210105DR | 2022-01-14 13:00 | 2022-01-19 12:30 | 2022-02-05 | COMPLETE
Minas | MNS-P10 | Minas 01992 | 8E-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3210108DR | 2022-02-05 | 2022-02-13 18:30 | 2022-03-12 13:00 | RELEASE
Minas | MNS-P1 | Minas 01995 | 8D-48S | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220204DR | 2022-03-12 13:00 | 2022-03-20 15:30 | 2022-03-30 10:30 | RELEASE
Minas | MNS-P13 | Minas 01997 | 8D-57N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220201DR | 2022-03-30 10:30 | 2022-04-04 19:00 | 2022-04-15 18:00 | COMPLETE
Minas | MNS-P06 | Minas 01998 | 7E-56N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220213DR | 2022-04-14 18:00 | 2022-04-20 05:00 | 2022-05-01 12:30 | COMPLETE
Minas | MNA-P11 | Minas 02002 | 8D-49N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220217DR | 2022-05-01 12:30 | 2022-05-06 12:00 | 2022-05-17 12:30 | COMPLETE
Minas | MNS-P01 | Minas 02007 | 8E-94E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220209DR | 2022-05-17 12:30 | 2022-05-23 03:30 | 2022-06-06 | COMPLETE
Minas | P_7D-17N | Minas 02009 | 7D-17N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220225DR | 2022-06-06 | 2022-06-11 04:00 | 2022-06-21 15:00 | COMPLETE
Minas | P_7D-53N | Minas 02010 | 7D-53N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220228DR | 2022-06-21 15:00 | 2022-06-27 06:00 | 2022-07-07 08:00 | COMPLETE
Minas | MNS-P12_1 | Minas 02013 | 8C-88N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220211DR | 2022-07-07 08:00 | 2022-07-16 04:00 | 2022-07-25 09:30 | COMPLETE
Minas | P_6E-73E | Minas 02016 | 6E-73E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | GRK2/402/3220223DR | 2022-07-25 09:30 | 2022-07-31 | 2022-08-09 02:45 | COMPLETE
Minas | P_7D-48N | Minas 02019 | 7D-48N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220319DR | 2022-08-09 02:45 | 2022-08-14 02:30 | 2022-09-12 | COMPLETE
Minas | P_6C-11E | Minas 02022 | 6C-11E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220531DR | 2022-09-12 | 2022-09-19 04:30 | 2022-10-03 06:00 | COMPLETE
Minas | P_4D-58N | Minas 02024 | 4D-58N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220337DR | 2022-10-03 06:00 | 2022-10-15 12:00 | 2022-11-06 15:00 | COMPLETE
Minas | P_3C-87 | Minas 02028 | 3C-87 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220405DR | 2022-11-06 15:00 | 2022-11-15 18:00 | 2022-11-27 01:30 | COMPLETE
Minas | P_4C-14E | Minas 02029 | 4C-14E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220382DR | 2022-11-27 01:30 | 2022-12-02 17:15 | 2022-12-15 12:00 | RELEASE
Minas | P_6D-53N | Minas 02033 | 6D-53N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220350DR | 2022-12-15 12:00 | 2022-12-27 08:30 | 2023-01-07 08:00 | RELEASE
Minas | P_1E-72 | Minas 02038 | 1E-72 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220641DR | 2023-01-07 08:00 | 2023-01-17 05:30 | 2023-02-04 | COMPLETE
Minas | P_7C-37E | Minas 02040 | 7C-37E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220642DR | 2023-02-04 | 2023-02-21 08:00 | 2023-03-04 18:00 | COMPLETE
Minas | P_5B-77E | Minas 02043 | 5B-77E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220656DR | 2023-03-04 18:00 | 2023-03-13 06:00 | 2023-03-29 02:00 | COMPLETE
Minas | P_8C-66E | Minas 02053 | 8C-66E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220639DR | 2023-03-29 02:00 | 2023-04-08 03:00 | 2023-04-19 | COMPLETE
Minas | P_9E-11N | Minas 02048 | 9E-11N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230210DR | 2023-04-19 | 2023-04-27 04:00 | 2023-05-11 22:00 | COMPLETE
Minas | P_9E-21N | Minas 02049 | 9E-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220654DR | 2023-05-11 22:00 | 2023-05-16 22:00 | 2023-05-25 17:00 | COMPLETE
Minas | P_5C-59 | Minas 02067 | 5C-59 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230215DR | 2023-05-25 17:00 | 2023-06-02 08:00 | 2023-06-14 16:00 | COMPLETE
Minas | P_4D-38E | Minas 02070 | 4D-38E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220640DR | 2023-06-14 16:00 | 2023-06-22 08:00 | 2023-07-02 06:30 | COMPLETE
Minas | P_5D-14E1 | Minas 02077 | 5D-14E1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220648DR | 2023-07-02 06:30 | 2023-07-08 14:00 | 2023-07-17 04:00 | COMPLETE
Minas | P_7D-23N | Minas 02078 | 7D-23N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230247DR | 2023-07-17 04:00 | 2023-07-23 14:00 | 2023-08-04 05:00 | COMPLETE
Minas | P_3D-79N | Minas 02083 | 3D-79N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220653DR | 2023-08-04 05:00 | 2023-08-13 | 2023-08-22 18:00 | COMPLETE
Minas | P_6D-11E1 | Minas 02086 | 6D-11E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230231DR | 2023-08-22 18:00 | 2023-08-28 11:00 | 2023-09-05 13:30 | COMPLETE
Bangko | BNK_P88B_LQR | Bangko 00426 | O-W2-26B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220457DR | 2023-09-05 13:30 | 2023-09-17 14:00 | 2023-09-25 10:30 | COMPLETE
Bangko | BNK23_P08 | Bangko 00430 | O-O-52B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230275DR | 2023-09-25 10:30 | 2023-09-29 18:00 | 2023-10-17 16:30 | COMPLETE
Bangko | WFE-BNK_6 | Bangko 00432 | N2-W1-82A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230287DR | 2023-10-17 16:30 | 2023-10-22 13:00 | 2023-11-01 | COMPLETE
Bangko | BNK23_P11 | Bangko 00435 | N1-W2-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230269DR | 2023-11-01 | 2023-11-05 15:00 | 2023-11-15 13:00 | COMPLETE
Balam So | BLSO23-LQR-TE056 | Balam So 00560 | N1-O-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230359DR | 2023-11-15 13:00 | 2023-11-23 13:00 | 2023-11-29 23:00 | COMPLETE
Balam So | P_BLSO24_LQR01 | Balam So 00568 | O-W1-24D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230323DR | 2023-11-29 23:00 | 2023-12-12 13:00 | 2023-12-19 | COMPLETE
Balam So | BLSO23-P07 | Balam So 00571 | N1-W1-63H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSO2/402/3220599DR | 2023-12-19 | 2023-12-24 10:00 | 2023-12-31 14:30 | COMPLETE
Balam So | P_BLSO24_LQR04 | Balam So 00572 | O-W1-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230346DR | 2023-12-31 14:30 | 2024-01-15 22:00 | 2024-01-22 07:30 | COMPLETE
Bangko | P_BNKO24_P02 | Bangko 00438 | S1-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSM2/402/3230598DR | 2024-01-22 07:30 | 2024-01-31 11:30 | 2024-02-11 18:30 | COMPLETE
Balam So | LQR-TE011_BLSO_33 | Balam So 00588 | N1-W1-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3230331DR | 2024-02-11 18:30 | 2024-02-16 19:00 | 2024-02-24 | COMPLETE
Balam Se | P_BLSE24_P03 | Balam Se 00040 | O-O-76C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | AIRLANGGA-99 | SSE2/402/3240647DR | 2024-02-24 | 2024-03-04 18:00 | 2024-03-30 07:30 | RELEASE
Duri | P_3L44D | Duri 10852 | 3L-44D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210093DR | 2021-08-04 15:30 | 2021-08-06 05:00 | 2021-08-11 15:00 | COMPLETE
Duri | P_3K49C | Duri 10853 | 3K-49C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210024DR | 2021-08-11 15:00 | 2021-08-13 20:30 | 2021-08-18 09:00 | COMPLETE
Duri | P_4K50D | Duri 10854 | 4K-50D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/3210155DR | 2021-08-18 09:00 | 2021-08-19 22:00 | 2021-08-24 12:00 | COMPLETE
Duri | P_3F0108B | Duri 10859 | 3F-0108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210022DR | 2021-08-24 12:00 | 2021-08-25 22:00 | 2021-08-29 18:00 | COMPLETE
Duri | P_3E1009B | Duri 10860 | 3E-1009B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210023DR | 2021-08-29 18:00 | 2021-08-31 19:00 | 2021-09-04 15:00 | COMPLETE
Duri | 6G-0501B | Duri 10865 | 6G-0501B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210086DR | 2021-09-04 15:00 | 2021-09-06 01:30 | 2021-09-10 11:00 | COMPLETE
Duri | 6G-0303B | Duri 10866 | 6G-0303B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210087DR | 2021-09-10 11:00 | 2021-09-11 23:00 | 2021-09-16 09:00 | COMPLETE
Duri | 6F-0802B | Duri 10870 | 6F-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210083DR | 2021-09-16 09:00 | 2021-09-17 20:00 | 2021-09-22 06:00 | COMPLETE
Duri | 6G-0802B | Duri 10871 | 6G-0802B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210084DR | 2021-09-22 06:00 | 2021-09-23 15:00 | 2021-09-27 21:00 | COMPLETE
Duri | 6F-0702B | Duri 10874 | 6F-0702B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210031DR | 2021-09-27 21:00 | 2021-09-30 14:30 | 2021-10-05 07:00 | COMPLETE
Duri | 6F-0801B | Duri 10875 | 6F-0801B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210033DR | 2021-10-05 07:00 | 2021-10-06 19:00 | 2021-10-11 07:00 | COMPLETE
Duri | 5F-0309B | Duri 10878 | 5F-0309B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210035DR | 2021-10-11 07:00 | 2021-10-12 20:00 | 2021-10-17 07:00 | COMPLETE
Duri | 5F-1007B | Duri 10879 | 5F-1007B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210045DR | 2021-10-17 07:00 | 2021-10-18 21:00 | 2021-10-23 09:15 | COMPLETE
Duri | 6F-1203B | Duri 10882 | 6F-1203B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210051DR | 2021-10-23 09:15 | 2021-10-26 09:30 | 2021-10-31 09:30 | COMPLETE
Duri | 6G-0601B | Duri 10883 | 6G-0601B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210082DR | 2021-10-31 10:00 | 2021-11-03 02:30 | 2021-11-07 14:00 | COMPLETE
Duri | 5G-0412C | Duri 10887 | 5G-0412C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210007DR | 2021-11-07 14:00 | 2021-11-10 03:00 | 2021-11-14 18:15 | COMPLETE
Duri | 6G-1002B | Duri 10891 | 6G-1002B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210085DR | 2021-11-14 18:15 | 2021-11-17 10:30 | 2021-11-22 | COMPLETE
Duri | 5G-0412B | Duri 10888 | 5G-0412B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210010DR | 2021-11-22 | 2021-11-24 | 2021-11-28 15:30 | COMPLETE
Duri | 6G-0402B | Duri 10892 | 6G-0402B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210013DR | 2021-11-28 15:30 | 2021-11-30 15:30 | 2021-12-06 | COMPLETE
Duri | 5G-0209B | Duri 10895 | 5G-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210021DR | 2021-12-06 | 2021-12-08 11:30 | 2021-12-12 17:30 | COMPLETE
Duri | 5F-0612C | Duri 10896 | 5F-0612C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210076DR | 2021-12-12 17:30 | 2021-12-25 10:00 | 2021-12-29 15:15 | COMPLETE
Duri | 4V-28C | Duri 10899 | 4V-28C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210077DR | 2021-12-29 15:15 | 2022-01-07 | 2022-01-13 16:00 | COMPLETE
Duri | 4V-28D | Duri 10900 | 4V-28D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2210078DR | 2022-01-13 16:00 | 2022-01-17 01:00 | 2022-01-23 04:00 | COMPLETE
Duri | 3G-0606B | Duri 10903 | 3G-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220089DR | 2022-01-23 04:00 | 2022-01-30 13:00 | 2022-02-05 03:00 | COMPLETE
Duri | 3H-0201B | Duri 10904 | 3H-0201B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220091DR | 2022-02-05 03:00 | 2022-02-08 21:00 | 2022-02-15 05:30 | COMPLETE
Duri | 3H-0302B | Duri 10907 | 3H-0302B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220093DR | 2022-02-15 05:30 | 2022-02-17 14:00 | 2022-02-22 15:00 | COMPLETE
Duri | 4H-0912B | Duri 10911 | 4H-0912B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220102DR | 2022-02-22 15:00 | 2022-02-25 04:00 | 2022-03-02 01:00 | COMPLETE
Duri | 4H-0913B | Duri 10912 | 4H-0913B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220097DR | 2022-03-02 01:00 | 2022-03-03 23:00 | 2022-03-09 21:00 | COMPLETE
Duri | 6G-0301B | Duri 10923 | 6G-0301B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220112DR | 2022-03-09 21:00 | 2022-03-15 20:00 | 2022-03-20 16:00 | COMPLETE
Duri | 5G-0404B | Duri 10919 | 5G-0404B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220103DR | 2022-03-20 16:00 | 2022-03-23 09:00 | 2022-03-29 | COMPLETE
Duri | 5G-0308C | Duri 10927 | 5G-0308C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220114DR | 2022-03-28 | 2022-03-29 12:00 | 2022-04-02 17:00 | COMPLETE
Duri | 5E-1009C | Duri 10930 | 5E-1009C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220116DR | 2022-04-02 17:00 | 2022-04-05 23:30 | 2022-04-10 14:30 | COMPLETE
Duri | 5E-1110B | Duri 10937 | 5E-1110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220161DR | 2022-04-10 14:30 | 2022-04-21 06:00 | 2022-04-25 20:30 | COMPLETE
Duri | 5E-1010C | Duri 10940 | 5E-1010C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220152DR | 2022-04-25 20:30 | 2022-04-28 13:00 | 2022-05-03 05:00 | COMPLETE
Duri | 5E-1210B | Duri 10942 | 5E-1210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220160DR | 2022-05-03 05:00 | 2022-05-05 14:00 | 2022-05-10 07:00 | COMPLETE
Duri | 5E-0910B | Duri 10939 | 5E-0910B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220158DR | 2022-05-10 07:00 | 2022-05-13 02:00 | 2022-05-17 20:00 | COMPLETE
Duri | 5F-0210B | Duri 10941 | 5F-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220157DR | 2022-05-17 20:00 | 2022-05-20 07:00 | 2022-05-26 18:00 | COMPLETE
Duri | 5F-0310B | Duri 10949 | 5F-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220159DR | 2022-05-26 18:00 | 2022-05-29 | 2022-06-03 08:00 | COMPLETE
Duri | 5F-0308B | Duri 10947 | 5F-0308B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220136DR | 2022-06-03 08:00 | 2022-06-05 18:00 | 2022-06-12 21:30 | COMPLETE
Duri | 5F-0412B | Duri 10950 | 5F-0412B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220134DR | 2022-06-12 21:30 | 2022-06-15 12:00 | 2022-06-21 07:30 | COMPLETE
Duri | 6F-0501C | Duri 10960 | 6F-0501C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220144DR | 2022-06-21 07:30 | 2022-06-24 23:00 | 2022-06-29 15:00 | COMPLETE
Duri | 5F-0510C | Duri 10956 | 5F-0510C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220154DR | 2022-06-29 15:00 | 2022-06-30 23:30 | 2022-07-05 15:30 | COMPLETE
Duri | 5F-0507C | Duri 10952 | 5F-0507C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220162DR | 2022-07-05 15:30 | 2022-07-07 03:30 | 2022-07-11 12:30 | COMPLETE
Duri | 4I-0312B | Duri 10968 | 4I-0312B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220121DR | 2022-07-11 12:30 | 2022-07-13 23:00 | 2022-07-18 02:15 | COMPLETE
Duri | 5F-0606B | Duri 10962 | 5F-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-3511 | GRK2/402/2220148DR | 2022-07-18 02:15 | 2022-07-20 03:00 | 2022-07-24 12:00 | COMPLETE
Petani | Petani P01 | Petani 00130 | O-O-76B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-3516 | GRK2/402/2210139DR | 2021-11-02 02:30 | 2021-11-06 02:30 | 2021-11-15 09:30 | COMPLETE
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | APS-3523 | GRK2/402/2210034DR | 2021-09-29 03:30 | 2021-09-30 20:30 | 2021-10-04 22:30 | COMPLETE
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-3523 | GRK2/402/2210065DR | 2022-03-24 11:00 | 2022-03-25 18:00 | 2022-03-29 11:00 | COMPLETE
Balam So | BLSO-P02 | Balam So 00459 | O-O-36C | Perforation - Re-perforation | PRF04 - Perforation - Re-Perforation | Land Workover Unit | APS-3523 | GRK2/402/2220004DR | 2022-07-16 02:00 | 2022-07-17 14:00 | 2022-07-24 13:00 | COMPLETE
Balam So | BLSO-P16 | Balam So 00454 | O-O-36B | Perforation - Re-perforation | PRF04 - Perforation - Re-Perforation | Land Workover Unit | APS-3523 | GRK2/402/2220009DR | 2022-07-24 13:00 | 2022-07-25 17:30 | 2022-07-28 19:00 | COMPLETE
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220010DR | 2022-04-19 | 2022-04-22 15:30 | 2022-04-26 09:30 | COMPLETE
Balam So | BLSO-P31 | Balam So 00455 | S1-O-45C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220023DR | 2022-05-04 14:00 | 2022-05-05 09:00 | 2022-05-13 | COMPLETE
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220028DR | 2022-05-17 16:30 | 2022-05-18 16:30 | 2022-06-02 | COMPLETE
Balam So | BLSO-P17 | Balam So 00472 | O-O-35G | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220025DR | 2022-06-26 22:00 | 2022-06-28 | 2022-07-04 21:00 | COMPLETE
Balam So | BLSO-P23 | Balam So 00470 | N1-W1-84A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220022DR | 2022-07-04 21:00 | 2022-07-06 09:00 | 2022-07-16 | COMPLETE
Balam So | BLSO-P26 | Balam So 00462 | N1-W1-67C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | APS-358 | GRK2/402/2220024DR | 2022-08-03 21:30 | 2022-08-05 06:00 | 2022-08-06 12:00 | COMPLETE
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210093DR | 2021-08-07 20:30 | 2021-08-07 20:30 | 2021-09-07 14:00 | COMPLETE
Bangko | Bangko P29 | Bangko 00347 | O-W1-78A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210032DR | 2021-09-07 14:00 | 2021-09-19 12:00 | 2021-10-03 | COMPLETE
Tilan | Tilan P02 | Tilan 00033 | O-O-27F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210165DR | 2021-10-03 | 2021-10-16 12:00 | 2021-11-21 09:00 | COMPLETE
Tilan | Tilan P01 | Tilan 00034 | O-O-44C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210166DR | 2021-11-21 09:00 | 2021-11-29 08:45 | 2021-12-31 02:30 | COMPLETE
Pager | PG-P2 | Pager 00048 | O-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210130DR | 2021-12-31 02:30 | 2022-01-14 10:00 | 2022-01-31 18:00 | COMPLETE
Pager | PG-P1 | Pager 00049 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2210129DR | 2022-01-31 18:00 | 2022-02-05 16:00 | 2022-03-02 09:00 | COMPLETE
Pager | PG-P3 | Pager 00050 | O-O-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220238DR | 2022-03-02 09:00 | 2022-03-15 02:00 | 2022-04-01 06:00 | COMPLETE
Petani | PETA22-P14 | Petani 00142 | S1-O-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220258DR | 2022-04-01 06:00 | 2022-04-09 | 2022-04-29 04:00 | COMPLETE
Petani | PTN-X11 | Petani 00144 | S1-O-26C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220250DR | 2022-04-29 04:00 | 2022-05-07 22:00 | 2022-05-26 | RELEASE
Hitam | Hitam P07 | Hitam 00012 | N1-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220163DR | 2022-05-26 | 2022-06-06 22:30 | 2022-07-03 16:00 | COMPLETE
Kotabatak | KB_PL4 | Kotabatak 00487 | O-W2-17 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/2220253DR | 2022-07-03 16:00 | 2022-07-18 13:00 | 2022-08-01 13:00 | COMPLETE
Kotabatak | KB_PL5 Inj | Kotabatak 00490 | N1-W2-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | GRK2/402/3220191DR | 2022-08-01 13:00 | 2022-08-05 19:30 | 2022-08-16 12:00 | RELEASE
Kotabatak | KTB-X08 | Kotabatak 00493 | N1-W2-59 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220513DR | 2022-08-16 12:00 | 2022-08-21 20:00 | 2022-09-02 10:00 | COMPLETE
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220522DR | 2022-09-02 10:00 | 2022-09-07 18:00 | 2022-09-20 13:00 | COMPLETE
Kotabatak | KB_PL12 | Kotabatak 00496 | S1-O-22 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220345DR | 2022-09-20 13:00 | 2022-10-03 03:30 | 2022-10-13 17:00 | COMPLETE
Kotabatak | KB_PL19 | Kotabatak 00499 | S1-O-19 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220367DR | 2022-10-13 17:00 | 2022-10-19 12:00 | 2022-10-31 17:00 | COMPLETE
Kotabatak | KB_PL47 Inj | Kotabatak 00501 | N1-W2-36 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220537DR | 2022-10-31 17:00 | 2022-11-07 19:00 | 2022-11-21 10:00 | RELEASE
Kotabatak | KTB-P1 | Kotabatak 00503 | S2-O-25 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220446DR | 2022-11-21 10:00 | 2022-11-28 22:00 | 2022-12-25 15:00 | RELEASE
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220625DR | 2022-12-25 15:00 | 2023-01-03 16:30 | 2023-01-15 15:30 | COMPLETE
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220627DR | 2023-01-15 15:30 | 2023-01-20 18:00 | 2023-02-01 03:30 | COMPLETE
Kotabatak | KTB-X11 | Kotabatak 00511 | N1-W1-54 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220426DR | 2023-02-01 03:30 | 2023-02-07 11:00 | 2023-02-28 09:00 | COMPLETE
Kotabatak | KTB-X36-INJ | Kotabatak 00513 | N1-W1-37 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220388DR | 2023-02-28 09:00 | 2023-03-06 | 2023-03-23 15:00 | COMPLETE
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230384DR | 2023-03-23 15:00 | 2023-04-02 19:00 | 2023-04-15 11:00 | COMPLETE
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230386DR | 2023-04-15 11:00 | 2023-04-20 17:30 | 2023-05-03 20:00 | COMPLETE
Kotabatak | KTB-A267 | Kotabatak 00519 | N1-W1-49 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230388DR | 2023-05-03 20:00 | 2023-05-10 | 2023-05-20 06:00 | COMPLETE
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230391DR | 2023-05-20 06:00 | 2023-05-26 15:00 | 2023-06-07 10:30 | COMPLETE
Kotabatak | KB_PL17 Inj | Kotabatak 00529 | O-O-11 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230390DR | 2023-06-07 10:30 | 2023-06-10 12:00 | 2023-06-19 14:00 | COMPLETE
Kotabatak | KB_PL13 | Kotabatak 00527 | N1-O-84 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220626DR | 2023-06-19 14:00 | 2023-06-22 19:00 | 2023-07-02 16:30 | COMPLETE
Kotabatak | KTB-X37-INJ | Kotabatak 00528 | S1-W1-47 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230396DR | 2023-07-02 16:30 | 2023-07-08 01:45 | 2023-07-18 21:00 | COMPLETE
Kotabatak | KB_PL9 | Kotabatak 00535 | S1-W1-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230431DR | 2023-07-18 21:00 | 2023-07-22 12:00 | 2023-08-02 22:30 | COMPLETE
Kotabatak | KTB-A198_INJ | Kotabatak 00536 | S1-W1-43 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230434DR | 2023-08-02 22:30 | 2023-08-07 18:00 | 2023-08-20 | COMPLETE
Kotabatak | KTB-A98 | Kotabatak 00537 | S1-W1-42 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230430DR | 2023-08-20 | 2023-08-22 15:30 | 2023-09-03 | COMPLETE
Kotabatak | KTB-A023 | Kotabatak 00546 | O-W1-55 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230418DR | 2023-09-03 | 2023-09-09 | 2023-09-19 14:00 | COMPLETE
Kotabatak | KTB-A185_INJ | Kotabatak 00547 | O-W1-66 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SKB2/402/3230433DR | 2023-09-19 14:00 | 2023-09-24 14:00 | 2023-10-07 10:00 | COMPLETE
Petapahan | PTPBL3-P9B | Petapahan 00166 | N2-W1-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220878DR | 2023-10-07 10:00 | 2023-10-14 13:30 | 2023-11-03 05:00 | COMPLETE
Petapahan | PTPBL3-P15 | Petapahan 00168 | N2-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220879DR | 2023-11-03 05:00 | 2023-11-08 05:00 | 2023-11-27 07:00 | COMPLETE
Petapahan | PETP21-P09 | Petapahan 00170 | O-O-68 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220877DR | 2023-11-27 07:00 | 2023-12-11 19:30 | 2023-12-25 06:00 | COMPLETE
Petapahan | PTP BL2-P16 | Petapahan 00171 | N1-W1-44D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220880DR | 2023-12-25 06:00 | 2024-01-07 12:00 | 2024-01-26 05:00 | COMPLETE
Petapahan | PTP BL2-Z09 | Petapahan 00172 | N1-W1-44E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSO2/402/3220411DR | 2024-01-26 05:00 | 2024-01-26 17:00 | 2024-02-16 16:30 | COMPLETE
Petapahan | P_PETP24_INJ04 | Petapahan 00173 | N2-W1-57A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220882DR | 2024-02-16 16:30 | 2024-03-01 23:30 | 2024-03-19 15:00 | COMPLETE
Petapahan | PTPBL3-P8 | Petapahan 00174 | N2-W1-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSA2/402/3220876DR | 2024-03-19 15:00 | 2024-03-23 22:30 | 2024-04-14 | COMPLETE
Kotabatak | KB_PL15 | Kotabatak 00556 | O-E1-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | APS-752 | SSE2/402/3230393DR | 2024-04-14 | 2024-04-22 04:00 | 2024-05-06 12:00 | COMPLETE
Duri | 5F-0609B | Duri 10965 | 5F-0609B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | GRK2/402/2220156DR | 2022-07-24 12:00 | 2022-07-30 08:00 | 2022-08-05 13:15 | COMPLETE
Duri | 6F-0602B | Duri 10967 | 6F-0602B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | GRK2/402/2220141DR | 2022-08-05 13:15 | 2022-08-08 20:00 | 2022-08-14 | COMPLETE
Duri | 5F-0707B | Duri 10969 | 5F-0707B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220555DR | 2022-08-14 | 2022-08-16 08:00 | 2022-08-21 14:00 | COMPLETE
Duri | 5F-0710B | Duri 10971 | 5F-0710B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220556DR | 2022-08-21 14:00 | 2022-08-23 05:00 | 2022-08-28 05:00 | COMPLETE
Duri | 5F-0809B | Duri 10975 | 5F-0809B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220463DR | 2022-08-28 05:00 | 2022-08-30 12:30 | 2022-09-04 12:45 | COMPLETE
Duri | 5F-0812B | Duri 10978 | 5F-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220464DR | 2022-09-04 12:45 | 2022-09-06 12:45 | 2022-09-11 | COMPLETE
Duri | 5H-1103B | Duri 10980 | 5H-1103B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220478DR | 2022-09-11 12:00 | 2022-09-13 04:30 | 2022-09-18 02:30 | COMPLETE
Duri | 5H-0703C | Duri 10983 | 5H-0703C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220481DR | 2022-09-18 02:30 | 2022-09-20 02:30 | 2022-09-24 18:00 | COMPLETE
Duri | 5F-1009B | Duri 10987 | 5F-1009B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220468DR | 2022-09-24 18:00 | 2022-09-28 13:00 | 2022-10-03 11:00 | COMPLETE
Duri | 6F-1101B | Duri 10985 | 6F-1101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220470DR | 2022-10-03 11:00 | 2022-10-05 22:30 | 2022-10-11 04:00 | COMPLETE
Duri | 5H-0503C | Duri 10982 | 5H-0503C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220482DR | 2022-10-11 04:00 | 2022-10-15 23:00 | 2022-10-21 15:00 | COMPLETE
Duri | 6H-0202B | Duri 10995 | 6H-0202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220487DR | 2022-10-21 15:00 | 2022-10-24 02:00 | 2022-10-29 | COMPLETE
Duri | 6F-0902B | Duri 10991 | 6F-0902B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220467DR | 2022-10-29 | 2022-11-02 04:00 | 2022-11-08 | COMPLETE
Duri | 6F-1102B | Duri 10994 | 6F-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220471DR | 2022-11-08 | 2022-11-11 01:00 | 2022-11-16 15:30 | COMPLETE
Duri | 6H-0301B | Duri 10996 | 6H-0301B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220486DR | 2022-11-16 15:30 | 2022-11-19 04:30 | 2022-11-26 22:00 | COMPLETE
Duri | 5F-1108B | Duri 10999 | 5F-1108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220473DR | 2022-11-26 22:00 | 2022-11-29 17:00 | 2022-12-05 | COMPLETE
Duri | 5F-1209B | Duri 11004 | 5F-1209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220474DR | 2022-12-05 | 2022-12-06 16:00 | 2022-12-11 14:00 | COMPLETE
Duri | 5G-0108B | Duri 11011 | 5G-0108B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220476DR | 2022-12-11 14:00 | 2022-12-17 12:00 | 2022-12-21 23:30 | COMPLETE
Duri | 6F-1202B | Duri 11008 | 6F-1202B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220475DR | 2022-12-21 23:30 | 2022-12-25 10:30 | 2022-12-30 12:00 | COMPLETE
Duri | 5G-0110B | Duri 11015 | 5G-0110B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220557DR | 2022-12-30 12:00 | 2023-01-01 13:00 | 2023-01-06 13:00 | COMPLETE
Duri | 6G-0202C | Duri 11012 | 6G-0202C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220558DR | 2023-01-06 13:00 | 2023-01-08 17:00 | 2023-01-14 | COMPLETE
Duri | 5G-0310B | Duri 11016 | 5G-0310B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220559DR | 2023-01-14 | 2023-01-16 | 2023-01-20 20:30 | COMPLETE
Duri | 6G-0405B | Duri 11027 | 6G-0405B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220560DR | 2023-01-20 20:30 | 2023-01-23 | 2023-01-29 03:30 | COMPLETE
Duri | 5G-0513B | Duri 11028 | 5G-0513B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220561DR | 2023-01-29 03:30 | 2023-01-31 01:00 | 2023-02-05 03:30 | COMPLETE
Duri | 5G-0703B | Duri 11029 | 5G-0703B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220562DR | 2023-02-05 03:30 | 2023-02-07 | 2023-02-23 15:00 | COMPLETE
Duri | 5H-0601B | Duri 11030 | 5H-0601B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | DRI2/402/3220825DR | 2023-02-22 15:00 | 2023-02-25 03:30 | 2023-03-03 02:00 | COMPLETE
Duri | 5G-1102B | Duri 11031 | 5G-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | DRI2/402/3220826DR | 2023-03-03 02:00 | 2023-03-06 23:00 | 2023-03-11 15:00 | COMPLETE
Duri | 5G-0711B | Duri 11034 | 5G-0711B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220870DR | 2023-03-11 15:00 | 2023-03-20 10:00 | 2023-03-27 03:00 | COMPLETE
Duri | 5G-1105B | Duri 11050 | 5G-1105B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220866DR | 2023-03-27 03:00 | 2023-04-04 18:00 | 2023-04-10 06:00 | COMPLETE
Duri | 6G-0901B | Duri 11051 | 6G-0901B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220873DR | 2023-04-10 06:00 | 2023-04-13 15:00 | 2023-04-18 10:00 | COMPLETE
Duri | 5H-0403B | Duri 11052 | 5H-0403B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220857DR | 2023-04-18 10:00 | 2023-04-21 01:00 | 2023-04-26 14:00 | COMPLETE
Duri | 6G-1102B | Duri 11053 | 6G-1102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220871DR | 2023-04-26 14:00 | 2023-04-29 06:00 | 2023-05-03 13:00 | COMPLETE
Duri | 6G-0801B | Duri 11057 | 6G-0801B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230095DR | 2023-05-03 13:00 | 2023-06-01 23:00 | 2023-06-07 13:00 | COMPLETE
Duri | 5G-0112B | Duri 11059 | 5G-0112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230113DR | 2023-06-07 13:00 | 2023-06-10 | 2023-06-15 21:00 | COMPLETE
Duri | 6F-1001B | Duri 11078 | 6F-1001B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230059DR | 2023-06-15 21:00 | 2023-06-18 01:00 | 2023-06-24 07:00 | COMPLETE
Duri | 5F-1013B | Duri 11072 | 5F-1013B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230096DR | 2023-06-24 07:00 | 2023-06-26 12:00 | 2023-07-03 02:30 | COMPLETE
Duri | 5F-1013C | Duri 11073 | 5F-1013C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230058DR | 2023-07-03 02:30 | 2023-07-04 22:00 | 2023-07-10 22:00 | COMPLETE
Duri | 5H-0406B | Duri 11086 | 5H-0406B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | ADH2/402/2220864DR | 2023-07-10 22:00 | 2023-07-13 16:00 | 2023-07-18 23:00 | COMPLETE
Duri | 5E-1210C | Duri 11087 | 5E-1210C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230116DR | 2023-07-18 23:00 | 2023-07-21 02:00 | 2023-07-27 15:00 | COMPLETE
Duri | 5F-1112B | Duri 11090 | 5F-1112B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230097DR | 2023-07-27 15:00 | 2023-07-29 22:00 | 2023-08-04 14:00 | COMPLETE
Duri | 5K-23F | Duri 11091 | 5K-23F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230067DR | 2023-08-04 14:00 | 2023-08-06 02:00 | 2023-08-14 12:00 | COMPLETE
Duri | 6K-22D | Duri 11042 | 6K-22D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230121DR | 2023-08-14 12:00 | 2023-08-16 18:00 | 2023-08-24 13:00 | COMPLETE
Duri | 6G-0102B | Duri 11060 | 6G-0102B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230068DR | 2023-08-24 13:00 | 2023-08-26 12:00 | 2023-09-01 19:00 | COMPLETE
Duri | 6G-0301C | Duri 11107 | 6G-0301C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230070DR | 2023-09-01 19:00 | 2023-09-03 03:00 | 2023-09-08 15:00 | COMPLETE
Duri | 6G-0301D | Duri 11108 | 6G-0301D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230124DR | 2023-09-08 15:00 | 2023-09-09 19:00 | 2023-09-15 21:00 | COMPLETE
Duri | 5F-1011B | Duri 11119 | 5F-1011B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230071DR | 2023-09-15 21:00 | 2023-09-17 01:00 | 2023-09-22 21:00 | COMPLETE
Duri | 2H-1010A | Duri 11121 | 2H-1010A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220797DR | 2023-09-22 21:00 | 2023-09-24 | 2023-10-01 05:00 | COMPLETE
Duri | 2H-1011A | Duri 11122 | 2H-1011A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220799DR | 2023-10-01 05:00 | 2023-10-02 03:00 | 2023-10-07 18:30 | COMPLETE
Duri | 2H-1112A | Duri 11126 | 2H-1112A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220795DR | 2023-10-07 18:30 | 2023-10-08 16:00 | 2023-10-16 05:30 | COMPLETE
Duri | 2H-1210A | Duri 11132 | 2H-1210A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220776DR | 2023-10-16 05:30 | 2023-10-17 02:00 | 2023-10-23 13:00 | COMPLETE
Duri | 2H-1211A | Duri 11136 | 2H-1211A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220779DR | 2023-10-23 13:00 | 2023-10-24 11:00 | 2023-10-30 18:30 | COMPLETE
Duri | 2J-0113A | Duri 11139 | 2J-0113A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220787DR | 2023-10-30 18:30 | 2023-10-31 23:00 | 2023-11-07 09:00 | COMPLETE
Duri | 2J-0112A | Duri 11140 | 2J-0112A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220773DR | 2023-11-07 09:00 | 2023-11-08 14:00 | 2023-11-15 01:30 | COMPLETE
Duri | 2J-0211A | Duri 11146 | 2J-0211A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220784DR | 2023-11-15 01:30 | 2023-11-16 10:00 | 2023-11-23 17:00 | COMPLETE
Duri | 2J-0312A | Duri 11147 | 2J-0312A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220775DR | 2023-11-23 17:00 | 2023-11-25 | 2023-12-01 03:00 | COMPLETE
Duri | 2J-0811A | Duri 11157 | 2J-0811A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220745DR | 2023-12-01 03:00 | 2023-12-02 20:00 | 2023-12-10 05:30 | COMPLETE
Duri | 2J-0413A | Duri 11158 | 2J-0413A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220763DR | 2023-12-10 05:30 | 2023-12-14 15:30 | 2023-12-21 04:00 | COMPLETE
Duri | 2J-0910A | Duri 11168 | 2J-0910A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220737DR | 2023-12-21 04:00 | 2023-12-27 01:00 | 2024-01-06 14:00 | COMPLETE
Duri | 3J-0502A | Duri 11169 | 3J-0502A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220757DR | 2024-01-06 14:00 | 2024-01-28 15:00 | 2024-02-03 05:30 | COMPLETE
Duri | 2J-0613A | Duri 11175 | 2J-0613A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220754DR | 2024-01-09 | 2024-01-16 21:00 | 2024-01-25 | COMPLETE
Duri | 2J-0410A | Duri 11181 | 2J-0410A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220762DR | 2024-02-03 05:30 | 2024-02-06 18:00 | 2024-02-12 19:30 | COMPLETE
Duri | 5H-0901B | Duri 11182 | 5H-0901B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240034DR | 2024-02-12 19:30 | 2024-02-15 03:00 | 2024-02-20 19:00 | COMPLETE
Duri | 6G-1101B | Duri 11183 | 6G-1101B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240035DR | 2024-02-20 19:00 | 2024-02-22 11:30 | 2024-02-28 | COMPLETE
Duri | 5E-1111B | Duri 11191 | 5E-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240036DR | 2024-02-28 | 2024-02-29 18:00 | 2024-03-06 16:00 | COMPLETE
Duri | 3F-0303A | Duri 11192 | 3F-0303A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240038DR | 2024-03-06 16:00 | 2024-03-08 09:00 | 2024-03-15 20:00 | COMPLETE
Duri | 6K-12B | Duri 11202 | 6K-12B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230092DR | 2024-03-15 20:00 | 2024-03-18 12:00 | 2024-03-26 08:00 | COMPLETE
Duri | 5J-78E | Duri 11207 | 5J-78E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240039DR | 2024-03-26 08:00 | 2024-03-28 15:00 | 2024-04-04 17:00 | COMPLETE
Duri | 5J-85D | Duri 11210 | 5J-85D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240048DR | 2024-04-04 17:00 | 2024-04-07 08:30 | 2024-04-15 12:00 | COMPLETE
Duri | 5J-86D | Duri 11216 | 5J-86D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240049DR | 2024-04-15 12:00 | 2024-04-19 16:30 | 2024-04-30 | COMPLETE
Duri | 5G-0905C | Duri 11219 | 5G-0905C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240044DR | 2024-04-30 | 2024-05-02 | 2024-05-08 05:00 | COMPLETE
Duri | 5G-1010B | Duri 11223 | 5G-1010B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240076DR | 2024-05-08 05:00 | 2024-05-09 22:30 | 2024-05-16 02:00 | COMPLETE
Duri | 5G-1010C | Duri 11225 | 5G-1010C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240050DR | 2024-05-16 02:00 | 2024-05-17 14:30 | 2024-05-23 18:00 | COMPLETE
Duri | 5F-0207B | Duri 11231 | 5F-0207B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240043DR | 2024-05-23 18:00 | 2024-05-25 12:00 | 2024-05-31 14:00 | COMPLETE
Duri | 5G-0909B | Duri 11234 | 5G-0909B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240838DR | 2024-05-31 14:00 | 2024-06-04 18:00 | 2024-06-11 | COMPLETE
Duri | 5E-0907B | Duri 11238 | 5E-0907B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2230091DR | 2024-06-11 | 2024-06-12 23:00 | 2024-06-19 04:00 | COMPLETE
Duri | 4G-0313B | Duri 11228 | 4G-0313B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHT2/402/2240836DR | 2024-06-19 04:00 | 2024-06-21 04:00 | 2024-06-26 17:00 | COMPLETE
Duri | 3H-1201A | Duri 11241 | 3H-1201A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220801DR | 2024-06-26 17:00 | 2024-06-28 09:00 | 2024-07-04 17:00 | COMPLETE
Duri |  | Duri 11249 | 2H-1213A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220800DR | 2024-07-04 17:00 | 2024-07-06 16:00 | 2024-07-14 02:00 | COMPLETE
Duri | 3J-0102A | Duri 11245 | 3J-0102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-01 | RHO2/402/2220796DR | 2024-07-14 02:00 |  |  | IN_PROGRESS
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220373DR | 2022-09-22 19:00 | 2022-09-22 19:00 | 2022-09-26 11:30 | COMPLETE
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220394DR | 2022-09-26 11:30 | 2022-10-02 03:00 | 2022-10-05 | COMPLETE
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220440DR | 2022-10-05 | 2022-10-14 04:00 | 2022-10-16 10:00 | RELEASE
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220415DR | 2022-10-16 10:00 | 2022-10-20 19:00 | 2022-10-22 14:00 | COMPLETE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220407DR | 2022-10-22 14:00 | 2022-10-24 23:00 | 2022-10-26 19:00 | RELEASE
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | SSO2/402/3220390DR | 2022-10-26 19:00 | 2022-10-30 02:00 | 2022-11-01 | COMPLETE
Duri | 4I-0113B | Duri 10993 | 4I-0113B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220494DR | 2022-11-01 | 2022-11-19 05:00 | 2022-12-12 | COMPLETE
Duri | 5G-0610B | Duri 10998 | 5G-0610B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220493DR | 2022-12-12 | 2022-12-20 03:00 | 2022-12-30 | COMPLETE
Duri | 4H-0812B | Duri 11000 | 4H-0812B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220495DR | 2022-12-30 | 2023-01-02 17:00 | 2023-01-09 12:30 | COMPLETE
Duri | 6G-0701B | Duri 11017 | 6G-0701B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220499DR | 2023-01-09 12:30 | 2023-01-12 18:00 | 2023-01-19 14:30 | COMPLETE
Duri | 5G-0806B | Duri 11005 | 5G-0806B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220496DR | 2023-01-19 14:30 | 2023-01-22 05:00 | 2023-01-28 19:00 | COMPLETE
Duri | 6G-0804B | Duri 11009 | 6G-0804B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220497DR | 2023-01-28 19:00 | 2023-02-01 01:00 | 2023-02-08 10:00 | COMPLETE
Duri | 5G-0710B | Duri 11014 | 5G-0710B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220498DR | 2023-02-08 10:00 | 2023-02-10 18:00 | 2023-03-02 18:00 | COMPLETE
Duri | 5G-0910B | Duri 11022 | 5G-0910B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220573DR | 2023-03-02 18:00 | 2023-03-09 07:00 | 2023-03-17 05:00 | COMPLETE
Duri | 5G-1111B | Duri 11039 | 5G-1111B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220869DR | 2023-03-17 05:00 | 2023-03-23 03:00 | 2023-03-30 13:00 | COMPLETE
Duri | 5H-0409B | Duri 11040 | 5H-0409B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220872DR | 2023-03-30 13:00 | 2023-04-02 17:00 | 2023-04-09 07:00 | COMPLETE
Duri | 5H-0210B | Duri 11038 | 5H-0210B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220863DR | 2023-04-09 07:00 | 2023-04-19 13:00 | 2023-04-26 03:00 | COMPLETE
Duri | 6G-0503B | Duri 11019 | 6G-0503B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220500DR | 2023-04-26 03:00 | 2023-04-28 17:30 | 2023-05-04 18:00 | COMPLETE
Duri | 5G-0605B | Duri 11033 | 5G-0605B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | DRI2/402/3220828DR | 2023-05-04 18:00 | 2023-05-07 13:00 | 2023-05-13 15:30 | COMPLETE
Duri | 5H-0606B | Duri 11055 | 5H-0606B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230056DR | 2023-05-13 15:30 | 2023-05-22 07:00 | 2023-05-29 | COMPLETE
Duri | 5H-0213B | Duri 11045 | 5H-0213B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220862DR | 2023-05-29 | 2023-06-01 18:00 | 2023-06-10 02:00 | COMPLETE
Duri | 5G-1103C | Duri 11047 | 5G-1103C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | ADH2/402/2220868DR | 2023-06-10 02:00 | 2023-06-12 10:30 | 2023-06-18 16:00 | COMPLETE
Duri | 6G-0101C | Duri 11075 | 6G-0101C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230115DR | 2023-06-18 16:00 | 2023-06-21 06:30 | 2023-07-01 15:00 | COMPLETE
Duri | 5F-0708B | Duri 11076 | 5F-0708B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230102DR | 2023-07-01 15:00 | 2023-07-03 15:00 | 2023-07-10 05:30 | COMPLETE
Duri | 5F-0708C | Duri 11077 | 5F-0708C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230118DR | 2023-07-10 05:30 | 2023-07-13 | 2023-07-20 05:00 | COMPLETE
Duri | 5F-0106B | Duri 11092 | 5F-0106B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230120DR | 2023-07-20 05:00 | 2023-07-22 08:00 | 2023-07-29 11:00 | COMPLETE
Duri | 5F-1211B | Duri 11093 | 5F-1211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230077DR | 2023-07-29 11:00 | 2023-07-31 | 2023-08-07 08:00 | COMPLETE
Duri | 5F-0613B | Duri 11094 | 5F-0613B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230061DR | 2023-08-07 08:00 | 2023-08-08 22:00 | 2023-08-16 02:00 | COMPLETE
Duri | 5F-0408B | Duri 11100 | 5F-0408B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230126DR | 2023-08-16 02:00 | 2023-08-27 02:00 | 2023-09-03 06:00 | COMPLETE
Duri | 5F-1010B | Duri 11104 | 5F-1010B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230076DR | 2023-09-03 06:00 | 2023-09-04 20:00 | 2023-09-11 | COMPLETE
Duri | 5F-0808B | Duri 11103 | 5F-0808B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230103DR | 2023-09-11 | 2023-09-12 14:00 | 2023-09-18 09:00 | COMPLETE
Duri | 5G-0211B | Duri 11109 | 5G-0211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230083DR | 2023-09-18 09:00 | 2023-09-21 09:30 | 2023-09-27 10:00 | COMPLETE
Duri | 5E-1209B | Duri 11110 | 5E-1209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230117DR | 2023-09-27 10:00 | 2023-09-29 | 2023-10-04 16:00 | COMPLETE
Duri | 5F-0709B | Duri 11111 | 5F-0709B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230073DR | 2023-10-04 16:00 | 2023-10-06 03:00 | 2023-10-11 18:00 | COMPLETE
Duri | 2J-1010A | Duri 11128 | 2J-1010A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220735DR | 2023-10-11 18:00 | 2023-10-13 08:00 | 2023-10-20 12:00 | COMPLETE
Duri | 2J-1011A | Duri 11129 | 2J-1011A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220736DR | 2023-10-20 12:00 | 2023-10-21 23:00 | 2023-10-27 16:00 | COMPLETE
Duri | 2J-0912A | Duri 11137 | 2J-0912A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220741DR | 2023-10-27 16:00 | 2023-10-29 02:00 | 2023-11-04 | COMPLETE
Duri | 3J-0401A | Duri 11138 | 3J-0401A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220768DR | 2023-11-04 | 2023-11-05 17:00 | 2023-11-12 08:00 | COMPLETE
Duri | 2J-0810A | Duri 11148 | 2J-0810A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220743DR | 2023-11-12 08:00 | 2023-11-14 | 2023-11-22 01:30 | COMPLETE
Duri | 2J-0913A | Duri 11149 | 2J-0913A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220738DR | 2023-11-22 01:30 | 2023-11-24 01:00 | 2023-12-02 13:00 | COMPLETE
Duri | 2H-1113A | Duri 11150 | 2H-1113A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220782DR | 2023-12-02 13:00 | 2023-12-05 08:00 | 2023-12-11 22:00 | COMPLETE
Duri | 3J-0601A | Duri 11156 | 3J-0601A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220756DR | 2023-12-11 22:00 | 2023-12-14 14:00 | 2023-12-20 05:00 | COMPLETE
Duri | 2J-0512A | Duri 11164 | 2J-0512A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220761DR | 2023-12-20 05:00 | 2023-12-26 12:00 | 2024-01-04 15:00 | COMPLETE
Duri | 2J-0513A | Duri 11165 | 2J-0513A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220753DR | 2024-01-04 15:00 | 2024-01-16 17:00 | 2024-01-24 16:00 | COMPLETE
Duri | 2J-0813A | Duri 11171 | 2J-0813A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220740DR | 2024-01-24 16:00 | 2024-01-29 16:00 | 2024-02-04 11:00 | COMPLETE
Duri | 2J-0411A | Duri 11172 | 2J-0411A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220764DR | 2024-02-04 11:00 | 2024-02-06 | 2024-02-11 19:00 | COMPLETE
Duri | 2J-0310A | Duri 11185 | 2J-0310A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220769DR | 2024-02-11 19:00 | 2024-02-13 06:30 | 2024-02-19 07:00 | COMPLETE
Duri | 2H-1110A | Duri 11187 | 2H-1110A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220789DR | 2024-02-19 07:00 | 2024-02-22 16:00 | 2024-02-29 02:00 | COMPLETE
Duri | 2J-0110A | Duri 11188 | 2J-0110A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220767DR | 2024-02-29 02:00 | 2024-03-01 14:00 | 2024-03-07 09:00 | COMPLETE
Duri | 3H-1001A | Duri 11196 | 3H-1001A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220794DR | 2024-03-07 08:30 | 2024-03-08 21:00 | 2024-03-14 13:00 | COMPLETE
Duri | 3H-1102A | Duri 11189 | 3H-1102A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220788DR | 2024-03-14 13:00 | 2024-03-16 06:00 | 2024-03-22 03:00 | COMPLETE
Duri | 2J-0213A | Duri 11206 | 2J-0213A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220783DR | 2024-03-22 03:00 | 2024-03-23 14:00 | 2024-03-29 02:00 | COMPLETE
Duri | 2J-0210A | Duri 11209 | 2J-0210A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220778DR | 2024-03-29 02:00 | 2024-03-30 13:00 | 2024-04-05 12:00 | COMPLETE
Duri | 2H-1013A | Duri 11212 | 2H-1013A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHO2/402/2220791DR | 2024-04-05 12:00 | 2024-04-07 12:00 | 2024-04-14 07:00 | COMPLETE
Duri | 5G-0208B | Duri 11067 | 5G-0208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230123DR | 2024-04-14 07:00 | 2024-04-16 21:00 | 2024-04-25 16:30 | COMPLETE
Duri | 5G-0108C | Duri 11215 | 5G-0108C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240040DR | 2024-04-25 16:30 | 2024-04-27 07:00 | 2024-05-04 | COMPLETE
Duri | 6G-0901C | Duri 11218 | 6G-0901C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240051DR | 2024-05-04 | 2024-05-05 13:00 | 2024-05-12 | COMPLETE
Duri | 5F-1208B | Duri 11226 | 5F-1208B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2230131DR | 2024-05-12 | 2024-05-13 23:30 | 2024-05-21 10:00 | COMPLETE
Duri | 5G-0313C | Duri 11229 | 5G-0313C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240083DR | 2024-05-21 10:00 | 2024-05-23 11:00 | 2024-05-29 23:00 | COMPLETE
Duri | 5G-0313B | Duri 11232 | 5G-0313B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240063DR | 2024-05-29 23:00 | 2024-05-31 08:00 | 2024-06-06 | COMPLETE
Duri | 3S-67B | Duri 11236 | 3S-67B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240081DR | 2024-06-06 | 2024-06-08 06:30 | 2024-06-15 10:00 | COMPLETE
Duri | 5N-56F | Duri 11240 | 5N-56F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240082DR | 2024-06-15 10:00 | 2024-06-17 20:00 | 2024-06-25 | COMPLETE
Duri | 5E-1211B | Duri 11243 | 5E-1211B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240055DR | 2024-06-25 | 2024-06-26 22:00 | 2024-07-03 12:00 | COMPLETE
Duri | 5F-0209B | Duri 11244 | 5F-0209B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240890DR | 2024-07-03 12:00 | 2024-07-05 02:00 | 2024-07-11 05:00 | COMPLETE
Duri | 4E-0610A | Duri 11248 | 4E-0610A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | ARJ-02 | RHT2/402/2240052DR | 2024-07-11 05:00 | 2024-07-13 12:00 |  | IN_PROGRESS
Sikladi | SKL23_P05 | Sikladi 00030 | N1-O-14A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220925DR | 2023-06-10 | 2023-06-11 06:00 | 2023-06-21 02:00 | COMPLETE
Ubi | UBI-X11 | Ubi 00053 | N3-O-34A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220919DR | 2023-07-20 10:30 | 2023-07-23 01:00 | 2023-08-01 | COMPLETE
Sikladi | SKL23_P04 | Sikladi 00035 | N1-O-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-06 | SSA2/402/3220923DR | 2023-10-01 19:30 | 2023-10-04 21:30 | 2023-10-14 | COMPLETE
Benar | BNR-X05 | Benar 00060 | N2-0-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSO2/402/3220355DR | 2022-11-23 13:00 | 2022-12-04 07:30 | 2022-12-24 20:00 | COMPLETE
Ubi | UBI-X05 | Ubi 00052 | N4-O-84C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSA2/402/3220918DR | 2023-06-02 16:00 | 2023-06-04 11:30 | 2023-06-13 05:00 | COMPLETE
Menggala No | MNO-P26 | Menggala No 00065 | N4-W2-36A | Perforation Initial | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSM2/402/3230209DR | 2023-09-22 13:00 | 2023-09-23 21:30 | 2023-10-11 | COMPLETE
Ubi | UBI-X13 | Ubi 00054 | N1-W1-18A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-07 | SSA2/402/3220920DR | 2023-10-23 18:30 | 2023-10-26 01:30 | 2023-11-01 22:30 | COMPLETE
Petani | PETA22-P12 | Petani 00194 | S1-O-88D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-08 | SSA2/402/3220908DR | 2024-04-20 10:00 | 2024-04-21 12:00 | 2024-04-28 15:00 | COMPLETE
Balam So | BLSO-P46 | Balam So 00502 | N1-O-73B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-12 | SSO2/402/3220341DR | 2023-01-14 21:30 | 2023-01-16 23:00 | 2023-01-22 17:30 | COMPLETE
Balam So | BLSO-P25 | Balam So 00458 | N1-W1-67B | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ARJ-15 | GRK2/402/2220019DR | 2022-08-24 17:00 | 2022-08-26 11:00 | 2022-08-31 20:00 | COMPLETE
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Perforation | PRF01 - Regular Perforation | Land Workover Unit | ARJ-15 | GRK2/402/2220010DR | 2022-10-05 23:30 | 2022-10-07 03:00 | 2022-10-13 19:30 | COMPLETE
Balam So | BLSO-P41 | Balam So 00485 | O-W1-15G | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220317DR | 2022-10-13 19:30 | 2022-10-17 11:00 | 2022-10-30 19:00 | COMPLETE
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | ARJ-15 | GRK2/402/2220028DR | 2022-11-04 22:00 | 2022-11-05 18:00 | 2022-11-10 20:30 | COMPLETE
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220351DR | 2022-11-15 21:30 | 2022-11-24 21:30 | 2022-11-27 08:00 | COMPLETE
Balam So | BLSO-P21 | Balam So 00463 | O-W1-18B | Perforation | PRF01 - Regular Perforation | Land Workover Unit | ARJ-15 | GRK2/402/2220011DR | 2023-01-28 21:30 | 2023-01-29 23:00 | 2023-02-01 21:00 | COMPLETE
Balam Se | P_BLSE23_P02_MN | Balam Se 00031 | O-O-32C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSO2/402/3220581DR | 2023-12-22 18:00 | 2023-12-27 07:00 | 2024-01-03 17:30 | COMPLETE
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | ARJ-15 | SSE2/402/3230314DR | 2024-01-22 19:00 | 2024-01-24 23:00 | 2024-01-31 16:00 | COMPLETE
Minas | MNA-P7 | Minas 01993 | 8E-61N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | GRK2/402/3220202DR | 2022-06-06 08:00 | 2022-06-06 16:00 | 2022-06-11 14:30 | COMPLETE
Minas | P_6C-28E | Minas 02008 | 6C-28E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | GRK2/402/3220230DR | 2022-08-06 21:00 | 2022-08-07 02:30 | 2022-08-11 | COMPLETE
Minas | MNS-P07 | Minas 02045 | 9D-79N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220632DR | 2023-04-18 17:00 | 2023-04-19 06:00 | 2023-04-24 06:00 | COMPLETE
Minas | P_5E-96N | Minas 02052 | 5E-96N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220636DR | 2023-05-19 09:00 | 2023-05-19 22:00 | 2023-05-25 07:00 | COMPLETE
Minas | P_4D-38E | Minas 02070 | 4D-38E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220640DR | 2023-08-01 11:00 | 2023-08-01 23:00 | 2023-08-14 | COMPLETE
Minas | P_3D-33E | Minas 02072 | 3D-33E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-05 | SSO2/402/3220638DR | 2023-08-14 | 2023-08-14 11:00 | 2023-08-20 05:00 | COMPLETE
Minas | MNS-P10 | Minas 01992 | 8E-83E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | GRK2/402/3210108DR | 2022-04-21 08:00 | 2022-04-21 20:00 | 2022-04-27 10:00 | COMPLETE
Minas | MNS-P06 | Minas 01998 | 7E-56N | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | AU-06 | GRK2/402/3220213DR | 2022-06-09 22:30 | 2022-06-10 17:30 | 2022-06-11 05:00 | COMPLETE
Minas | P_6E-73E | Minas 02016 | 6E-73E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | GRK2/402/3220223DR | 2022-08-23 06:00 | 2022-08-23 16:00 | 2022-08-29 22:30 | COMPLETE
Minas | P_7C-16N | Minas 02055 | 7C-16N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSO2/402/3220644DR | 2023-05-11 23:00 | 2023-05-12 08:00 | 2023-05-21 14:00 | COMPLETE
Minas | P_5E-64N | Minas 02071 | 5E-64N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230230DR | 2023-08-04 | 2023-08-04 10:00 | 2023-08-07 14:00 | COMPLETE
Minas | P_3D-12N | Minas 02099 | 3D-12N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230229DR | 2023-11-23 11:00 | 2023-11-24 07:30 | 2023-11-29 02:30 | COMPLETE
Minas | P_MINA24_6E-58N | Minas 02102 | 6E-58N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230497DR | 2024-01-22 | 2024-01-25 09:30 | 2024-01-29 | COMPLETE
Minas | P_3A-92E | Minas 02109 | 3A-92E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230219DR | 2024-02-01 15:00 | 2024-02-04 19:00 | 2024-02-09 05:30 | COMPLETE
Minas | P_MINA24_5C-27N | Minas 02110 | 5C-27N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-06 | SSM2/402/3230494DR | 2024-02-21 | 2024-02-26 12:00 | 2024-03-14 08:30 | COMPLETE
Minas | P_4C-14E | Minas 02029 | 4C-14E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220382DR | 2023-01-03 19:00 | 2023-01-04 01:30 | 2023-01-15 22:00 | COMPLETE
Minas | P_4C-25N2 | Minas 02047 | 4C-25N2 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220430DR | 2023-05-15 05:00 | 2023-05-15 13:00 | 2023-05-22 | COMPLETE
Minas | P_6D-64N | Minas 02061 | 6D-64N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220652DR | 2023-06-17 16:00 | 2023-06-18 01:30 | 2023-06-22 15:30 | COMPLETE
Minas | P_5D-14E1 | Minas 02077 | 5D-14E1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220648DR | 2023-09-05 20:00 | 2023-09-06 05:00 | 2023-09-10 05:00 | COMPLETE
Minas | P_3B-34 | Minas 02082 | 3B-34 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220433DR | 2023-09-23 18:30 | 2023-09-24 05:30 | 2023-09-27 08:30 | COMPLETE
Minas | Minas P03 | Minas 02097 | 8D-43N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | SSO2/402/3220458DR | 2023-11-22 07:00 | 2023-11-22 15:00 | 2023-11-27 16:00 | COMPLETE
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | MBS2/402/3230833EX | 2024-06-17 | 2024-05-16 | 2024-06-18 17:00 | COMPLETE
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | AU-08 | MBS2/402/3230833EX | 2024-07-03 11:30 | 2024-05-16 | 2024-07-06 02:30 | COMPLETE
Duri | 3L-18D | Duri 11131 | 3L-18D | Pump Repair | PMP27 - Rod Pump-Bump Down Job | Mast Unit | BDJ-01 | RHT2/402/2230110DR | 2024-02-05 10:15 |  | 2024-02-05 11:30 | COMPLETE
Duri | 4H-54C | Duri 11200 | 4H-54C | Pump Repair | PMP27 - Rod Pump-Bump Down Job | Mast Unit | BDJ-01 | RHT2/402/2240033DR | 2024-05-31 10:30 |  | 2024-05-31 12:00 | COMPLETE
Topaz | P_TOPA23_P03 | Topaz 00013 | O-O-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-18 | SSV2/402/3230678DR | 2024-05-31 21:30 | 2024-05-31 21:30 | 2024-07-07 20:30 | COMPLETE
Topaz | P_TOPA23_P01 | Topaz 00014 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-18 | SSV2/402/3230677DR | 2024-07-07 20:30 |  |  | IN_PROGRESS
Tilan | P_TILA24_01 | Tilan 00038 | O-O-25D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | TLA2/402/3230739DR | 2024-03-24 | 2024-03-24 | 2024-04-17 19:00 | COMPLETE
Petani | P_PETA24_26 | Petani 00205 | O-O-33D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230897DR | 2024-04-17 19:00 | 2024-04-28 | 2024-05-15 02:00 | COMPLETE
Petani | P_PETA24_29 | Petani 00206 | O-O-52D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230920DR | 2024-05-15 02:00 | 2024-05-21 12:00 | 2024-06-06 02:30 | COMPLETE
Petani | P_PETA24_30 | Petani 00208 | O-O-33E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230921DR | 2024-06-06 02:30 | 2024-06-19 13:30 | 2024-07-05 | COMPLETE
Petani | P_PETA24_28 | Petani 00212 | O-O-33F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-19 | PTO2/402/3230919DR | 2024-07-05 | 2024-07-08 18:30 |  | IN_PROGRESS
Petani | PETA24_INJ02 | Petani 00204 | O-O-74F | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | SSM2/402/3230611DR | 2024-05-13 10:00 | 2024-05-13 10:00 | 2024-05-31 16:00 | COMPLETE
Petani | P_PETA24_20 | Petani 00207 | S1-E1-42B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | PTO2/402/3230912DR | 2024-05-31 16:00 | 2024-06-10 01:00 | 2024-07-02 07:00 | COMPLETE
Petani | P_PETA24_24 | Petani 00209 | S1-E1-42C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-21 | PTO2/402/3230916DR | 2024-07-02 07:00 | 2024-07-06 16:30 |  | IN_PROGRESS
Petapahan | PETP21-P08 | Petapahan 00150 | O-E1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210145DR | 2021-09-29 20:00 | 2021-09-29 20:00 | 2021-10-12 23:00 | COMPLETE
Kotabatak | KOTA21_P_TE_B3 | Kotabatak 00460 | N1-W1-55 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210097DR | 2021-10-12 23:00 | 2021-10-19 15:00 | 2021-10-31 18:00 | COMPLETE
Kotabatak | KOTA21_P_TE_2B | Kotabatak 00461 | N1-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210099DR | 2021-10-31 18:00 | 2021-11-05 | 2021-11-17 02:30 | RELEASE
Kotabatak | KOTA21_P_TE_A2 | Kotabatak 00462 | N1-W1-59 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210095DR | 2021-11-17 02:30 | 2021-11-21 21:00 | 2021-12-01 16:00 | RELEASE
Kotabatak | KOTA21_P_TE_B1 | Kotabatak 00464 | N1-W1-60 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210096DR | 2021-12-01 16:00 | 2021-12-04 06:30 | 2021-12-15 14:00 | COMPLETE
Kotabatak | KTB-X23 | Kotabatak 00466 | S1-O-17 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3210101DR | 2021-12-15 14:00 | 2021-12-26 22:00 | 2022-01-06 | COMPLETE
Kotabatak | KTB-X27 | Kotabatak 00472 | N1-W1-27 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220167DR | 2022-01-06 | 2022-01-16 17:00 | 2022-01-27 | COMPLETE
Kotabatak | KTB-X09 | Kotabatak 00469 | N1-W1-25A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220169DR | 2022-01-27 | 2022-01-30 11:00 | 2022-02-10 | COMPLETE
Kotabatak | KTB-X21 | Kotabatak 00475 | O-O-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220164DR | 2022-02-10 | 2022-02-20 02:00 | 2022-03-06 | COMPLETE
Kotabatak | KTB-X13 | Kotabatak 00478 | O-W1-32 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220172DR | 2022-03-06 | 2022-03-14 14:00 | 2022-03-26 19:00 | COMPLETE
Kotabatak | KTB-X22 | Kotabatak 00480 | O-O-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220175DR | 2022-03-26 19:00 | 2022-04-02 08:00 | 2022-04-14 | COMPLETE
Kotabatak | KTB-X12 | Kotabatak 00482 | O-W1-12 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220171DR | 2022-04-14 | 2022-04-21 02:00 | 2022-05-03 20:00 | COMPLETE
Kotabatak | KOTA21_P_TE_8A_HZ | Kotabatak 00483 | O-E1-32 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220177DR | 2022-05-03 20:00 | 2022-05-10 01:00 | 2022-06-07 09:00 | COMPLETE
Kotabatak | KTB-X30 | Kotabatak 00484 | S1-W1-46 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220178DR | 2022-06-07 09:00 | 2022-06-14 15:00 | 2022-06-28 01:00 | COMPLETE
Kotabatak | KB_PL2 Inj | Kotabatak 00486 | O-W2-15 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/2220261DR | 2022-06-28 01:00 | 2022-07-04 14:00 | 2022-07-18 | COMPLETE
Petapahan | PETP21_HW_P05 | Petapahan 00157 | N2-W1-49B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | GRK2/402/3220269DR | 2022-07-18 | 2022-08-03 03:00 | 2022-09-26 22:00 | COMPLETE
Kotabatak | KB_PL43 | Kotabatak 00498 | N1-W2-54 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220423DR | 2022-10-09 18:00 | 2022-10-09 18:00 | 2022-10-25 18:00 | COMPLETE
Kotabatak | KB_PL37 | Kotabatak 00500 | O-O-79 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220338DR | 2022-10-24 18:00 | 2022-11-02 21:00 | 2022-11-14 14:00 | COMPLETE
Kotabatak | KB_PL32 Inj | Kotabatak 00502 | O-E1-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220370DR | 2022-11-14 14:00 | 2022-11-21 02:00 | 2022-12-05 05:00 | COMPLETE
Kotabatak | KB_PL31 | Kotabatak 00504 | O-E1-37 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220339DR | 2022-12-05 05:00 | 2022-12-12 22:00 | 2022-12-29 08:00 | COMPLETE
Kotabatak | KB_PL48 | Kotabatak 00506 | O-E1-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220369DR | 2022-12-28 08:00 | 2023-01-06 04:00 | 2023-01-20 | COMPLETE
Kotabatak | KB_PL24 Inj | Kotabatak 00508 | O-E1-59 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220402DR | 2023-01-20 | 2023-01-29 12:00 | 2023-02-24 | COMPLETE
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220360DR | 2023-02-24 | 2023-03-01 19:00 | 2023-03-28 07:00 | COMPLETE
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220380DR | 2023-03-28 07:00 | 2023-04-03 17:00 | 2023-04-19 06:30 | COMPLETE
Minas | MINA21_HW_P04 | Minas 02058 | 6E-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220631DR | 2023-04-19 06:30 | 2023-05-05 01:00 | 2023-05-26 | COMPLETE
Petapahan | PETP21_HW_P07_Ext | Petapahan 00156 | N2-W1-34B | Drill and Complete | DRL01 - Drill Hole (Re-Entry) | Land Drilling Rig | BDSI-27 | SSA2/402/3220885DR | 2023-05-26 | 2023-06-13 20:30 | 2023-08-15 18:00 | COMPLETE
Petapahan | PTP_SO_P01 | Petapahan 00165 | N2-W2-87A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3230152DR | 2023-08-15 18:00 | 2023-08-24 04:00 | 2023-09-07 09:00 | RELEASE
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSO2/402/3220629DR | 2023-09-07 09:00 | 2023-09-22 01:30 | 2023-10-24 05:00 | COMPLETE
Petapahan | PTP BL2-Z10 | Petapahan 00167 | N1-W2-28C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3220884DR | 2023-10-24 05:00 | 2023-11-03 21:30 | 2023-11-15 12:00 | RELEASE
Petapahan | PTP BL2-P20 | Petapahan 00169 | N1-W2-28B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSA2/402/3220881DR | 2023-11-15 12:00 | 2023-11-19 18:00 | 2023-12-04 20:30 | COMPLETE
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | MBS2/402/3230833EX | 2023-12-04 20:30 | 2023-12-30 21:00 | 2024-02-29 19:00 | COMPLETE
Minas | MINAHW23_P04 | Minas 02118 | 2D-85A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230252DR | 2024-02-29 19:00 | 2024-03-14 | 2024-04-09 19:00 | COMPLETE
Minas | MINAHW23_P08 | Minas 02124 | 6C-19A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230251DR | 2024-04-09 19:00 | 2024-04-20 05:00 | 2024-05-07 03:00 | COMPLETE
Minas | MINAHW23_P09 | Minas 02128 | 5D-94A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230256DR | 2024-05-07 03:00 | 2024-05-13 02:30 | 2024-05-31 13:00 | COMPLETE
Minas | MINAHW23_P16 | Minas 02131 | 3D-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-27 | SSM2/402/3230255DR | 2024-05-31 13:00 | 2024-06-24 03:00 |  | IN_PROGRESS
Petapahan | PETP21-P11 | Petapahan 00149 | O-E1-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210148DR | 2021-09-21 04:00 | 2021-09-21 04:00 | 2021-10-06 22:00 | COMPLETE
Petapahan | PETP21-P10 | Petapahan 00151 | O-E1-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210147DR | 2021-10-06 22:00 | 2021-10-20 09:30 | 2021-11-03 13:00 | COMPLETE
Petapahan | PTP-P3 | Petapahan 00153 | N2-W1-23B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210152DR | 2021-11-03 13:00 | 2021-11-09 05:00 | 2021-11-27 02:00 | COMPLETE
Petapahan | PTP-P5 | Petapahan 00154 | N2-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210156DR | 2021-11-26 02:00 | 2021-11-28 19:00 | 2021-12-14 10:30 | COMPLETE
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210149DR | 2021-12-14 10:30 | 2021-12-22 05:00 | 2022-01-05 | COMPLETE
Kotabatak | KTB-X15 | Kotabatak 00468 | O-O-53A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3210150DR | 2022-01-05 | 2022-01-13 14:15 | 2022-01-25 08:30 | COMPLETE
Kotabatak | KTB-X16 | Kotabatak 00471 | O-O-34 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220166DR | 2022-01-25 08:30 | 2022-01-31 02:00 | 2022-02-12 17:00 | COMPLETE
Kotabatak | KTB-X25 | Kotabatak 00477 | N1-O-69 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220174DR | 2022-02-12 17:00 | 2022-02-18 06:00 | 2022-03-02 | COMPLETE
Kotabatak | KTB-X28 | Kotabatak 00474 | O-W1-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220168DR | 2022-03-02 | 2022-03-09 04:00 | 2022-03-21 11:00 | COMPLETE
Petapahan | PTP-P1 | Petapahan 00155 | N2-W1-16A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220267DR | 2022-03-21 11:00 | 2022-03-28 03:00 | 2022-04-23 | COMPLETE
Minas | MNS-P12 | Minas 02000 | 8D-48N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220210DR | 2022-04-23 | 2022-05-06 02:30 | 2022-05-17 04:30 | COMPLETE
Minas | P_6D-31N | Minas 02003 | 6D-31N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220232DR | 2022-05-17 04:30 | 2022-05-25 | 2022-06-03 03:00 | COMPLETE
Minas | MINA21_HW_P02 | Minas 02005 | 8F-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220224DR | 2022-06-03 03:00 | 2022-06-12 | 2022-07-10 | COMPLETE
Petani | PETA22-P05 | Petani 00151 | O-O-43D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | GRK2/402/3220218DR | 2022-07-10 | 2022-07-25 09:00 | 2022-08-13 03:00 | COMPLETE
Petani | PETA22-P20 | Petani 00154 | S1-O-15A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSO2/402/3220508DR | 2022-08-13 03:00 | 2022-08-23 21:00 | 2022-09-13 12:00 | COMPLETE
Petani | PETA22-P18 | Petani 00159 | N1-W1-38A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PTF2/402/3220460DR | 2022-09-13 12:00 | 2022-09-20 19:30 | 2022-10-10 11:00 | COMPLETE
Petani | PETA22-P27 | Petani 00158 | O-O-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSO2/402/3220327DR | 2022-10-10 11:00 | 2022-10-20 01:30 | 2022-11-09 16:00 | COMPLETE
Kelok Ne | P_KENE_P02 | Kelok NE 00004 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | KEN2/402/3220807DR | 2022-11-09 16:00 | 2022-11-29 16:00 | 2023-01-17 05:00 | RELEASE
Sidingin North | Exp_P02_Sidingin | Sidingin North 00001 | O-O-44 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SDN2/402/2220001EX | 2023-01-17 05:00 | 2023-02-08 16:00 | 2023-04-13 08:30 | RELEASE
Pinang | P_PINA23_P11 | Pinang 00055 | N1-W1-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220842DR | 2023-04-13 18:30 | 2023-05-10 04:30 | 2023-05-25 13:00 | COMPLETE
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNA2/402/3220823DR | 2023-05-25 13:00 | 2023-05-31 17:30 | 2023-06-15 12:30 | RELEASE
Pinang | P_PINA23_HW03 | Pinang 00061 | O-W1-13A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220841DR | 2023-06-15 12:30 | 2023-06-23 | 2023-07-21 15:00 | COMPLETE
Pinang | P_PINA23_HW01 | Pinang 00063 | O-O-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220840DR | 2023-07-21 15:00 | 2023-07-31 23:45 | 2023-08-29 18:00 | COMPLETE
Pinang | P_PINA23_HW02 | Pinang 00064 | O-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PNG2/402/3220839DR | 2023-08-29 18:00 | 2023-09-06 01:30 | 2023-10-06 18:00 | COMPLETE
Pungut | PUNG23_H02 | Pungut 00053 | S2-O-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230194DR | 2023-10-12 | 2023-11-06 | 2023-11-27 12:00 | COMPLETE
Pungut | PUNG23_D03 | Pungut 00054 | S1-O-18A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230191DR | 2023-11-27 12:00 | 2023-12-06 11:00 | 2023-12-18 02:00 | COMPLETE
Pungut | PUNG23_H03 | Pungut 00055 | S1-O-18B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230198DR | 2023-12-18 02:00 | 2023-12-23 18:00 | 2024-01-27 02:00 | COMPLETE
Pungut | PUNG23_H01 | Pungut 00056 | S2-E1-54D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230196DR | 2024-01-27 02:00 | 2024-02-07 | 2024-03-03 11:00 | COMPLETE
Pungut | PUNG23_P15 | Pungut 00057 | S2-E1-54E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SSM2/402/3230201DR | 2024-03-03 11:00 | 2024-03-09 | 2024-03-22 14:00 | COMPLETE
Astrea | Astrea-1 | Astrea 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | AST2/402/3230001EX | 2024-03-22 14:00 | 2024-04-10 17:00 | 2024-05-27 | COMPLETE
Pukat | P_PUKA24_02 | Pukat 00006 | S1-O-71A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | SPS2/402/3240891DR | 2024-05-27 | 2024-06-10 | 2024-06-24 19:00 | COMPLETE
Petani | P_PETA24-P01 | Petani 00213 | N1-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-28 | PTO2/402/3230900DR | 2024-06-24 17:00 | 2024-07-11 |  | IN_PROGRESS
Kotabatak | KTB-X26 | Kotabatak 00488 | N1-W1-88 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | GRK2/402/3220188DR | 2022-07-27 | 2022-07-27 | 2022-08-10 21:00 | COMPLETE
Kotabatak | KB_PL18 Inj | Kotabatak 00491 | N1-O-76 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220507DR | 2022-08-10 21:00 | 2022-08-21 | 2022-09-01 20:00 | COMPLETE
Kotabatak | KB_PL10 Inj | Kotabatak 00492 | N1-W1-78 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220325DR | 2022-09-01 20:00 | 2022-09-09 22:00 | 2022-09-21 18:30 | COMPLETE
Kotabatak | KB_PL45 | Kotabatak 00495 | N1-W2-38 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220534DR | 2022-09-21 18:30 | 2022-09-29 09:30 | 2022-10-12 06:00 | COMPLETE
Kotabatak | KB_PL46 | Kotabatak 00497 | N1-W2-39 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220358DR | 2022-10-12 06:00 | 2022-10-17 22:00 | 2022-10-31 15:00 | COMPLETE
Petani | PETA23_P16 | Petani 00161 | S1-O-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTM2/402/3220814DR | 2022-10-31 15:00 | 2022-11-18 19:30 | 2022-12-08 11:00 | COMPLETE
Petani | PETA22-P17 | Petani 00164 | O-O-74B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTJ2/402/3220810DR | 2022-12-08 11:00 | 2022-12-15 05:00 | 2023-01-03 12:00 | COMPLETE
Pager | PG22-P01 | Pager 00053 | O-O-65B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220334DR | 2023-01-03 12:00 | 2023-01-13 09:00 | 2023-01-28 19:30 | COMPLETE
Pager | PG22-P05 | Pager 00055 | O-O-54C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220354DR | 2023-01-28 19:30 | 2023-02-04 | 2023-02-28 10:00 | COMPLETE
Pematang | PMT-P11 | Pematang 00118 | O-O-62C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSO2/402/3220391DR | 2023-02-28 10:00 | 2023-03-10 13:30 | 2023-03-30 10:15 | COMPLETE
Petani | PETA22-INJ5 | Petani 00170 | N1-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220916DR | 2023-03-30 10:15 | 2023-04-09 10:30 | 2023-05-03 17:00 | COMPLETE
Petani | PETA23_P03 | Petani 00172 | N1-O-81A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220905DR | 2023-05-03 17:00 | 2023-05-10 18:00 | 2023-05-26 22:00 | COMPLETE
Petani | PETA23_P11 | Petani 00175 | O-O-56A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230296DR | 2023-05-26 22:00 | 2023-06-02 20:00 | 2023-06-18 10:00 | COMPLETE
Petani | PETA23-P31 | Petani 00177 | O-O-56B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220915DR | 2023-06-18 10:00 | 2023-06-22 01:30 | 2023-07-09 22:00 | COMPLETE
Petani | PETA23B-P04 | Petani 00180 | O-O-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230297DR | 2023-07-09 22:00 | 2023-07-19 21:00 | 2023-08-06 11:00 | COMPLETE
Petani | PT22_P25 | Petani 00183 | O-O-74C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230295DR | 2023-08-06 11:00 | 2023-08-12 04:00 | 2023-08-26 17:00 | COMPLETE
Petani | PT22_P22 | Petani 00186 | O-O-74D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230294DR | 2023-08-26 17:00 | 2023-08-29 20:30 | 2023-09-13 14:00 | COMPLETE
Petani | PETA-BK3140-P04 | Petani 00188 | O-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220911DR | 2023-09-13 14:00 | 2023-09-20 05:00 | 2023-10-14 | COMPLETE
Petani | PETA23B-P01 | Petani 00195 | O-O-33C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220899DR | 2023-10-14 | 2023-10-19 02:00 | 2023-11-05 03:15 | COMPLETE
Petani | PETA_BK3140_P01 | Petani 00199 | O-O-52B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220909DR | 2023-11-05 03:15 | 2023-11-13 21:00 | 2023-12-09 | COMPLETE
Petani | PETA_BK3140_P03 | Petani 00200 | O-O-52C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220910DR | 2023-12-09 | 2023-12-14 12:00 | 2024-02-19 08:00 | COMPLETE
Petani | PETA22-P16 | Petani 00201 | O-O-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSM2/402/3230299DR | 2024-02-19 08:00 | 2024-02-29 22:00 | 2024-04-15 | COMPLETE
Petani | PETA22-P29 | Petani 00203 | O-O-85I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | SSA2/402/3220907DR | 2024-04-15 | 2024-04-19 02:00 | 2024-05-31 07:30 | COMPLETE
Kopar | KPR-X10_OPT | Kopar 00047 | S1-O-15B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTO2/402/3240789DR | 2024-05-31 07:30 | 2024-06-18 08:00 | 2024-07-06 10:00 | COMPLETE
Petani | P_PETA24_25 | Petani 00211 | O-O-32F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-29 | PTO2/402/3230917DR | 2024-07-06 10:00 | 2024-07-14 04:00 |  | IN_PROGRESS
Kopar | KPR-X16_OPT | Kopar 00046 | O-O-84C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BDSI-60 | PTO2/402/3240791DR | 2024-07-12 21:00 | 2024-07-12 21:00 |  | IN_PROGRESS
Hiu | P_HIU24_11 | Hiu 00010 | O-W2-52A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BDSI-61 | SPS2/402/3240900DR | 2024-07-09 03:00 | 2024-07-09 03:00 |  | IN_PROGRESS
Petani | PETA22-P24 | Petani 00153 | O-W1-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-87 | GRK2/402/2220257DR | 2022-10-13 09:00 | 2022-10-17 04:00 | 2022-10-24 20:00 | COMPLETE
Petani | PTN-X06 | Petani 00145 | O-O-43C | Perforation | PRF01 - Regular Perforation | Land Workover Unit | BDSI-87 | GRK2/402/2220249DR | 2022-11-23 04:00 | 2022-11-25 20:00 | 2022-12-02 15:00 | COMPLETE
Petani | PETA23B-P01 | Petani 00195 | O-O-33C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-87 | SSA2/402/3220899DR | 2023-11-26 13:30 | 2023-11-27 21:30 | 2023-12-06 06:30 | COMPLETE
Petani | PETA22-INJ3 | Petani 00189 | S1-O-15C | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BDSI-87 | SSA2/402/3220917DR | 2024-07-04 13:30 | 2024-07-05 05:30 | 2024-07-11 08:00 | COMPLETE
Minas | P_6C-21N | Minas 02018 | 6C-21N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220514DR | 2022-09-25 11:00 | 2022-09-30 20:30 | 2022-10-07 10:30 | COMPLETE
Minas | MNS-P03 | Minas 02014 | 9C-66 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220510DR | 2022-11-20 13:00 | 2022-11-22 02:00 | 2022-11-29 | COMPLETE
Minas | P_7E-94E1 | Minas 02035 | 7E-94E1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-90 | SSO2/402/3220378DR | 2023-03-29 | 2023-03-30 15:00 | 2023-04-04 11:00 | COMPLETE
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Pump Repair | PMP05 - Rod Pump Not Pumping Normal | Land Workover Unit | BDSI-94 | SSO2/402/3220373DR | 2022-12-31 18:00 | 2023-01-02 12:00 | 2023-01-05 | COMPLETE
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BDSI-94 | SSE2/402/3230314DR | 2024-04-09 10:30 | 2024-04-12 | 2024-04-16 | COMPLETE
Kotabatak | KOTA21_P_TE_2A | Kotabatak 00457 | N1-W1-42A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210100DR | 2021-10-12 06:00 | 2021-10-12 13:00 | 2021-10-19 | COMPLETE
Kotabatak | KOTA21_P_TE_INJ_1 | Kotabatak 00458 | N1-W1-46A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | GRK2/402/3210102DR | 2021-10-28 | 2021-10-28 12:00 | 2021-11-24 | COMPLETE
Kotabatak | KOTA21_P_TE_B2 | Kotabatak 00459 | N1-W1-84E | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210098DR | 2021-11-24 | 2021-11-26 22:00 | 2021-12-09 | COMPLETE
Kotabatak | KOTA21_P_TE_B3 | Kotabatak 00460 | N1-W1-55 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210097DR | 2021-12-09 | 2021-12-10 05:00 | 2021-12-17 18:00 | COMPLETE
Kotabatak | KOTA21_P_TE_2B | Kotabatak 00461 | N1-W1-46B | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210099DR | 2021-12-17 18:00 | 2021-12-18 17:30 | 2021-12-26 20:00 | COMPLETE
Kotabatak | KTB-P2 | Kotabatak 00463 | S1-E1-72 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210104DR | 2022-01-07 | 2022-01-07 08:00 | 2022-01-18 11:00 | COMPLETE
Kotabatak | KTB-X04 | Kotabatak 00467 | N1-O-73A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/2210131DR | 2022-01-22 08:00 | 2022-01-22 14:30 | 2022-01-28 19:00 | COMPLETE
Kotabatak | KOTA21_P_TE_A2 | Kotabatak 00462 | N1-W1-59 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210095DR | 2022-02-08 11:00 | 2022-02-08 21:00 | 2022-02-16 11:00 | COMPLETE
Kotabatak | KOTA21_P_TE_B1 | Kotabatak 00464 | N1-W1-60 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210096DR | 2022-02-16 11:00 | 2022-02-17 08:00 | 2022-02-28 11:00 | COMPLETE
Kotabatak | KTB-X15 | Kotabatak 00468 | O-O-53A | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3210150DR | 2022-02-28 11:00 | 2022-03-01 19:00 | 2022-03-07 18:00 | COMPLETE
Kotabatak | KTB-X16 | Kotabatak 00471 | O-O-34 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3220166DR | 2022-03-21 09:00 | 2022-03-21 17:00 | 2022-03-29 19:00 | COMPLETE
Kotabatak | KTB-X21 | Kotabatak 00475 | O-O-76 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220164DR | 2022-04-30 19:00 | 2022-05-01 01:00 | 2022-05-07 12:00 | COMPLETE
Kotabatak | KTB-X27 | Kotabatak 00472 | N1-W1-27 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220167DR | 2022-05-20 07:00 | 2022-05-20 19:00 | 2022-05-26 20:00 | COMPLETE
Kotabatak | KTB-X22 | Kotabatak 00480 | O-O-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220175DR | 2022-06-12 19:00 | 2022-06-13 03:00 | 2022-06-19 09:00 | COMPLETE
Kotabatak | KTB-X18 | Kotabatak 00470 | O-O-13 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-02 | GRK2/402/3220165DR | 2022-06-23 10:00 | 2022-06-23 20:00 | 2022-06-30 02:30 | COMPLETE
Kotabatak | KTB-X13 | Kotabatak 00478 | O-W1-32 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220172DR | 2022-06-30 02:30 | 2022-06-30 09:00 | 2022-07-07 14:00 | COMPLETE
Kotabatak | KTB-X12 | Kotabatak 00482 | O-W1-12 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220171DR | 2022-07-07 14:00 | 2022-07-07 22:30 | 2022-07-14 14:30 | COMPLETE
Kotabatak | KTB-X07 | Kotabatak 00481 | N1-W1-34 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220176DR | 2022-07-28 | 2022-07-28 14:00 | 2022-08-09 17:00 | COMPLETE
Kotabatak | KTB-X25 | Kotabatak 00477 | N1-O-69 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220174DR | 2022-08-11 11:00 | 2022-08-11 20:00 | 2022-08-19 20:30 | COMPLETE
Kotabatak | KTB-X28 | Kotabatak 00474 | O-W1-63 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220168DR | 2022-08-19 20:30 | 2022-08-20 07:00 | 2022-08-28 19:00 | COMPLETE
Kotabatak | KB_PL10 Inj | Kotabatak 00492 | N1-W1-78 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220325DR | 2022-10-17 16:00 | 2022-10-17 23:00 | 2022-10-27 08:30 | COMPLETE
Kotabatak | KTB-X17 | Kotabatak 00485 | O-O-39 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220180DR | 2022-10-27 08:30 | 2022-10-27 21:30 | 2022-11-08 09:30 | COMPLETE
Kotabatak | KTB-X08 | Kotabatak 00493 | N1-W2-59 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220513DR | 2022-11-08 09:30 | 2022-11-09 03:00 | 2022-11-16 02:00 | COMPLETE
Kotabatak | KTB-X02 | Kotabatak 00489 | N1-E1-73 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/3220182DR | 2022-11-16 02:00 | 2022-11-17 02:30 | 2022-11-27 15:00 | COMPLETE
Kotabatak | KB_PL4 | Kotabatak 00487 | O-W2-17 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | GRK2/402/2220253DR | 2022-11-27 15:00 | 2022-11-27 22:00 | 2022-12-05 04:00 | COMPLETE
Kotabatak | KB_PL18 Inj | Kotabatak 00491 | N1-O-76 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220507DR | 2022-12-10 10:30 | 2022-12-12 14:00 | 2022-12-20 21:30 | COMPLETE
Kotabatak | KB_PL19 | Kotabatak 00499 | S1-O-19 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220367DR | 2022-12-20 21:30 | 2022-12-21 13:00 | 2022-12-31 18:00 | COMPLETE
Kotabatak | KB_PL45 | Kotabatak 00495 | N1-W2-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220534DR | 2022-12-31 18:00 | 2023-01-02 17:00 | 2023-01-11 17:00 | COMPLETE
Kotabatak | KB_PL32 Inj | Kotabatak 00502 | O-E1-34 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220370DR | 2023-01-11 17:00 | 2023-01-12 09:30 | 2023-01-21 12:00 | COMPLETE
Kotabatak | KB_PL43 | Kotabatak 00498 | N1-W2-54 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220423DR | 2023-01-21 12:00 | 2023-01-24 05:30 | 2023-02-01 | COMPLETE
Kotabatak | KB_PL47 Inj | Kotabatak 00501 | N1-W2-36 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220537DR | 2023-02-01 | 2023-02-01 08:00 | 2023-02-20 05:00 | COMPLETE
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220522DR | 2023-02-23 | 2023-02-23 18:00 | 2023-02-27 05:00 | COMPLETE
Kotabatak | KB_PL12 | Kotabatak 00496 | S1-O-22 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220345DR | 2023-05-04 18:00 | 2023-05-05 04:00 | 2023-05-12 18:00 | COMPLETE
Kotabatak | KB_PL37 | Kotabatak 00500 | O-O-79 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220338DR | 2023-05-12 18:00 | 2023-05-13 07:00 | 2023-05-23 | COMPLETE
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220360DR | 2023-06-02 | 2023-06-02 10:00 | 2023-06-05 10:00 | COMPLETE
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220625DR | 2023-06-05 10:00 | 2023-06-06 11:00 | 2023-06-09 09:00 | COMPLETE
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220627DR | 2023-06-09 09:00 | 2023-06-09 20:00 | 2023-06-12 21:00 | COMPLETE
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230384DR | 2023-06-12 21:00 | 2023-06-13 02:00 | 2023-06-16 | COMPLETE
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230386DR | 2023-06-16 | 2023-06-16 05:00 | 2023-06-18 11:00 | COMPLETE
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220624DR | 2023-06-18 11:00 | 2023-06-19 01:00 | 2023-06-21 04:00 | COMPLETE
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220380DR | 2023-06-21 04:00 | 2023-06-21 12:00 | 2023-06-24 13:00 | COMPLETE
Kotabatak | KB_PL23 | Kotabatak 00512 | O-E1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220624DR | 2023-07-16 | 2023-06-19 01:00 | 2023-07-22 18:00 | COMPLETE
Kotabatak | KTB-A271 | Kotabatak 00514 | S1-E1-12 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230385DR | 2023-07-22 18:00 | 2023-07-23 03:00 | 2023-07-30 | COMPLETE
Kotabatak | KTB-A128 | Kotabatak 00524 | S1-E1-18 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230383DR | 2023-07-30 | 2023-07-31 | 2023-08-08 | COMPLETE
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220628DR | 2023-09-02 | 2023-09-02 08:00 | 2023-09-05 03:00 | COMPLETE
Kotabatak | KTB-X35-INJ | Kotabatak 00533 | N1-O-88 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220455DR | 2023-09-05 03:00 | 2023-09-05 12:00 | 2023-09-13 02:30 | COMPLETE
Kotabatak | KTB-X01 | Kotabatak 00534 | N1-E1-71 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220628DR | 2023-09-13 02:30 | 2023-09-02 08:00 | 2023-09-18 20:00 | COMPLETE
Kotabatak | KTB-X33-INJ | Kotabatak 00530 | O-W2-29 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230382DR | 2023-09-18 20:00 | 2023-09-19 08:00 | 2023-09-25 12:00 | COMPLETE
Kotabatak | KB_PL34 | Kotabatak 00531 | O-W1-13 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230392DR | 2023-09-25 12:00 | 2023-09-25 20:00 | 2023-10-02 12:00 | COMPLETE
Kotabatak | KTB-X34-INJ | Kotabatak 00532 | O-W1-20 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230389DR | 2023-10-02 12:00 | 2023-10-03 02:00 | 2023-10-09 12:00 | COMPLETE
Kotabatak | KTB-X37-INJ | Kotabatak 00528 | S1-W1-47 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230396DR | 2023-10-09 12:00 | 2023-10-10 | 2023-10-17 | COMPLETE
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2023-10-26 | 2023-10-26 12:00 | 2023-10-29 16:00 | COMPLETE
Kotabatak | KB_PL39 | Kotabatak 00521 | N1-W1-63 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220393DR | 2023-10-29 16:00 | 2023-10-31 20:00 | 2023-11-06 14:00 | COMPLETE
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Remedial Liner | RLN06 - Install Liner-Cementing | Land Workover Unit | BMS-02 | SSO2/402/3220629DR | 2023-11-06 14:00 | 2023-11-07 01:30 | 2023-11-18 04:00 | COMPLETE
Kotabatak | KTB-X24 | Kotabatak 00539 | N1-W2-78 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230426DR | 2023-11-18 04:00 | 2023-11-18 20:00 | 2023-11-27 18:00 | COMPLETE
Kotabatak | KB_PL3 | Kotabatak 00540 | O-W2-25 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230420DR | 2024-01-08 08:00 | 2024-01-10 17:00 | 2024-01-26 18:00 | COMPLETE
Kotabatak | KB_PL44 | Kotabatak 00520 | N1-W1-41 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220392DR | 2024-02-02 06:00 | 2024-02-02 17:00 | 2024-02-10 | COMPLETE
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2024-02-10 | 2023-10-26 12:00 | 2024-02-15 09:00 | COMPLETE
Kotabatak | KB_PL33 Inj | Kotabatak 00522 | N1-W1-64 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSO2/402/3220424DR | 2024-02-15 09:00 | 2024-02-18 01:00 | 2024-02-26 11:00 | COMPLETE
Kotabatak | KB_PL38 | Kotabatak 00542 | O-O-73 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230429DR | 2024-02-26 11:00 | 2024-02-27 15:00 | 2024-03-05 12:00 | COMPLETE
Kotabatak | KB_PL41 | Kotabatak 00545 | O-E1-80 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230410DR | 2024-03-05 12:00 | 2024-03-06 03:00 | 2024-03-15 | COMPLETE
Kotabatak | KTB-A223 | Kotabatak 00544 | O-E1-51 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230412DR | 2024-03-15 | 2024-03-16 | 2024-03-23 12:00 | COMPLETE
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Logging | LOG14 - Run Temperature And CBL/ USIT Log | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-03-23 12:00 |  |  | SUSPENDED
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-03-23 12:00 | 2024-03-24 08:00 | 2024-03-26 10:00 | COMPLETE
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230394DR | 2024-03-26 10:00 | 2024-04-09 13:00 | 2024-03-29 10:00 | COMPLETE
Kotabatak | KB_PL20 | Kotabatak 00541 | O-O-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSE2/402/3230394DR | 2024-04-09 04:00 | 2024-04-09 13:00 | 2024-04-15 19:00 | COMPLETE
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SSE2/402/3230397DR | 2024-04-15 19:00 | 2024-03-24 08:00 | 2024-04-23 19:00 | COMPLETE
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Land Workover Unit | BMS-02 | SSO2/402/3220629DR | 2024-05-05 15:00 | 2024-04-18 22:00 | 2024-05-09 08:00 | IN_PROGRESS
Kotabatak | KTB-A268_INJ | Kotabatak 00553 | N1-W1-15B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SKB2/402/3230438DR | 2024-06-05 22:00 | 2024-06-06 08:00 | 2024-06-13 12:00 | COMPLETE
Kotabatak | KTB-A125 | Kotabatak 00554 | O-E1-79 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230421DR | 2024-06-13 12:00 | 2024-06-14 | 2024-06-22 12:00 | COMPLETE
Kotabatak | KTB-A207_INJ | Kotabatak 00555 | O-E1-78 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-02 | SKB2/402/3230436DR | 2024-06-22 12:00 | 2024-06-23 16:30 | 2024-07-01 04:00 | COMPLETE
Kotabatak | KTB-X10 | Kotabatak 00523 | N1-W1-65 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SSO2/402/3220623DR | 2024-07-01 04:00 | 2023-10-26 12:00 | 2024-07-12 13:00 | COMPLETE
Kotabatak | KTB-A023 | Kotabatak 00546 | O-W1-55 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-02 | SKB2/402/3230418DR | 2024-07-12 13:00 | 2024-07-12 23:00 |  | IN_PROGRESS
Petapahan | PTP BL2-P19 | Petapahan 00162 | N1-W1-64A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSO2/402/3220660DR | 2023-02-25 10:00 | 2023-02-25 22:00 | 2023-03-01 | COMPLETE
Petapahan | PTP_SO_P01 | Petapahan 00165 | N2-W2-87A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSA2/402/3230152DR | 2023-09-22 03:00 | 2023-09-22 21:00 | 2023-10-01 11:00 | COMPLETE
Petapahan | PTP BL2-Z10 | Petapahan 00167 | N1-W2-28C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSA2/402/3220884DR | 2024-03-24 | 2024-03-24 19:00 | 2024-04-04 18:00 | COMPLETE
Petapahan | PTP BL2-Z09 | Petapahan 00172 | N1-W1-44E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-03 | SSO2/402/3220411DR | 2024-06-18 12:00 | 2024-06-19 10:00 | 2024-06-29 17:00 | COMPLETE
Pemburu | PEMB21-P07 | Pemburu 00036 | O-O-65E | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-05 | GRK2/402/2210123DR | 2021-11-15 22:30 | 2021-11-16 08:00 | 2021-11-16 16:30 | COMPLETE
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220372DR | 2023-09-21 | 2023-09-21 20:30 | 2023-09-23 07:30 | COMPLETE
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220372DR | 2023-10-20 21:30 | 2023-09-21 20:30 | 2023-10-25 07:30 | COMPLETE
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220554DR | 2023-10-28 13:30 | 2023-10-29 19:00 | 2023-11-01 04:30 | COMPLETE
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220554DR | 2023-11-11 06:00 | 2023-10-29 19:00 | 2023-11-14 19:00 | COMPLETE
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220588DR | 2023-11-14 19:00 | 2023-11-15 21:00 | 2023-11-18 10:30 | COMPLETE
Bangko | WFE-BNK_5 | Bangko 00423 | N2-W1-51A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-05 | SSM2/402/3230286DR | 2024-02-25 04:30 | 2024-02-25 22:00 | 2024-02-28 21:00 | COMPLETE
Bangko | WFE-BNK_4 | Bangko 00429 | O-O-33B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-05 | SSM2/402/3230284DR | 2024-03-24 17:30 | 2024-03-25 15:30 | 2024-03-28 16:30 | COMPLETE
Bangko | BNK23_P24 | Bangko 00427 | N1-W2-54B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSM2/402/3230274DR | 2024-04-05 08:30 | 2024-04-06 01:00 | 2024-04-10 05:00 | COMPLETE
Bangko | BNK23_P08 | Bangko 00430 | O-O-52B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSM2/402/3230275DR | 2024-04-12 02:00 | 2024-04-12 21:00 | 2024-04-28 08:30 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220383DR | 2024-06-09 19:00 | 2024-06-10 17:00 | 2024-06-12 17:00 | IN_PROGRESS
Bangko | BNK_P244A_LQR | Bangko 00414 | N1-W3-41A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220398DR | 2024-06-14 22:00 | 2024-06-15 22:00 | 2024-06-19 06:30 | COMPLETE
Bangko | BNK_P277B_LQR | Bangko 00409 | N1-W4-18A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220366DR | 2024-06-21 22:00 | 2024-06-23 05:00 | 2024-07-10 16:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-05 | SSO2/402/3220383DR | 2024-07-10 16:00 | 2024-06-10 17:00 |  | IN_PROGRESS
Bekasap | BKS-P16 | Bekasap 00208 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2210017DR | 2022-01-21 17:30 | 2022-01-22 20:00 | 2022-02-04 10:30 | COMPLETE
Petani | PTN-P1 | Petani 00134 | N1-W1-57A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Land Workover Unit | BMS-06 | GRK2/402/2210141DR | 2022-02-03 12:00 |  |  | SUSPENDED
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2210018DR | 2022-02-10 | 2022-02-12 | 2022-02-16 | COMPLETE
Bekasap | BKS-X10 | Bekasap 00218 | O-E1-43B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-06 | GRK2/402/2220286DR | 2022-06-04 11:00 | 2022-06-04 23:00 | 2022-06-05 11:00 | COMPLETE
Bekasap | BKS-X14 | Bekasap 00220 | O-E1-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-06 | GRK2/402/2220275DR | 2022-09-10 12:00 | 2022-09-11 02:00 | 2022-09-26 | COMPLETE
Pematang | PMT-P05 | Pematang 00111 | O-O-53A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-07 | SSO2/402/3220364DR | 2022-12-14 07:00 | 2022-12-17 17:30 | 2023-01-03 | COMPLETE
Sidingin North | Exp_P02_Sidingin | Sidingin North 00001 | O-O-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-07 | SDN2/402/2220001EX | 2023-07-31 20:00 | 2023-08-06 11:00 | 2023-10-02 14:30 | COMPLETE
Astrea | Astrea-1 | Astrea 00001 | O-O-44 | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-07 | AST2/402/3230001EX | 2024-06-25 12:00 | 2024-06-30 02:00 |  | IN_PROGRESS
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210149DR | 2022-02-15 09:00 | 2022-02-15 20:30 | 2022-02-23 | COMPLETE
Kotabatak | KTB-X14 | Kotabatak 00465 | O-W2-10 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210149DR | 2022-03-18 22:00 | 2022-02-15 20:30 | 2022-03-25 07:00 | COMPLETE
Kotabatak | KTB-X23 | Kotabatak 00466 | S1-O-17 | Complete | COM01 - Initial Completion (SMF well) | Land Workover Unit | BMS-08 | GRK2/402/3210101DR | 2022-03-25 07:00 | 2022-03-25 12:30 | 2022-04-02 12:00 | COMPLETE
Kotabatak | KTB-X05 | Kotabatak 00476 | O-O-18 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220173DR | 2022-04-02 12:00 | 2022-04-02 23:00 | 2022-04-14 04:00 | COMPLETE
Kotabatak | KTB-X03 | Kotabatak 00473 | N1-O-32A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3210103DR | 2022-06-14 14:00 | 2022-06-14 22:00 | 2022-06-23 20:00 | COMPLETE
Kotabatak | KTB-X09 | Kotabatak 00469 | N1-W1-25A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220169DR | 2022-07-18 09:00 | 2022-07-18 23:00 | 2022-07-25 22:00 | COMPLETE
Kotabatak | KTB-X06 | Kotabatak 00479 | S1-O-12A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220170DR | 2022-07-25 22:00 | 2022-07-26 22:00 | 2022-08-05 14:00 | COMPLETE
Kotabatak | KTB-X30 | Kotabatak 00484 | S1-W1-46 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | GRK2/402/3220178DR | 2022-08-06 15:30 | 2022-08-06 15:30 | 2022-08-17 21:00 | COMPLETE
Kotabatak | KB_PL2 Inj | Kotabatak 00486 | O-W2-15 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-08 | GRK2/402/2220261DR | 2022-08-26 09:00 | 2022-08-26 17:00 | 2022-09-03 | COMPLETE
Kotabatak | KB_PL5 Inj | Kotabatak 00490 | N1-W2-76 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-08 | GRK2/402/3220191DR | 2022-09-28 20:00 | 2022-09-29 05:00 | 2022-10-10 08:00 | COMPLETE
Minas | P_6D-53N | Minas 02033 | 6D-53N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220350DR | 2023-01-31 03:30 | 2023-02-01 02:30 | 2023-02-07 06:00 | COMPLETE
Minas | P_6C-89E | Minas 02034 | 6C-89E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220387DR | 2023-03-03 05:00 | 2023-03-06 00:30 | 2023-03-10 17:30 | COMPLETE
Minas | P_7E-14 | Minas 02041 | 7E-14 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220637DR | 2023-03-27 10:30 | 2023-03-28 14:00 | 2023-04-10 | COMPLETE
Minas | P_10C-26 | Minas 02050 | 10C-26 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSO2/402/3220646DR | 2023-05-07 21:00 | 2023-05-08 17:30 | 2023-05-13 | COMPLETE
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230246DR | 2023-07-15 06:00 | 2023-07-15 16:00 | 2023-07-25 06:00 | COMPLETE
Minas | MNS-P21 | Minas 02075 | 9D-48E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230216DR | 2023-08-19 16:00 | 2023-08-21 15:00 | 2023-08-25 09:00 | COMPLETE
Minas | P_4C-35E | Minas 02074 | 4C-35E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230220DR | 2023-09-14 14:30 | 2023-09-15 11:00 | 2023-09-18 15:00 | COMPLETE
Minas | P_4C-45N1 | Minas 02079 | 4C-45N1 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230225DR | 2023-09-18 15:00 | 2023-09-19 08:00 | 2023-09-27 14:00 | COMPLETE
Minas | P_4C-46 | Minas 02080 | 4C-46 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-08 | SSM2/402/3230222DR | 2023-09-27 14:00 | 2023-09-28 01:00 | 2023-10-02 12:00 | COMPLETE
Seruni | SRN-P1 | Seruni 00054 | N2-W3-47A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | GRK2/402/2210161DR | 2022-01-20 21:00 | 2022-01-21 13:30 | 2022-01-26 19:00 | COMPLETE
Seruni | SRN-P3 | Seruni 00055 | N2-W3-34A | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-11 | GRK2/402/2210163DR | 2022-02-06 | 2022-02-11 23:00 | 2022-03-02 21:00 | COMPLETE
Seruni | SRN-P14 | Seruni 00057 | N1-W2-31B | Pump Repair | PMP18 - Raise up Tubing | Land Workover Unit | BMS-11 | GRK2/402/2220276DR | 2022-06-06 13:00 | 2022-06-07 16:00 | 2022-06-08 04:00 | COMPLETE
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | GRK2/402/2220061DR | 2022-09-06 08:00 | 2022-09-07 02:00 | 2022-09-10 | COMPLETE
Bangko | BNK_P5A_LQR | Bangko 00415 | N2-W1-85A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220389DR | 2022-11-24 06:00 | 2022-11-26 02:00 | 2022-12-04 | COMPLETE
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220425DR | 2023-05-12 | 2023-05-13 02:00 | 2023-05-14 08:00 | COMPLETE
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220450DR | 2023-05-14 08:00 | 2023-05-15 02:00 | 2023-05-16 10:00 | COMPLETE
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220419DR | 2023-05-16 10:00 | 2023-05-17 | 2023-05-18 | COMPLETE
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220348DR | 2023-05-18 | 2023-05-19 08:00 | 2023-05-20 08:00 | COMPLETE
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220359DR | 2023-05-20 08:00 | 2023-05-21 08:00 | 2023-05-22 | COMPLETE
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220425DR | 2023-05-22 | 2023-05-13 02:00 | 2023-05-27 | COMPLETE
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220419DR | 2023-05-27 | 2023-05-17 | 2023-05-31 | COMPLETE
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220450DR | 2023-05-31 | 2023-05-15 02:00 | 2023-06-03 05:00 | COMPLETE
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220348DR | 2023-06-03 05:00 | 2023-05-19 08:00 | 2023-06-06 10:00 | COMPLETE
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220437DR | 2023-06-12 19:00 | 2023-06-13 12:00 | 2023-06-14 15:00 | COMPLETE
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220377DR | 2023-06-14 15:00 | 2023-06-15 03:00 | 2023-06-16 | COMPLETE
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220434DR | 2023-06-19 17:00 | 2023-06-05 14:00 | 2023-06-23 | COMPLETE
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220437DR | 2023-06-28 | 2023-06-13 12:00 | 2023-07-02 | COMPLETE
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220377DR | 2023-07-04 19:00 | 2023-06-15 03:00 | 2023-07-09 20:00 | COMPLETE
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220359DR | 2023-07-09 20:00 | 2023-05-21 08:00 | 2023-07-18 13:00 | COMPLETE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220407DR | 2023-07-18 13:00 | 2023-07-20 02:00 | 2023-07-21 07:00 | COMPLETE
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220440DR | 2023-07-26 | 2023-07-27 | 2023-07-28 20:00 | COMPLETE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220407DR | 2023-07-30 14:30 | 2023-07-20 02:00 | 2023-08-01 10:00 | COMPLETE
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220373DR | 2023-09-24 19:00 | 2023-09-25 14:00 | 2023-09-28 06:00 | COMPLETE
Balam So | LQR-TE003_BLSO_41 | Balam So 00553 | N1-W1-73B | Clean-Out | CLO03 - Clean/ Bail Out Sand | Land Workover Unit | BMS-11 | SSO2/402/3220583DR | 2024-02-03 | 2024-02-03 18:00 | 2024-02-04 17:00 | COMPLETE
Balam So | LQR-TE012_BLSO_34 | Balam So 00559 | N1-W1-66E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220357DR | 2024-02-04 17:00 | 2024-02-06 14:00 | 2024-02-09 19:00 | COMPLETE
Balam So | LQR-TE212_BLSO_52 | Balam So 00558 | N1-W1-66D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230368DR | 2024-02-09 19:00 | 2024-02-10 15:00 | 2024-02-12 | COMPLETE
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230364DR | 2024-02-25 20:30 | 2024-02-26 20:00 | 2024-02-28 08:00 | COMPLETE
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220588DR | 2024-03-06 | 2023-11-15 21:00 | 2024-03-10 14:00 | COMPLETE
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230364DR | 2024-03-10 14:00 | 2024-02-26 20:00 | 2024-03-14 16:30 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220548DR | 2024-03-14 16:30 | 2024-05-05 05:00 | 2024-03-16 07:00 | COMPLETE
Balam So | BLSO23-LQR-TE040 | Balam So 00531 | N1-W1-34A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220586DR | 2024-03-18 03:00 | 2024-03-19 04:00 | 2024-03-26 03:00 | COMPLETE
Balam So | BLSO23-LQR-TE019 | Balam So 00532 | O-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220587DR | 2024-03-21 | 2024-03-27 | 2024-04-02 | COMPLETE
Balam So | BLSO23-LQR-TE024 | Balam So 00537 | O-O-75A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220439DR | 2024-04-02 | 2024-04-03 | 2024-04-08 17:00 | COMPLETE
Balam So | BLSO23-LQR-TE068 | Balam So 00536 | O-O-75B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220406DR | 2024-04-08 17:00 | 2024-04-09 15:00 | 2024-04-16 | COMPLETE
Balam So | BLSO23-LQR-TE042 | Balam So 00539 | O-O-77B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230349DR | 2024-04-19 | 2024-04-20 |  | COMPLETE
Balam So | BLSO23-LQR-TE050 | Balam So 00549 | N1-W1-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230336DR | 2024-04-26 | 2024-04-27 11:00 | 2024-05-03 07:30 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220548DR | 2024-05-03 07:30 | 2024-05-05 05:00 | 2024-05-08 05:00 | COMPLETE
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220416DR | 2024-05-19 08:00 | 2024-05-20 02:00 | 2024-05-21 16:00 | COMPLETE
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230350DR | 2024-05-24 17:00 | 2024-05-25 10:00 | 2024-05-27 18:00 | SUSPENDED
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230355DR | 2024-06-11 11:00 | 2024-06-12 16:00 | 2024-06-14 20:00 | SUSPENDED
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSO2/402/3220416DR | 2024-06-14 20:00 | 2024-05-20 02:00 | 2024-06-20 | COMPLETE
Balam So | BLSO23-LQR-TE065 | Balam So 00545 | N1-O-21A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230343DR | 2024-06-27 | 2024-06-27 23:00 | 2024-07-03 09:00 | COMPLETE
Balam So | BLSO23-LQR-TE046 | Balam So 00552 | O-O-73A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-11 | SSE2/402/3230351DR | 2024-07-03 09:00 | 2024-07-04 07:00 | 2024-07-09 06:30 | COMPLETE
Petani | PTN-X09 | Petani 00139 | O-O-68A | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-15 | GRK2/402/2220245DR | 2022-05-26 11:00 | 2022-05-27 22:00 | 2022-06-10 16:00 | COMPLETE
Petani | PTN-X11 | Petani 00144 | S1-O-26C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | GRK2/402/2220250DR | 2022-06-24 21:00 | 2022-06-26 14:30 | 2022-07-07 07:00 | COMPLETE
Bekasap | BKS-X12 | Bekasap 00222 | O-O-48B | Complete | COM01 - Initial Completion | Land Workover Unit | BMS-15 | SSO2/402/3220332DR | 2022-11-22 19:00 | 2022-11-26 05:00 | 2022-12-09 04:00 | COMPLETE
Pematang | PMT-P17 | Pematang 00113 | O-O-52E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSO2/402/3220344DR | 2022-12-29 | 2022-12-29 13:00 | 2023-01-23 16:00 | COMPLETE
Libo Se | LISE23_CC16 | Libo Se 00058 | S1-E4-86 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSV2/402/3230628DR | 2023-11-10 | 2023-11-13 02:00 | 2023-11-26 19:00 | COMPLETE
Libo Se | LISE23_SC03 | Libo Se 00059 | S2-W3-67A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-15 | SSV2/402/3230657DR | 2024-04-04 12:00 | 2024-04-05 19:00 | 2024-04-16 12:00 | COMPLETE
Duri | 6F-1102B | Duri 10994 | 6F-1102B | Pump Repair | PMP09 - Rod Pump Stuck Normal | Land Workover Unit | BMS-16 | RHO2/402/2220471DR | 2023-01-15 10:30 | 2023-01-15 22:00 | 2023-01-16 15:30 | COMPLETE
Petani | PETA22-P06 | Petani 00152 | O-O-54C | Perforation | PRF01 - Regular Perforation | Land Workover Unit | BMS-17 | GRK2/402/2220254DR | 2022-09-19 16:00 | 2022-09-20 05:00 | 2022-09-30 13:00 | COMPLETE
Petani | PETA22-INJ2 | Petani 00155 | S1-E1-33B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-17 | SSO2/402/3220502DR | 2022-10-10 23:00 | 2022-10-11 19:00 | 2022-10-21 | COMPLETE
Petani | PETA22-INJ4 | Petani 00156 | N1-W1-25A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-17 | SSO2/402/3220505DR | 2022-10-27 03:00 | 2022-10-29 21:00 | 2022-11-08 10:30 | COMPLETE
Petani | PTN-X09 | Petani 00139 | O-O-68A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | BMS-18 | GRK2/402/2220245DR | 2022-07-23 21:00 | 2022-07-24 12:30 | 2022-07-28 18:00 | COMPLETE
Petani | PTN-X09 | Petani 00139 | O-O-68A | Swabbing | SWB01 - Regular Swab Test | Land Workover Unit | BMS-18 | GRK2/402/2220245DR | 2022-08-03 13:30 | 2022-07-24 12:30 | 2022-08-12 12:00 | COMPLETE
Petani | PETA22-INJ5 | Petani 00170 | N1-W1-27A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3220916DR | 2023-07-13 12:30 | 2023-07-14 02:00 | 2023-07-29 21:30 | COMPLETE
Petani | PETA23B-P03 | Petani 00192 | O-O-63E | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSM2/402/3230301DR | 2024-03-01 16:00 | 2024-03-03 23:00 | 2024-03-17 13:00 | COMPLETE
Pematang | PMT-P08 | Pematang 00123 | O-O-51A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSA2/402/3220894DR | 2024-03-21 01:00 | 2024-03-21 17:00 | 2024-03-26 | COMPLETE
Kopar | KPR-X20 | Kopar 00040 | O-O-66A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | BMS-18 | SSO2/402/3220622DR | 2024-04-09 06:30 | 2024-04-09 22:30 | 2024-04-18 21:00 | COMPLETE
Pematang | P_PEMA24_INJ3 | Pematang 00130 | O-O-23B | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3230170DR | 2024-04-22 13:00 | 2024-04-23 16:00 | 2024-05-01 | COMPLETE
Pematang | P_PEMA24_INJ6 | Pematang 00131 | O-O-57D | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | BMS-18 | SSA2/402/3230173DR | 2024-05-04 05:00 | 2024-05-05 14:00 | 2024-05-16 07:00 | COMPLETE
Petani | PTN-X03 | Petani 00136 | O-O-11A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220242DR | 2022-01-29 20:00 | 2022-01-29 20:00 | 2022-02-25 07:00 | COMPLETE
Petani | PTN-X04 | Petani 00138 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220244DR | 2022-02-25 07:00 | 2022-03-07 23:00 | 2022-04-03 02:00 | COMPLETE
Petani | PTN-X05 | Petani 00141 | O-O-43B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220246DR | 2022-04-03 02:00 | 2022-04-09 | 2022-04-30 14:30 | COMPLETE
Petani | PTN-X06 | Petani 00145 | O-O-43C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220249DR | 2022-04-30 14:30 | 2022-05-03 16:00 | 2022-05-25 19:00 | COMPLETE
Petani | PTN-X02 | Petani 00148 | N1-O-72A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220251DR | 2022-05-25 19:00 | 2022-05-30 08:00 | 2022-06-19 05:00 | COMPLETE
Petani | PETA22-P01 | Petani 00149 | N1-O-72B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220260DR | 2022-06-19 05:00 | 2022-06-23 20:30 | 2022-07-16 06:00 | COMPLETE
Petani | PETA22-P24 | Petani 00153 | O-W1-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | GRK2/402/2220257DR | 2022-07-16 06:00 | 2022-07-21 09:00 | 2022-08-07 | RELEASE
Petani | PETA22-INJ2 | Petani 00155 | S1-E1-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220502DR | 2022-08-07 | 2022-08-12 16:00 | 2022-08-30 15:30 | RELEASE
Petani | PETA22-P08 | Petani 00157 | O-O-64D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220539DR | 2022-08-30 15:30 | 2022-09-11 | 2022-09-29 22:00 | COMPLETE
Petani | PETA22-P02 | Petani 00160 | O-O-21C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTF2/402/3220459DR | 2022-09-29 22:00 | 2022-10-11 04:00 | 2022-11-08 13:00 | COMPLETE
Petani | PETA23_P17 | Petani 00162 | O-O-32E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTG2/402/3220461DR | 2022-11-08 13:00 | 2022-11-14 | 2022-12-11 02:00 | COMPLETE
Petani | PETA23_P05 | Petani 00163 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTG2/402/3220462DR | 2022-12-11 02:00 | 2022-12-15 13:00 | 2023-01-07 | COMPLETE
Pager | PG22-P17 | Pager 00054 | O-O-22A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220385DR | 2023-01-07 | 2023-01-23 16:00 | 2023-03-09 12:00 | COMPLETE
Pager | PG22-P20 | Pager 00056 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220414DR | 2023-03-09 12:00 | 2023-03-16 07:00 | 2023-04-26 | COMPLETE
Petani | PETA23B-P07 | Petani 00171 | S1-O-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSM2/402/3230292DR | 2023-04-26 | 2023-07-29 23:00 | 2023-08-23 13:00 | COMPLETE
Petani | PETA23B-P09 | Petani 00184 | S1-O-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSM2/402/3230293DR | 2023-08-23 13:00 | 2023-08-31 10:30 | 2023-09-22 18:30 | COMPLETE
Petani | PETA22-P11 | Petani 00190 | S1-O-88C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | PTI2/402/3220809DR | 2023-09-22 18:30 | 2023-09-27 09:00 | 2023-10-18 13:00 | COMPLETE
Petani | PETA22-P12 | Petani 00194 | S1-O-88D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSA2/402/3220908DR | 2023-10-18 13:00 | 2023-10-22 13:00 | 2023-11-15 12:00 | COMPLETE
Petani | PETA22-P15 | Petani 00197 | S1-O-88E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSA2/402/3220904DR | 2023-11-15 12:00 | 2023-11-22 08:00 | 2023-12-09 | COMPLETE
Kopar | KPR-X15 | Kopar 00041 | S1-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-03 | SSO2/402/3220620DR | 2023-12-09 | 2024-03-14 22:30 | 2024-01-29 | COMPLETE
Tilan | TILA23-P03 | Tilan 00035 | O-O-27H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220664DR | 2022-12-03 20:00 | 2022-12-03 20:00 | 2023-01-03 20:00 | COMPLETE
Tilan | TILA23-P02 | Tilan 00036 | O-O-27G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220663DR | 2023-01-03 20:00 | 2023-01-08 20:00 | 2023-02-03 02:00 | COMPLETE
Tilan | TILA23-P01 | Tilan 00037 | O-O-25C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220662DR | 2023-02-03 02:00 | 2023-02-11 04:00 | 2023-05-04 21:00 | COMPLETE
Petani | PETA23_P01 | Petani 00169 | N1-W1-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSA2/402/3220906DR | 2023-05-04 21:00 | 2023-05-28 14:00 | 2023-06-20 20:00 | COMPLETE
Petani | PETA23B-P11 | Petani 00176 | S1-E1-33D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSA2/402/3220900DR | 2023-06-20 20:00 | 2023-07-04 02:00 | 2023-07-26 08:30 | COMPLETE
Petani | PETA23B-P12 | Petani 00179 | S1-E1-33C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230303DR | 2023-07-26 08:30 | 2023-07-29 22:00 | 2023-08-23 01:30 | COMPLETE
Petani | PETA23B-P06 | Petani 00185 | O-O-85H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230304DR | 2023-08-23 01:30 | 2023-09-15 21:00 | 2023-10-04 18:00 | COMPLETE
Petani | PETA23B-P05 | Petani 00191 | O-O-85G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTB2/402/3230480DR | 2023-10-04 18:00 | 2023-10-07 12:00 | 2023-10-25 19:30 | COMPLETE
Petani | PETA22-P09 | Petani 00193 | O-O-85D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSM2/402/3230305DR | 2023-10-25 19:30 | 2023-10-31 11:00 | 2023-11-13 19:30 | RELEASE
Petani | PETA23B-P08 | Petani 00198 | N1-O-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTB2/402/3230479DR | 2023-11-13 19:30 | 2024-02-09 17:00 | 2024-03-02 21:00 | COMPLETE
Kopar | KPR-X15 | Kopar 00041 | S1-O-12A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220620DR | 2024-03-02 21:00 | 2024-03-14 22:30 | 2024-03-31 | COMPLETE
Kopar | KPR-X03 | Kopar 00043 | O-O-44A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220617DR | 2024-03-31 | 2024-04-09 04:00 | 2024-05-07 | COMPLETE
Kopar | KPR-X04_OPT | Kopar 00045 | O-O-44B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTO2/402/3240787DR | 2024-05-07 | 2024-05-10 21:00 | 2024-06-03 | COMPLETE
Kopar | KPR-X11 | Kopar 00048 | S1-O-32A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | SSO2/402/3220619DR | 2024-06-03 | 2024-06-14 | 2024-07-01 17:00 | COMPLETE
Petani | P_PETA24_33 | Petani 00210 | S1-O-16A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-05 | PTO2/402/3230898DR | 2024-07-01 17:00 |  |  | IN_PROGRESS
Sikladi | Sikladi P05 | Sikladi 00027 | O-O-28A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210093DR | 2021-07-28 14:30 | 2021-08-02 16:00 | 2021-08-15 07:00 | COMPLETE
Sikladi | Sikladi P05 | Sikladi 00027 | O-O-28A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210093DR | 2021-08-15 07:00 | 2021-08-15 10:30 | 2021-08-17 04:00 | COMPLETE
Sikladi | SIKL21-P06 | Sikladi 00028 | O-O-28B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210157DR | 2021-08-17 04:00 | 2021-08-19 15:00 | 2021-08-29 22:00 | COMPLETE
Sikladi | SIKL21-P06 | Sikladi 00028 | O-O-28B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210157DR | 2021-08-28 22:00 | 2021-08-28 22:00 | 2021-08-31 | COMPLETE
Sikladi | SIKL21-P07 | Sikladi 00029 | N1-O-86A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210158DR | 2021-08-31 | 2021-09-05 18:00 | 2021-09-16 06:00 | COMPLETE
Sikladi | SIKL21-P07 | Sikladi 00029 | N1-O-86A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-16 | GRK2/402/2210158DR | 2021-09-16 06:00 | 2021-09-16 06:00 | 2021-09-18 02:00 | COMPLETE
Pinang | Pinang P04 | Pinang 00051 | N1-W2-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210135DR | 2021-09-18 02:00 | 2021-09-30 23:00 | 2021-10-15 09:30 | COMPLETE
Pinang | Pinang P06 | Pinang 00052 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210137DR | 2021-10-15 09:30 | 2021-10-19 11:00 | 2021-10-31 13:00 | COMPLETE
Pinang | Pinang P05 | Pinang 00053 | N1-W2-62A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210136DR | 2021-10-31 13:00 | 2021-11-05 17:00 | 2021-11-18 16:00 | COMPLETE
Pinang | Pinang P07 | Pinang 00054 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210138DR | 2021-11-18 16:00 | 2021-11-24 15:00 | 2021-12-06 20:30 | COMPLETE
Bangko | BNK-P21 | Bangko 00369 | N2-W1-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210049DR | 2021-12-06 20:30 | 2021-12-24 07:00 | 2022-01-02 22:00 | COMPLETE
Bangko | BNK-P8 | Bangko 00381 | N1-W2-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2210071DR | 2022-01-02 22:00 | 2022-01-19 07:00 | 2022-01-28 13:00 | COMPLETE
Balam So | BLSO-P08 | Balam So 00450 | O-O-15C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220016DR | 2022-01-28 13:00 | 2022-02-07 12:00 | 2022-02-14 01:00 | COMPLETE
Balam So | BLSO-P11 | Balam So 00451 | O-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220010DR | 2022-02-26 21:00 | 2022-02-26 21:00 | 2022-03-06 04:00 | RELEASE
Balam So | BLSO-P15 | Balam So 00456 | O-O-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220005DR | 2022-03-06 04:00 | 2022-03-12 08:15 | 2022-03-18 22:00 | COMPLETE
Balam So | BLSO-P04 | Balam So 00460 | O-O-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220008DR | 2022-03-18 22:00 | 2022-03-20 21:30 | 2022-03-27 14:00 | COMPLETE
Balam So | BLSO-P21 | Balam So 00463 | O-W1-18B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220011DR | 2022-03-27 14:00 | 2022-04-02 08:00 | 2022-04-10 06:30 | COMPLETE
Balam So | BLSO-P22 | Balam So 00467 | O-W1-18C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220017DR | 2022-04-10 06:30 | 2022-04-12 12:00 | 2022-04-19 16:00 | COMPLETE
Balam So | BLSO-P23 | Balam So 00470 | N1-W1-84A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220022DR | 2022-04-19 16:00 | 2022-04-27 10:00 | 2022-05-05 09:00 | RELEASE
Balam So | LQR-TE223_BLSO_30 | Balam So 00473 | N1-W1-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220031DR | 2022-05-05 09:00 | 2022-05-07 17:00 | 2022-05-15 | COMPLETE
Menggala No | MNO-P01 | Menggala No 00049 | N3-W1-14B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220194DR | 2022-05-14 | 2022-05-24 18:00 | 2022-06-10 01:30 | COMPLETE
Menggala No | MNO-P18 | Menggala No 00051 | N3-W1-14A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/3220234DR | 2022-06-10 01:30 | 2022-06-12 12:00 | 2022-06-25 18:00 | COMPLETE
Menggala No | MNO-P15 | Menggala No 00053 | N3-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/3220237DR | 2022-06-25 18:00 | 2022-06-30 23:45 | 2022-07-14 08:00 | COMPLETE
Menggala No | MNO-P02 | Menggala No 00055 | N3-W1-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220195DR | 2022-07-14 08:00 | 2022-07-19 12:30 | 2022-08-05 15:00 | COMPLETE
Menggala No | MNO-P17 | Menggala No 00057 | N3-W1-33C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | GRK2/402/2220068DR | 2022-08-05 15:00 | 2022-08-08 | 2022-08-21 19:00 | COMPLETE
Balam So | BLSO-P41 | Balam So 00485 | O-W1-15G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220317DR | 2022-08-21 19:00 | 2022-09-08 19:00 | 2022-09-15 | RELEASE
Balam So | LQR-TE053_BLSO_15 | Balam So 00493 | N1-O-75B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220519DR | 2022-09-15 | 2022-09-23 05:30 | 2022-09-29 17:00 | COMPLETE
Pematang | PMT-P05 | Pematang 00111 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220364DR | 2022-09-29 17:00 | 2022-10-20 12:00 | 2022-11-08 12:00 | RELEASE
Pematang | PMT-P19 | Pematang 00112 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220545DR | 2022-11-08 12:00 | 2022-11-11 14:00 | 2022-12-05 13:00 | COMPLETE
Pematang | PMT-P09 | Pematang 00114 | O-W1-26A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220420DR | 2022-12-05 13:00 | 2022-12-11 04:00 | 2023-01-13 20:00 | COMPLETE
Pematang | PMT-P23 | Pematang 00115 | O-W1-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220658DR | 2023-01-13 20:00 | 2023-01-17 08:00 | 2023-02-07 10:00 | COMPLETE
Pematang | PMT-P12 | Pematang 00117 | O-O-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220408DR | 2023-02-07 10:00 | 2023-03-03 06:00 | 2023-04-01 16:00 | COMPLETE
Pematang | PMT-P22 | Pematang 00116 | O-O-52F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220371DR | 2023-04-01 | 2023-04-28 | 2023-05-19 10:00 | COMPLETE
Pematang | PMT-P25 | Pematang 00119 | O-O-52G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220432DR | 2023-05-19 10:00 | 2023-05-22 09:00 | 2023-06-09 22:30 | COMPLETE
Pematang | PMT-P06 | Pematang 00120 | O-O-52D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220893DR | 2023-06-09 22:30 | 2023-06-14 14:00 | 2023-07-03 12:00 | COMPLETE
Pematang | PMT-P04 | Pematang 00121 | O-O-52H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220456DR | 2023-07-03 12:00 | 2023-07-07 18:00 | 2023-07-26 11:00 | COMPLETE
Pematang | PMT-P16 | Pematang 00122 | O-O-52I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSO2/402/3220659DR | 2023-07-26 11:00 | 2023-07-29 09:00 | 2023-08-12 16:00 | COMPLETE
Pematang | PMT-P08 | Pematang 00123 | O-O-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220894DR | 2023-08-12 16:00 | 2023-08-18 04:00 | 2023-09-03 | RELEASE
Pematang | PMT-P18 | Pematang 00124 | O-O-51B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220895DR | 2023-09-03 | 2023-09-06 17:30 | 2023-09-26 15:00 | COMPLETE
Pematang | PMT-P24 | Pematang 00125 | O-O-51C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220896DR | 2023-09-26 15:00 | 2023-09-30 23:30 | 2023-10-19 05:00 | COMPLETE
Pematang | PMT-P20 | Pematang 00126 | O-O-51D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220897DR | 2023-10-19 05:00 | 2023-11-30 18:00 | 2023-12-18 05:00 | COMPLETE
Pematang | PMT-P10 | Pematang 00127 | O-O-51E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220898DR | 2023-12-18 05:00 | 2023-12-21 05:00 | 2024-01-15 18:00 | COMPLETE
Pematang | P_PEMA24_INJ6 | Pematang 00131 | O-O-57D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230173DR | 2024-01-15 18:00 | 2024-01-25 21:00 | 2024-02-08 18:00 | COMPLETE
Pematang | P_PEMA24_11 | Pematang 00129 | O-O-51F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230160DR | 2024-02-08 18:00 | 2024-02-15 | 2024-03-01 12:30 | COMPLETE
Pematang | P_PEMA24_INJ1 | Pematang 00133 | N1-W1-86B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230168DR | 2024-03-01 12:30 | 2024-03-07 22:00 | 2024-03-25 08:00 | COMPLETE
Pematang | P_PEMA24_INJ5 | Pematang 00135 | O-O-52N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3230172DR | 2024-03-25 08:00 | 2024-04-04 21:30 | 2024-04-26 07:00 | COMPLETE
Bekasap So | P_BESO24_02 | Bekasap So 00016 | S3-O-16B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSN2/402/3230682DR | 2024-04-26 07:00 | 2024-05-04 16:30 | 2024-05-29 15:00 | COMPLETE
Bekasap So | P_BESO24_04 | Bekasap So 00018 | S2-O-74A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSN2/402/3230681DR | 2024-05-29 15:00 | 2024-06-16 01:30 | 2024-06-28 06:00 | COMPLETE
Pematang | P_PEMA24_04 | Pematang 00139 | O-O-42C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-16 | SSA2/402/3220902DR | 2024-06-28 06:00 | 2024-07-06 |  | IN_PROGRESS
Bangko | BNK-P3 | Bangko 00348 | N1-W2-17A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210058DR | 2021-08-02 | 2021-08-28 16:00 | 2021-09-07 17:00 | COMPLETE
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210034DR | 2021-08-05 | 2021-08-10 23:30 | 2021-08-17 15:00 | COMPLETE
Bangko | Bangko P03reg 5 | Bangko 00344 | S1-E2-42A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-18 | 2210034DR | 2021-08-17 15:00 | 2021-08-17 15:00 | 2021-08-19 | COMPLETE
Bangko | BNK-P3 | Bangko 00348 | N1-W2-17A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | BN-18 | GRK2/402/2210058DR | 2021-09-06 17:00 | 2021-09-06 17:00 | 2021-09-08 08:00 | COMPLETE
Bangko | BNK-P26 | Bangko 00349 | N1-W1-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210054DR | 2021-09-08 08:00 | 2021-09-14 10:00 | 2021-09-22 05:00 | COMPLETE
Bangko | BNK-P34 | Bangko 00351 | N1-W1-76A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210063DR | 2021-09-22 05:00 | 2021-09-28 16:00 | 2021-10-06 10:00 | COMPLETE
Bangko | BNK-P11 | Bangko 00354 | N1-W2-77B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210040DR | 2021-10-06 10:00 | 2021-10-11 08:00 | 2021-10-18 19:00 | COMPLETE
Bangko | BNK-P39 | Bangko 00361 | N2-W2-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210066DR | 2021-10-18 19:00 | 2021-10-23 16:00 | 2021-11-01 | COMPLETE
Bangko | BNK-P10 | Bangko 00356 | N1-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210039DR | 2021-11-01 | 2021-11-08 10:00 | 2021-11-16 07:00 | RELEASE
Bangko | BNK-P7 | Bangko 00365 | N1-W1-51B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210072DR | 2021-11-16 07:00 | 2021-11-18 19:30 | 2021-11-28 22:00 | COMPLETE
Bangko | BNK-P5 | Bangko 00359 | N1-W1-22A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210070DR | 2021-11-28 22:00 | 2021-12-25 01:45 | 2022-01-02 06:00 | COMPLETE
Bangko | BNK-P22 | Bangko 00374 | N1-W1-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210050DR | 2022-01-02 06:00 | 2022-01-04 22:00 | 2022-01-19 15:00 | COMPLETE
Bangko | BNK-P30 | Bangko 00378 | N1-W2-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2210059DR | 2022-01-19 15:00 | 2022-01-30 22:00 | 2022-02-09 14:00 | COMPLETE
Bangko | BNK-P1 | Bangko 00382 | N1-W2-17C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220060DR | 2022-02-09 14:00 | 2022-02-12 04:00 | 2022-02-21 18:00 | COMPLETE
Balam So | BLSO-P16 | Balam So 00454 | O-O-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220009DR | 2022-03-12 20:30 | 2022-03-12 20:30 | 2022-03-19 03:30 | COMPLETE
Balam So | BLSO-P02 | Balam So 00459 | O-O-36C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220004DR | 2022-03-19 03:30 | 2022-03-21 | 2022-03-27 01:30 | COMPLETE
Balam So | BLSO-P24 | Balam So 00464 | N1-W1-75A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220027DR | 2022-03-27 01:30 | 2022-04-03 01:30 | 2022-04-11 01:00 | COMPLETE
Balam So | BLSO-P29 | Balam So 00468 | S1-O-17A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220030DR | 2022-04-11 01:00 | 2022-04-18 | 2022-04-28 | COMPLETE
Balam So | BLSO-P33 | Balam So 00469 | S1-O-17B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220035DR | 2022-04-28 | 2022-04-30 07:00 | 2022-05-07 15:30 | COMPLETE
Balam So | BLSO-P27 | Balam So 00471 | N1-W1-58B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220029DR | 2022-05-07 15:30 | 2022-05-13 03:00 | 2022-05-26 21:00 | COMPLETE
Balam So | BLSO-P05 | Balam So 00474 | N1-O-66B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220021DR | 2022-05-26 21:00 | 2022-05-31 23:45 | 2022-06-08 05:00 | COMPLETE
Balam So | BLSO-P10 | Balam So 00476 | N1-O-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220006DR | 2022-06-08 05:00 | 2022-06-14 | 2022-06-22 05:15 | COMPLETE
Balam So | LQR-TE036_BLSO_10 | Balam So 00477 | N1-O-83F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220036DR | 2022-06-22 05:15 | 2022-06-24 14:00 | 2022-06-30 08:00 | COMPLETE
Balam So | BLSO-P01 | Balam So 00479 | O-O-34D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220026DR | 2022-06-30 08:00 | 2022-07-08 04:30 | 2022-07-16 14:00 | COMPLETE
Balam So | LQR-TE047_BLSO_53 | Balam So 00480 | S1-O-35A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220053DR | 2022-07-16 14:00 | 2022-07-21 14:00 | 2022-07-29 11:30 | COMPLETE
Balam So | LQR-TE088_BLSO_55 | Balam So 00481 | S1-O-36A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220057DR | 2022-07-29 11:30 | 2022-08-02 13:00 | 2022-08-09 15:30 | COMPLETE
Balam So | LQR-TE216_BLSO_51 | Balam So 00482 | N1-W1-62F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | GRK2/402/2220047DR | 2022-08-09 15:30 | 2022-08-16 | 2022-08-22 12:00 | COMPLETE
Balam So | LQR-TE001_BLSO_44 | Balam So 00483 | N1-W1-62E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220509DR | 2022-08-22 12:00 | 2022-08-24 21:30 | 2022-09-01 12:00 | COMPLETE
Balam So | LQR-TE026_BLSO_9 | Balam So 00487 | O-O-33H | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220323DR | 2022-08-31 12:00 | 2022-09-08 21:30 | 2022-09-15 17:30 | COMPLETE
Balam So | BLSO-P03 | Balam So 00490 | O-O-44F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220501DR | 2022-09-25 07:00 | 2022-09-25 10:00 | 2022-10-05 09:30 | COMPLETE
Balam So | LQR-TE029_BLSO_16 | Balam So 00495 | O-O-33I | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220515DR | 2022-10-05 09:30 | 2022-10-11 12:00 | 2022-10-21 | COMPLETE
Balam So | LQR-TE171_BLSO_54 | Balam So 00500 | S1-O-47B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220532DR | 2022-10-21 | 2022-10-25 21:00 | 2022-11-04 | COMPLETE
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220373DR | 2022-11-04 | 2022-09-22 19:00 | 2022-11-24 18:00 | COMPLETE
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220390DR | 2022-11-24 18:00 | 2022-10-30 02:00 | 2022-12-19 08:30 | COMPLETE
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220450DR | 2022-12-19 08:30 | 2022-12-26 21:00 | 2023-01-04 19:00 | RELEASE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220407DR | 2023-01-04 19:00 | 2022-10-24 23:00 | 2023-01-16 17:30 | RELEASE
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220440DR | 2023-01-16 17:30 | 2022-10-14 04:00 | 2023-02-02 19:00 | RELEASE
Balam Se | P_BLSE23_P03_MN | Balam Se 00026 | O-O-32B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220577DR | 2023-02-02 19:00 | 2023-03-01 13:00 | 2023-04-23 20:30 | COMPLETE
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220416DR | 2023-08-11 16:30 | 2023-08-11 16:30 | 2023-08-17 02:00 | COMPLETE
Balam So | BLSO23-LQR-TE028 | Balam So 00540 | N1-W1-88A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230334DR | 2023-08-17 02:00 | 2023-08-25 02:00 | 2023-08-29 22:30 | RELEASE
Balam Se | P_BLSE23_P08_PM | Balam Se 00029 | O-O-14C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220576DR | 2023-08-29 22:30 | 2023-09-08 03:30 | 2023-09-29 12:00 | COMPLETE
Balam Se | P_BLSE23_P04_MN | Balam Se 00030 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220582DR | 2023-09-29 12:00 | 2023-10-06 16:00 | 2023-10-18 11:00 | COMPLETE
Balam Se | P_BLSE23_P02_MN | Balam Se 00031 | O-O-32C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220581DR | 2023-10-18 11:00 | 2023-10-23 01:00 | 2023-11-04 22:00 | COMPLETE
Balam Se | P_BLSE23_P10_PM | Balam Se 00032 | O-O-46C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230306DR | 2023-11-04 22:00 | 2023-11-11 15:30 | 2023-11-29 | COMPLETE
Balam Se | P_BLSE23_P23_PM | Balam Se 00034 | O-O-46D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220580DR | 2023-11-29 | 2023-12-03 13:30 | 2023-12-28 13:30 | COMPLETE
Balam So | P_BLSO24_LQR06 | Balam So 00573 | N1-W1-77D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230345DR | 2023-12-28 13:30 | 2024-01-14 22:30 | 2024-01-23 05:00 | COMPLETE
Balam So | P_BLSO24_LQR02 | Balam So 00587 | O-W1-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230324DR | 2024-01-22 05:00 | 2024-01-29 02:00 | 2024-02-04 12:00 | COMPLETE
Balam Se | P_BLSE23_P06_PM | Balam Se 00037 | N1-O-63 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230316DR | 2024-02-04 12:00 | 2024-02-11 12:00 | 2024-02-26 06:30 | COMPLETE
Balam Se | P_BLSE23_P07_PM | Balam Se 00038 | N1-E1-61C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230315DR | 2024-02-26 06:30 | 2024-02-28 17:00 | 2024-03-13 | COMPLETE
Balam So | LQR-TE013_BLSO_27 | Balam So 00593 | N1-W1-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230321DR | 2024-03-13 | 2024-03-19 15:00 | 2024-03-27 15:00 | COMPLETE
Balam So | LQR-TE138_BLSO_37 | Balam So 00594 | N1-W1-86C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSE2/402/3230322DR | 2024-03-23 | 2024-03-30 06:00 | 2024-04-05 08:00 | COMPLETE
Bangko | BNK_PX10E_LQR | Bangko 00440 | N2-W3-74 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220609DR | 2024-04-05 08:00 | 2024-04-13 01:00 | 2024-04-20 13:00 | COMPLETE
Bangko | BNK_PX10D_LQR | Bangko 00441 | N2-W3-74A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220352DR | 2024-04-20 13:00 | 2024-04-24 01:00 | 2024-04-30 19:30 | COMPLETE
Bangko | BNK_PX04D_LQR | Bangko 00442 | N2-W3-74C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220607DR | 2024-04-30 19:30 | 2024-05-04 12:00 | 2024-05-10 04:00 | COMPLETE
Bangko | BNK_PX10_LQR | Bangko 00443 | N2-W3-74D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220610DR | 2024-05-10 04:00 | 2024-05-14 09:00 | 2024-05-21 16:00 | COMPLETE
Bangko | BNK_PX04C_LQR | Bangko 00444 | N2-W3-74B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSO2/402/3220606DR | 2024-05-21 16:00 | 2024-05-27 18:00 | 2024-06-03 04:00 | COMPLETE
Bangko | BNK23_P15 | Bangko 00445 | N1-W1-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230282DR | 2024-06-03 04:00 | 2024-06-14 01:30 | 2024-06-27 | COMPLETE
Bangko | BNK23_P14 | Bangko 00447 | N1-W2-57C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230283DR | 2024-06-27 | 2024-06-30 09:00 | 2024-07-11 14:00 | COMPLETE
Bangko | BNK23_P13 | Bangko 00448 | N1-W2-57D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BN-18 | SSM2/402/3230280DR | 2024-07-11 14:00 |  |  | IN_PROGRESS
Minas | P_4C-26N2 | Minas 02017 | 4C-26N2 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220523DR | 2022-10-20 13:00 | 2022-11-02 13:00 | 2022-11-21 13:00 | COMPLETE
Minas | P_5C-58N | Minas 02020 | 5C-58N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220363DR | 2022-11-21 13:00 | 2022-11-29 18:00 | 2022-12-31 | COMPLETE
Minas | P_7E-94E1 | Minas 02035 | 7E-94E1 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220378DR | 2022-12-31 | 2023-01-09 04:00 | 2023-02-03 15:00 | COMPLETE
Minas | P_7E-95E1 | Minas 02037 | 7E-95E1 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220403DR | 2023-02-03 17:00 | 2023-02-11 08:00 | 2023-03-09 09:00 | COMPLETE
Minas | P_5C-78 | Minas 02044 | 5C-78 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220552DR | 2023-03-09 09:00 | 2023-03-18 | 2023-04-04 06:00 | COMPLETE
Minas | P_5E-96N | Minas 02052 | 5E-96N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220636DR | 2023-04-04 06:00 | 2023-04-17 01:00 | 2023-04-27 21:00 | COMPLETE
Minas | P_5B-21N | Minas 02056 | 5B-21N | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220645DR | 2023-04-27 21:00 | 2023-05-09 20:00 | 2023-06-30 12:00 | COMPLETE
Minas | P_7E-94N | Minas 02063 | 7E-94N | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNT-01 | SSO2/402/3220449DR | 2023-06-29 12:00 |  |  | SUSPENDED
Minas | MNS-P22 | Minas 02011 | 7E-68 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | BNt-TMS#01 | SSO2/402/3220630DR | 2022-08-28 12:00 | 2022-08-28 12:00 | 2022-09-12 11:00 | COMPLETE
Minas | MNS-P03 | Minas 02014 | 9C-66 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | BNt-TMS#01 | SSO2/402/3220510DR | 2022-09-12 11:00 | 2022-10-04 21:30 | 2022-10-20 21:00 | COMPLETE
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Coiled Tubing Unit | CTU-D1 | SSO2/402/3220629DR | 2024-04-05 06:00 | 2024-04-18 22:00 | 2024-05-05 15:00 | IN_PROGRESS
Kotabatak | KTB-X31-HZ | Kotabatak 00525 | N1-O-71 | Stimulation | STM06 - Fracturing | Coiled Tubing Unit | CTU-D1 | SSO2/402/3220629DR | 2024-05-09 08:00 | 2024-04-18 22:00 |  | IN_PROGRESS
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220425DR | 2023-05-14 08:00 | 2023-05-13 02:00 | 2023-05-21 13:00 | COMPLETE
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220419DR | 2023-05-20 11:00 | 2023-05-17 | 2023-05-26 13:00 | COMPLETE
Bangko | BNK_P122C_LQR | Bangko 00407 | N1-W3-26A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220450DR | 2023-05-22 08:00 | 2023-05-15 02:00 | 2023-05-28 13:00 | COMPLETE
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220348DR | 2023-05-26 13:00 | 2023-05-19 08:00 | 2023-06-01 13:00 | COMPLETE
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220434DR | 2023-06-12 08:00 | 2023-06-05 14:00 | 2023-06-19 17:00 | COMPLETE
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220437DR | 2023-06-18 11:00 | 2023-06-13 12:00 | 2023-06-24 18:00 | COMPLETE
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220377DR | 2023-06-25 08:00 | 2023-06-15 03:00 | 2023-07-01 18:00 | COMPLETE
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSO2/402/3220416DR | 2024-06-06 17:00 | 2024-05-20 02:00 | 2024-06-10 16:00 | COMPLETE
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 01 | SSE2/402/3230355DR | 2024-07-09 14:00 | 2024-06-12 16:00 | 2024-07-14 17:00 | SUSPENDED
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220407DR | 2023-07-23 08:00 | 2023-07-20 02:00 | 2023-07-28 | COMPLETE
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220440DR | 2023-07-29 13:00 | 2023-07-27 | 2023-08-04 18:00 | COMPLETE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220407DR | 2023-08-05 09:00 | 2023-07-20 02:00 | 2023-08-11 18:00 | COMPLETE
Balam So | BLSO23-LQR-TE051 | Balam So 00518 | O-O-57C | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220372DR | 2023-10-10 07:00 | 2023-09-21 20:30 |  | COMPLETE
Balam So | BLSO23-LQR-TE007 | Balam So 00517 | O-O-54F | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220554DR | 2023-11-04 14:00 | 2023-10-29 19:00 | 2023-11-09 17:00 | COMPLETE
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220588DR | 2024-02-17 14:00 | 2023-11-15 21:00 | 2024-02-22 16:00 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220548DR | 2024-02-27 09:00 | 2024-05-05 05:00 | 2024-04-24 19:00 | COMPLETE
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSE2/402/3230364DR | 2024-02-28 17:00 | 2024-02-26 20:00 | 2024-03-01 10:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSO2/402/3220383DR | 2024-06-20 18:00 | 2024-06-10 17:00 | 2024-06-26 12:00 | IN_PROGRESS
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Stim/Frac Unit | Frac Fleet - 02 | SSE2/402/3230350DR | 2024-07-11 06:00 | 2024-05-25 10:00 | 2024-07-15 17:00 | SUSPENDED
Kotabatak | KTB-X26 | Kotabatak 00488 | N1-W1-88 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | GRK2/402/3220188DR | 2022-09-06 21:00 | 2022-09-08 11:00 | 2022-09-17 06:00 | COMPLETE
Kotabatak | KB_PL46 | Kotabatak 00497 | N1-W2-39 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220358DR | 2023-01-25 12:00 | 2023-01-26 16:00 | 2023-02-08 23:00 | COMPLETE
Kotabatak | KTB-P1 | Kotabatak 00503 | S2-O-25 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220446DR | 2023-03-18 11:00 | 2023-03-19 02:00 | 2023-03-27 21:00 | COMPLETE
Kotabatak | KB_PL48 | Kotabatak 00506 | O-E1-38 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220369DR | 2023-04-24 11:00 | 2023-04-24 22:00 | 2023-05-03 18:00 | COMPLETE
Kotabatak | KTB-X32-INJ | Kotabatak 00494 | N1-W1-50 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSO2/402/3220522DR | 2023-05-03 18:00 | 2023-02-23 18:00 | 2023-05-11 12:00 | COMPLETE
Kotabatak | KB_PL24 Inj | Kotabatak 00508 | O-E1-59 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSO2/402/3220402DR | 2023-05-16 | 2023-05-16 12:00 | 2023-05-24 10:30 | COMPLETE
Kotabatak | KB_PL31 | Kotabatak 00504 | O-E1-37 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220339DR | 2023-05-29 13:00 | 2023-05-29 22:30 | 2023-06-07 16:00 | COMPLETE
Kotabatak | KB_PL26 | Kotabatak 00509 | O-E1-57 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220360DR | 2023-06-25 | 2023-06-02 10:00 | 2023-07-02 21:00 | COMPLETE
Kotabatak | KB_PL27 | Kotabatak 00510 | O-E1-58 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220380DR | 2023-07-02 21:00 | 2023-06-21 12:00 | 2023-07-09 20:00 | COMPLETE
Kotabatak | KTB-A249 | Kotabatak 00518 | N1-W1-47 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230386DR | 2023-07-09 20:00 | 2023-06-16 05:00 | 2023-07-21 17:00 | COMPLETE
Kotabatak | KTB-X19 | Kotabatak 00505 | N1-W1-53 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220625DR | 2023-07-21 17:00 | 2023-06-06 11:00 | 2023-07-27 18:00 | COMPLETE
Kotabatak | KTB-X20 | Kotabatak 00507 | N1-W1-56 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220627DR | 2023-07-27 18:00 | 2023-06-09 20:00 | 2023-08-05 12:00 | COMPLETE
Kotabatak | KTB-A266 | Kotabatak 00517 | N1-W1-48 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230384DR | 2023-08-05 12:00 | 2023-06-13 02:00 | 2023-08-12 18:00 | COMPLETE
Kotabatak | KB_PL17 Inj | Kotabatak 00529 | O-O-11 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SSE2/402/3230390DR | 2023-08-15 18:00 | 2023-08-16 06:00 | 2023-08-23 | COMPLETE
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230391DR | 2023-08-23 | 2023-08-23 10:00 | 2023-08-25 19:00 | COMPLETE
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220544DR | 2023-08-28 13:00 | 2023-08-29 06:30 | 2023-08-31 16:30 | COMPLETE
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230387DR | 2023-08-31 16:30 | 2023-09-01 | 2023-09-03 13:30 | COMPLETE
Kotabatak | KTB-A138 | Kotabatak 00515 | S1-E1-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220544DR | 2023-09-12 04:00 | 2023-08-29 06:30 | 2023-09-17 10:30 | COMPLETE
Kotabatak | KTB-A122 | Kotabatak 00516 | O-E1-67 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230387DR | 2023-09-17 10:30 | 2023-09-01 | 2023-09-23 06:00 | COMPLETE
Kotabatak | KTB-X29 | Kotabatak 00526 | O-O-15 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230391DR | 2023-09-23 06:00 | 2023-08-23 10:00 | 2023-09-29 | COMPLETE
Kotabatak | KTB-X11 | Kotabatak 00511 | N1-W1-54 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSO2/402/3220426DR | 2023-09-29 | 2023-09-29 17:00 | 2023-10-07 06:00 | COMPLETE
Kotabatak | KTB-A267 | Kotabatak 00519 | N1-W1-49 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SSE2/402/3230388DR | 2023-10-07 06:00 | 2023-10-07 14:00 | 2023-10-13 18:00 | COMPLETE
Kotabatak | KB_PL1 | Kotabatak 00538 | O-W2-19 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230416DR | 2023-10-13 18:00 | 2023-10-14 08:30 | 2023-10-21 14:00 | COMPLETE
Kotabatak | KTB-A98 | Kotabatak 00537 | S1-W1-42 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230430DR | 2023-11-12 11:30 | 2023-11-13 01:00 | 2023-11-19 | COMPLETE
Kotabatak | KB_PL9 | Kotabatak 00535 | S1-W1-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230431DR | 2023-11-28 09:00 | 2023-11-29 02:00 | 2023-12-08 17:00 | COMPLETE
Kotabatak | KTB-A198_INJ | Kotabatak 00536 | S1-W1-43 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230434DR | 2023-12-08 17:00 | 2023-12-09 02:00 | 2023-12-18 18:00 | COMPLETE
Kotabatak | KTB-A185_INJ | Kotabatak 00547 | O-W1-66 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230433DR | 2024-02-19 17:00 | 2024-02-20 13:30 | 2024-02-27 | COMPLETE
Kotabatak | KTB-A010 | Kotabatak 00549 | O-W1-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230417DR | 2024-02-29 04:00 | 2024-03-01 | 2024-03-12 12:00 | COMPLETE
Kotabatak | KTB-A146_INJ | Kotabatak 00550 | O-W1-45 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-06 | SKB2/402/3230432DR | 2024-03-12 12:00 | 2024-03-17 14:00 | 2024-03-26 09:00 | COMPLETE
Kotabatak | KTB-A005 | Kotabatak 00548 | O-W1-40 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-06 | SKB2/402/3230407DR | 2024-03-26 09:00 | 2024-03-27 14:30 | 2024-04-03 | COMPLETE
Minas | MNS-P1 | Minas 01995 | 8D-48S | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | GRK2/402/3220204DR | 2022-04-30 08:00 | 2022-05-01 | 2022-05-06 18:30 | COMPLETE
Bangko | BNK-X16 | Bangko 00400 | N1-W2-68C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | SSO2/402/3220336DR | 2022-12-21 16:30 | 2022-12-26 04:00 | 2023-01-06 07:30 | COMPLETE
Pinang | P_PINA23_P10 | Pinang 00056 | N1-W2-68B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNG2/402/3220838DR | 2023-07-07 22:00 | 2023-07-09 17:00 | 2023-07-27 | COMPLETE
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNA2/402/3220823DR | 2023-07-27 | 2023-07-28 04:00 | 2023-08-05 16:00 | COMPLETE
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-07 | PNG2/402/3220837DR | 2023-08-27 10:00 | 2023-08-28 06:00 | 2023-09-05 04:00 | COMPLETE
Bangko | WFE-BNK_2 | Bangko 00421 | N1-W2-75A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-07 | SSM2/402/3230279DR | 2023-10-20 11:00 | 2023-10-21 07:00 | 2023-10-22 22:00 | COMPLETE
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-09 | GRK2/402/2210008DR | 2022-02-09 | 2022-02-11 22:00 | 2022-02-15 17:00 | COMPLETE
Kotabatak | KTB-X36-INJ | Kotabatak 00513 | N1-W1-37 | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-09 | SSO2/402/3220388DR | 2023-07-25 21:00 | 2023-07-26 09:00 | 2023-07-31 21:00 | COMPLETE
Bangko | BNK-P10 | Bangko 00356 | N1-W1-51A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | GRK2/402/2210039DR | 2021-12-22 | 2021-12-25 14:00 | 2022-01-02 12:00 | COMPLETE
Bangko | BNK-P6 | Bangko 00377 | N1-W2-28A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | GRK2/402/2220065DR | 2022-06-22 12:00 | 2022-06-24 11:00 | 2022-06-30 18:00 | COMPLETE
Bangko | BNK_P169A_LQR | Bangko 00417 | N2-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220413DR | 2023-04-17 22:00 | 2023-04-19 09:00 | 2023-04-27 17:00 | COMPLETE
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220394DR | 2023-05-03 19:00 | 2023-05-05 12:00 | 2023-05-14 18:00 | COMPLETE
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220434DR | 2023-06-04 17:00 | 2023-06-05 14:00 | 2023-06-09 05:00 | COMPLETE
Bangko | BNK_P60E_LQR | Bangko 00424 | N2-W2-27A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220440DR | 2023-08-06 14:30 | 2023-07-27 | 2023-08-11 | COMPLETE
Bangko | BNK_P50A_LQR | Bangko 00418 | N1-W4-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220407DR | 2023-08-13 08:00 | 2023-07-20 02:00 | 2023-08-19 12:00 | COMPLETE
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220390DR | 2023-08-22 12:00 | 2023-08-23 10:00 | 2023-08-26 03:00 | COMPLETE
Bangko | BNK_P26B_LQR | Bangko 00405 | N2-W3-48A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220390DR | 2023-09-11 12:00 | 2023-08-23 10:00 | 2023-09-19 | COMPLETE
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220351DR | 2023-10-23 21:30 | 2022-11-24 21:30 | 2023-11-01 04:00 | COMPLETE
Bangko | BNK_P88B_LQR | Bangko 00426 | O-W2-26B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220457DR | 2023-11-11 | 2023-11-11 16:00 | 2023-11-19 20:30 | COMPLETE
Bangko | WFE-BNK_1 | Bangko 00422 | N1-W2-86A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-12 | SSM2/402/3230276DR | 2023-12-04 06:00 | 2023-12-07 21:00 | 2023-12-09 20:00 | COMPLETE
Bangko | WFE-BNK_6 | Bangko 00432 | N2-W1-82A | Complete | COM04 - Initial Completion Water Injector | Land Workover Unit | GBT-12 | SSM2/402/3230287DR | 2023-12-22 | 2023-12-24 18:00 | 2023-12-27 | COMPLETE
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220415DR | 2024-02-18 23:00 | 2024-02-19 15:00 | 2024-02-26 22:00 | COMPLETE
Bangko | BNK_P55A_LQR | Bangko 00436 | N2-W2-14A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220374DR | 2024-02-29 | 2024-02-29 16:00 | 2024-03-05 23:00 | COMPLETE
Bangko | BNK_P280D_LQR | Bangko 00412 | N2-W1-43A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220373DR | 2024-03-13 | 2023-09-25 14:00 | 2024-03-17 16:00 | COMPLETE
Balam Se | P_BLSE23_P08_PM | Balam Se 00029 | O-O-14C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220576DR | 2024-03-21 18:00 | 2024-03-22 18:00 | 2024-04-03 06:00 | COMPLETE
Balam Se | P_BLSE23_P16_PM | Balam Se 00027 | O-O-76A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSO2/402/3220579DR | 2024-05-04 22:00 | 2024-05-07 04:00 | 2024-05-15 14:00 | COMPLETE
Balam Se | P_BLSE23_P17_PM | Balam Se 00036 | N1-E1-61B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSE2/402/3230308DR | 2024-06-15 15:00 | 2024-06-16 12:00 | 2024-06-29 10:30 | COMPLETE
Balam Se | P_BLSE23_P10_PM | Balam Se 00032 | O-O-46C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-12 | SSE2/402/3230306DR | 2024-06-29 10:30 | 2024-07-01 02:00 | 2024-07-11 10:00 | COMPLETE
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Complete | SQZ03 - Improve Bonding | Land Workover Unit | GBT-17 | GRK2/402/2220061DR | 2022-07-25 | 2022-07-26 04:00 | 2022-07-31 11:00 | COMPLETE
Bangko | BNK-X01 | Bangko 00387 | O-O-21B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220067DR | 2022-07-31 11:00 | 2022-08-01 10:00 | 2022-08-09 17:30 | COMPLETE
Ubi | UBI-X09 | Ubi 00047 | N3-O-84B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220280DR | 2022-08-19 01:00 | 2022-08-20 19:00 | 2022-09-08 22:00 | COMPLETE
Ubi | UBI-X03 | Ubi 00048 | N4-O-84B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220279DR | 2022-09-08 22:00 | 2022-09-09 21:00 | 2022-09-23 10:30 | COMPLETE
Ubi | UBI-X06 | Ubi 00049 | N3-O-37A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | GRK2/402/2220285DR | 2022-09-23 10:30 | 2022-09-30 07:30 | 2022-10-15 | COMPLETE
Ubi | UBI-X10 | Ubi 00051 | N2-O-24B | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | SSO2/402/3220512DR | 2022-10-15 | 2022-10-17 16:00 | 2022-10-22 20:00 | COMPLETE
Bangko | BNK_P94E_LQR | Bangko 00406 | N1-W2-24A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | GBT-17 | SSO2/402/3220431DR | 2023-05-11 10:00 | 2023-05-12 13:00 | 2023-05-20 | COMPLETE
Balam So | P_BLSO24_LQR25 | Balam So 00599 | N1-W1-72C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-336 | SSE2/402/3240403DR | 2024-06-29 23:00 | 2024-06-29 23:00 | 2024-07-10 | COMPLETE
Balam So | P_BLSO24_LQR03 | Balam So 00603 | N1-W1-72D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-336 | SSE2/402/3230347DR | 2024-07-10 |  |  | IN_PROGRESS
Balam So | P_BLSO24_LQR_P22 | Balam So 00598 | S1-O-36B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-337 | SSE2/402/3240402DR | 2024-06-26 | 2024-06-27 16:00 | 2024-07-07 02:30 | COMPLETE
Balam So | P_BLSO24_P04 | Balam So 00606 | N1-W1-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-337 | SSO2/402/3240282DR | 2024-07-07 02:30 |  |  | IN_PROGRESS
Balam So | P_BLSO24_LQR37 | Balam So 00600 | O-W1-35D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-338 | SSE2/402/3240415DR | 2024-06-30 23:00 | 2024-06-30 23:00 | 2024-07-11 | COMPLETE
Balam So | P_BLSO24_LQR_P14 | Balam So 00605 | N1-W1-77G | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-338 | SSE2/402/3240397DR | 2024-07-11 |  |  | IN_PROGRESS
Pematang | P_PEMA24_14 | Pematang 00136 | O-O-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSA2/402/3230163DR | 2024-04-20 18:00 | 2024-04-20 18:00 | 2024-05-11 | COMPLETE
Balam Se | P_BLSE24_P02 | Balam Se 00043 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSE2/402/3240646DR | 2024-05-11 | 2024-05-24 19:00 | 2024-06-14 03:30 | COMPLETE
Balam So | P_BLSO24_P03 | Balam So 00601 | O-O-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSO2/402/3240281DR | 2024-06-13 03:30 | 2024-06-20 06:00 | 2024-07-02 05:00 | COMPLETE
Balam So | P_BLSO24_LQR19 | Balam So 00602 | N1-O-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | GW-339 | SSE2/402/3240401DR | 2024-07-02 05:00 | 2024-07-08 09:00 |  | IN_PROGRESS
Kelok Ne | P_KENE_P02 | Kelok NE 00004 | O-O-44B | Perforation Initial | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-08 | KEN2/402/3220807DR | 2023-03-05 05:00 | 2023-03-10 02:00 | 2023-03-18 02:00 | COMPLETE
Pager | PG22-P06 | Pager 00052 | O-O-53C | Fishing | FIS01 - Fishing Job | Land Workover Unit | IDB-09 | SSO2/402/3220331DR | 2022-12-26 | 2022-12-26 18:00 | 2022-12-29 19:00 | COMPLETE
Pager | PG22-P06 | Pager 00052 | O-O-53C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220331DR | 2023-02-03 15:00 | 2023-02-04 15:00 | 2023-03-10 14:00 | COMPLETE
Pager | PG22-P17 | Pager 00054 | O-O-22A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220385DR | 2023-10-08 13:00 | 2023-10-10 01:00 | 2023-10-23 22:00 | COMPLETE
Pager | PGR23-P03 | Pager 00057 | O-O-33A | Pump Repair | PMP14 - Change Pump Type Normal | Land Workover Unit | IDB-09 | PGR2/402/3230446DR | 2023-10-23 22:00 | 2023-10-26 21:00 | 2023-10-29 | COMPLETE
Pager | PG22-P16 | Pager 00051 | O-O-13A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220322DR | 2023-12-15 | 2023-12-16 03:00 | 2024-01-02 01:45 | COMPLETE
Pager | PGR23-P04 | Pager 00061 | O-O-85A | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | PGR2/402/3230447DR | 2024-03-09 07:00 | 2024-03-13 19:00 | 2024-03-20 | COMPLETE
Pager | PG22-P05 | Pager 00055 | O-O-54C | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | IDB-09 | SSO2/402/3220354DR | 2024-04-30 23:00 | 2024-05-01 18:30 | 2024-05-21 12:30 | COMPLETE
Bangko | Bangko P01 | Bangko 00343 | N1-W2-57A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210093DR | 2021-10-20 09:00 |  | 2021-10-22 15:00 | COMPLETE
Bekasap | BKS-P6 | Bekasap 00205 | S1-O-28A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210018DR | 2022-01-07 08:00 |  | 2022-01-09 18:00 | COMPLETE
Bekasap | BKS-P14 | Bekasap 00204 | O-E1-41C | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210008DR | 2022-01-11 09:00 |  | 2022-01-13 18:00 | COMPLETE
Bangko | BNK-P36 | Bangko 00364 | N1-W1-48B | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2210065DR | 2022-02-08 11:00 | 2022-02-10 17:00 | 2022-02-09 16:30 | COMPLETE
Minas | MNS-P10 | Minas 01992 | 8E-83E | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3210108DR | 2022-04-01 09:00 |  | 2022-04-03 15:00 | COMPLETE
Minas | MNS-P1 | Minas 01995 | 8D-48S | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3220204DR | 2022-04-18 08:00 |  | 2022-04-19 15:00 | COMPLETE
Minas | MNA-P7 | Minas 01993 | 8E-61N | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/3220202DR | 2022-05-12 13:30 |  | 2022-05-14 13:00 | COMPLETE
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck | GRK2/402/2220061DR | 2022-08-18 06:00 |  | 2022-08-18 18:00 | COMPLETE
Pager | PG22-P16 | Pager 00051 | O-O-13A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck | SSO2/402/3220322DR | 2022-11-18 10:00 |  | 2022-11-19 15:30 | COMPLETE
Pager | PG22-P06 | Pager 00052 | O-O-53C | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck | SSO2/402/3220331DR | 2022-11-30 08:30 |  | 2022-12-02 19:00 | COMPLETE
Duri | 2J-0712B | Duri 11127 | 2J-0712B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220746DR | 2024-01-27 08:30 |  | 2024-01-28 15:30 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | Mast Truck-01 | SSO2/402/3220548DR | 2024-04-22 05:00 | 2024-05-05 05:00 | 2024-04-22 19:00 | COMPLETE
Duri | 2J-0210B | Duri 11174 | 2J-0210B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220781DR | 2024-05-11 09:00 |  | 2024-05-12 16:00 | COMPLETE
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | Mast Truck-01 | SSO2/402/3220416DR | 2024-06-08 13:00 | 2024-05-20 02:00 | 2024-06-09 01:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSO2/402/3220383DR | 2024-06-22 08:00 | 2024-06-10 17:00 | 2024-06-23 13:00 | IN_PROGRESS
Duri | 3J-0101A | Duri 11167 | 3J-0101A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-01 | RHO2/402/2220790DR | 2024-07-01 12:45 |  | 2024-07-01 17:00 | COMPLETE
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSE2/402/3230355DR | 2024-07-12 05:00 | 2024-06-12 16:00 | 2024-07-12 13:30 | SUSPENDED
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | Electric Line Unit | Mast Truck-01 | SSE2/402/3230350DR | 2024-07-13 07:00 | 2024-05-25 10:00 | 2024-07-13 14:00 | SUSPENDED
Duri | 2H-0507B | Duri 11074 | 2H-0507B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220734DR | 2023-07-21 14:00 |  | 2023-07-22 18:00 | COMPLETE
Duri | 2J-0411B | Duri 11082 | 2J-0411B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220766DR | 2023-09-15 11:30 |  | 2023-09-17 17:15 | COMPLETE
Duri | 2J-0911A | Duri 11081 | 2J-0911A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220739DR | 2023-10-14 11:00 |  | 2023-10-21 16:30 | COMPLETE
Duri | 2H-1111A | Duri 11117 | 2H-1111A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220792DR | 2023-11-02 13:00 |  | 2023-11-02 18:00 | COMPLETE
Duri | 2J-0111A | Duri 11116 | 2J-0111A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220770DR | 2023-11-03 10:00 |  | 2023-11-03 18:00 | COMPLETE
Duri | 2J-0711A | Duri 11115 | 2J-0711A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220744DR | 2023-11-04 13:00 |  | 2023-11-04 18:00 | COMPLETE
Kotabatak | KB_PL40 Inj | Kotabatak 00543 | O-E1-60 | Logging | LOG14 - Run Temperature And CBL/ USIT Log | Mast Unit | Mast Truck-02 | SSE2/402/3230397DR | 2023-12-19 11:30 |  | 2023-12-19 17:00 | SUSPENDED
Duri | 2J-0413B | Duri 11134 | 2J-0413B | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220765DR | 2024-01-29 11:30 |  | 2024-01-30 18:00 | COMPLETE
Duri | 2J-0812A | Duri 11133 | 2J-0812A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220747DR | 2024-01-31 10:00 |  | 2024-01-31 15:00 | COMPLETE
Duri | 2J-0612A | Duri 11124 | 2J-0612A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220752DR | 2024-02-01 09:00 | 2024-02-01 18:00 | 2024-02-01 15:00 | COMPLETE
Duri | 2J-0212A | Duri 11166 | 2J-0212A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220780DR | 2024-05-19 09:00 |  | 2024-05-19 15:00 | COMPLETE
Duri | 2J-0311A | Duri 11178 | 2J-0311A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220772DR | 2024-07-11 13:00 |  | 2024-07-11 17:00 | COMPLETE
Duri | 3J-0301A | Duri 11160 | 3J-0301A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220774DR | 2024-07-12 10:00 |  | 2024-07-12 15:00 | COMPLETE
Duri | 3H-1101A | Duri 11159 | 3H-1101A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-02 | RHO2/402/2220785DR | 2024-07-13 10:00 |  | 2024-07-13 15:00 | COMPLETE
Minas | P_8D-56N1 | Minas 02068 | 8D-56N1 | Logging | LOG03 - Carbon Oxygen Log | Mast Unit | Mast Truck-03 | SSM2/402/3230246DR | 2023-07-08 09:00 |  | 2023-07-10 18:00 | COMPLETE
Duri | 2J-0511A | Duri 11144 | 2J-0511A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220760DR | 2024-04-26 09:00 |  | 2024-04-26 14:00 | COMPLETE
Duri | 3J-0501A | Duri 11145 | 3J-0501A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220755DR | 2024-04-27 09:00 |  | 2024-04-27 14:00 | COMPLETE
Duri | 2H-1212A | Duri 11135 | 2H-1212A | Logging | LOG14 - Run Temperature And CBL/ Usit Log | Mast Unit | Mast Truck-03 | RHO2/402/2220798DR | 2024-05-01 11:00 |  | 2024-05-01 15:00 | COMPLETE
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Logging | LOG04 - Cased Hole Formation Log | Mast Unit | Mast Truck-03 | PNE2/402/2220002EX | 2024-05-23 09:00 |  | 2024-05-24 13:30 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer |  | OMS | SSO2/402/3220383DR | 2024-06-22 05:00 | 2024-06-10 17:00 | 2024-06-22 08:00 | IN_PROGRESS
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Land Workover Unit | PDSI-35.1 | MBS2/402/3230833EX | 2024-05-03 18:00 | 2024-05-16 | 2024-06-09 14:30 | COMPLETE
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2023-07-27 12:00 | 2023-07-27 12:00 | 2023-11-10 04:00 | RELEASE
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2023-11-10 04:00 | 2023-11-10 04:00 | 2023-12-19 05:30 | SUSPENDED
Kelok | P01_KL17 | Kelok 00016 | O-O-61 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-42.3 | KLK2/402/2220003EX | 2023-12-19 05:30 | 2024-02-14 18:00 | 2024-05-20 10:00 | COMPLETE
Kelok | P01_KL17 | Kelok 00016 | O-O-61 | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | KLK2/402/2220003EX | 2024-05-20 10:00 | 2024-05-20 10:00 | 2024-06-28 13:00 | SUSPENDED
Gulamo | P_GULA22_P01 | Gulamo 00008 | O-O-24B | Complete | COM01 - Initial Completion | Land Drilling Rig | PDSI-42.3 | GLM2/402/2220004EX | 2024-06-28 13:00 | 2024-07-14 15:00 |  | IN_PROGRESS
Bangko | BNKO21-P01 | Bangko 00345 | N1-W2-68A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210036DR | 2021-08-29 13:00 | 2021-08-29 13:00 | 2021-09-13 06:30 | COMPLETE
Bangko | BNKO21-P01 | Bangko 00345 | N1-W2-68A | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210036DR | 2021-09-13 06:30 | 2021-09-13 06:30 | 2021-09-15 09:00 | COMPLETE
Bangko | Bangko P25 | Bangko 00350 | O-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210030DR | 2021-09-15 09:00 | 2021-09-27 01:30 | 2021-10-10 05:00 | COMPLETE
Bangko | BNK-P31 | Bangko 00355 | N1-W3-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210060DR | 2021-10-10 05:00 | 2021-10-16 12:00 | 2021-10-27 16:00 | COMPLETE
Bangko | BNK-P32 | Bangko 00352 | N1-W3-28A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210061DR | 2021-10-27 16:00 | 2021-11-03 01:00 | 2021-11-14 07:00 | RELEASE
Bangko | BNK-P14 | Bangko 00360 | N1-W1-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210042DR | 2021-11-14 07:00 | 2021-11-20 02:00 | 2021-11-29 20:00 | COMPLETE
Bangko | BNK-P27 | Bangko 00379 | N1-W1-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210055DR | 2021-11-29 20:00 | 2021-12-08 08:00 | 2021-12-21 | COMPLETE
Bangko | BNK-P33 | Bangko 00367 | N1-W1-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210067DR | 2021-12-21 | 2022-01-14 18:00 | 2022-01-25 07:30 | COMPLETE
Bangko | BNK-P28 | Bangko 00373 | N1-W1-64A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210056DR | 2022-01-25 07:30 | 2022-01-28 05:00 | 2022-02-08 10:00 | COMPLETE
Balam So | BLSO-P28 | Balam So 00449 | N1-W1-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220012DR | 2022-02-08 10:00 | 2022-02-17 02:00 | 2022-02-27 21:00 | COMPLETE
Balam So | BLSO-P30 | Balam So 00453 | S1-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220018DR | 2022-02-27 21:00 | 2022-03-07 03:00 | 2022-03-14 18:00 | COMPLETE
Balam So | BLSO-P25 | Balam So 00458 | N1-W1-67B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220019DR | 2022-03-14 18:00 | 2022-03-22 05:00 | 2022-03-30 13:00 | COMPLETE
Balam So | BLSO-P26 | Balam So 00462 | N1-W1-67C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220024DR | 2022-03-30 13:00 | 2022-04-02 01:00 | 2022-04-10 14:00 | RELEASE
Bangko | BNK-P29 | Bangko 00383 | N2-W2-77A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2210057DR | 2022-04-10 14:00 | 2022-04-17 23:00 | 2022-04-29 18:00 | COMPLETE
Bangko | BNK-P17 | Bangko 00385 | O-O-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220061DR | 2022-04-29 18:00 | 2022-05-05 01:00 | 2022-05-17 03:30 | RELEASE
Puncak | PNC-P04 | Puncak 00042 | O-O-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220273DR | 2022-05-17 03:30 | 2022-05-27 08:00 | 2022-06-08 | COMPLETE
Puncak | PNC-P05 | Puncak 00043 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220274DR | 2022-06-08 | 2022-06-10 15:30 | 2022-06-22 | COMPLETE
Puncak | PNC-P01 | Puncak 00044 | O-O-53A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220270DR | 2022-06-22 | 2022-06-27 22:30 | 2022-07-10 16:00 | COMPLETE
Puncak | PNC-P02 | Puncak 00045 | O-O-42A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220271DR | 2022-07-10 16:00 | 2022-07-15 08:00 | 2022-07-28 03:30 | COMPLETE
Bekasap | BKS-X14 | Bekasap 00220 | O-E1-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | GRK2/402/2220275DR | 2022-07-28 03:30 | 2022-08-05 22:30 | 2022-08-16 07:00 | RELEASE
Bekasap | BKS-X13 | Bekasap 00221 | O-E1-65B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220320DR | 2022-08-16 07:00 | 2022-08-18 16:00 | 2022-08-28 08:00 | COMPLETE
Bekasap | BKS-X12 | Bekasap 00222 | O-O-48B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220332DR | 2022-08-28 08:00 | 2022-09-02 07:00 | 2022-10-06 11:30 | RELEASE
Bekasap | BKS-X09 | Bekasap 00223 | O-O-48C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220343DR | 2022-10-06 11:30 | 2022-10-10 23:30 | 2022-10-31 | COMPLETE
Bekasap | BKS-X01 | Bekasap 00224 | O-O-73B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220365DR | 2022-10-31 | 2022-11-05 19:00 | 2022-11-21 03:00 | COMPLETE
Bekasap | BKS-X05 | Bekasap 00225 | O-E1-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220611DR | 2022-11-21 03:00 | 2022-11-25 18:00 | 2022-12-11 10:00 | COMPLETE
Bekasap | P_BK22_S1 | Bekasap 00226 | S1-E2-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SOB2/402/3220815DR | 2022-12-11 10:00 | 2022-12-18 14:00 | 2023-01-06 22:30 | COMPLETE
Bekasap | BKS-X07 | Bekasap 00227 | S1-O-15D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220613DR | 2023-01-06 22:30 | 2023-01-12 12:00 | 2023-01-25 21:00 | COMPLETE
Puncak | PNC-P03 | Puncak 00046 | O-O-53B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220546DR | 2023-01-25 21:00 | 2023-02-02 11:00 | 2023-02-23 03:00 | COMPLETE
Puncak | PNC-P06 | Puncak 00047 | O-O-34C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220410DR | 2023-02-23 03:00 | 2023-03-06 23:00 | 2023-03-18 11:00 | COMPLETE
Puncak | PNC-P07 | Puncak 00048 | O-O-24A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220428DR | 2023-03-18 11:00 | 2023-03-24 06:30 | 2023-04-05 02:30 | COMPLETE
Pinang | P_PINA23_P10 | Pinang 00056 | N1-W2-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220838DR | 2023-04-05 02:30 | 2023-04-20 23:00 | 2023-05-06 05:00 | RELEASE
Pinang | P_PINA23_P03 | Pinang 00057 | N1-W2-68C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNA2/402/3220822DR | 2023-05-06 05:00 | 2023-05-09 18:00 | 2023-05-25 05:00 | COMPLETE
Pinang | P_PINA23_P88 | Pinang 00058 | N1-W2-68D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220843DR | 2023-05-25 05:00 | 2023-05-28 18:30 | 2023-06-12 13:00 | COMPLETE
Pinang | P_PINA23_P02 | Pinang 00060 | N1-W2-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220836DR | 2023-06-12 13:00 | 2023-06-17 08:00 | 2023-07-04 18:30 | COMPLETE
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNG2/402/3220837DR | 2023-07-03 18:30 | 2023-07-08 23:00 | 2023-07-25 11:00 | RELEASE
Balam So | BLSO23-LQR-TE010 | Balam So 00541 | O-O-11A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220530DR | 2023-07-25 11:00 | 2023-08-05 18:00 | 2023-08-10 23:00 | COMPLETE
Balam Se | P_BLSE23_P16_PM | Balam Se 00027 | O-O-76A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220579DR | 2023-08-10 23:00 | 2023-08-17 06:00 | 2023-08-30 07:00 | COMPLETE
Balam Se | P_BLSE23_P24_PM | Balam Se 00028 | O-O-76B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220578DR | 2023-08-30 07:00 | 2023-09-03 03:30 | 2023-09-15 20:00 | COMPLETE
Bangko | BNK23_P24 | Bangko 00427 | N1-W2-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSM2/402/3230274DR | 2023-09-15 20:00 | 2023-09-24 16:30 | 2023-10-03 16:00 | RELEASE
Bangko | BNK23_P01 | Bangko 00431 | O-O-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSM2/402/3230268DR | 2023-10-03 16:00 | 2023-10-10 13:30 | 2023-10-20 22:00 | COMPLETE
Balam So | LQR-TE212_BLSO_52 | Balam So 00558 | N1-W1-66D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230368DR | 2023-10-20 22:00 | 2023-10-28 19:00 | 2023-11-04 05:00 | COMPLETE
Balam So | LQR-TE012_BLSO_34 | Balam So 00559 | N1-W1-66E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220357DR | 2023-11-04 05:00 | 2023-11-08 | 2023-11-13 13:00 | COMPLETE
Balam Se | P_BLSE23_P05_MN | Balam Se 00033 | O-O-11 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230314DR | 2023-11-13 13:00 | 2023-11-22 17:00 | 2023-12-24 21:00 | RELEASE
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNE2/402/2220002EX | 2023-12-24 21:00 | 2024-03-14 23:30 | 2023-12-29 | COMPLETE
Balam So | BLSO23-LQR-TE018 | Balam So 00577 | N1-W1-88B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230354DR | 2023-12-29 17:00 | 2024-01-25 14:00 | 2024-01-30 10:45 | COMPLETE
Balam So | BLSO23-LQR-TE058 | Balam So 00578 | N1-W1-88C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230352DR | 2024-01-30 10:45 | 2024-02-02 06:00 | 2024-02-06 14:00 | COMPLETE
Balam So | BLSO23-LQR-TE008 | Balam So 00579 | N1-W1-88D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSE2/402/3230353DR | 2024-02-06 14:00 | 2024-02-10 | 2024-02-16 05:00 | COMPLETE
Pinang East | Exp_P01_Pinang | Pinang East 00001 | O-O-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | PNE2/402/2220002EX | 2024-02-16 05:00 | 2024-03-14 23:30 | 2024-04-03 | COMPLETE
Benar | P_BENA22-P04 | Benar 00074 | O-W1-87 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SBN2/402/3220845DR | 2024-05-23 20:00 | 2024-05-23 20:00 | 2024-05-31 16:00 | RELEASE
Bangko | BNK_PX04F_LQR | Bangko 00446 | N2-W3-85 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | SSO2/402/3220608DR | 2024-05-31 16:00 | 2024-06-08 12:00 | 2024-06-15 | COMPLETE
Bangko | BNK_PX05A_LQR | Bangko 00450 | N2-W3-85C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240903DR | 2024-06-15 | 2024-06-20 | 2024-06-27 10:30 | COMPLETE
Bangko | BNK_PX04E_LQR | Bangko 00449 | N2-W3-85B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240902DR | 2024-06-27 10:30 | 2024-07-02 14:00 | 2024-07-09 02:00 | COMPLETE
Bangko | BNK_PX05_LQR | Bangko 00451 | N2-W3-85D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-49.2 | DBK2/402/2240901DR | 2024-07-09 02:00 | 2024-07-13 12:30 |  | IN_PROGRESS
Balam So | BLSO23-LQR-TE070 | Balam So 00524 | N1-O-83E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220417DR | 2023-05-13 | 2023-05-13 | 2023-05-25 12:00 | COMPLETE
Balam So | BLSO23-LQR-TE034 | Balam So 00528 | N1-O-83F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220535DR | 2023-05-25 12:00 | 2023-05-31 23:30 | 2023-06-11 14:30 | COMPLETE
Balam So | BLSO23-LQR-TE019 | Balam So 00532 | O-W1-27A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220587DR | 2023-06-11 15:30 | 2023-06-21 11:00 | 2023-07-03 17:00 | COMPLETE
Balam So | BLSO23-LQR-TE024 | Balam So 00537 | O-O-75A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220439DR | 2023-07-03 17:00 | 2023-07-15 11:00 | 2023-07-22 05:00 | RELEASE
Balam So | BLSO23-LQR-TE068 | Balam So 00536 | O-O-75B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220406DR | 2023-07-22 05:00 | 2023-07-25 23:00 | 2023-07-31 11:00 | COMPLETE
Bangko | WFE-BNK_2 | Bangko 00421 | N1-W2-75A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230279DR | 2023-07-31 11:00 | 2023-08-09 17:30 | 2023-08-22 17:00 | COMPLETE
Bangko | WFE-BNK_1 | Bangko 00422 | N1-W2-86A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230276DR | 2023-08-22 17:00 | 2023-08-27 03:00 | 2023-09-06 12:30 | COMPLETE
Bangko | WFE-BNK_5 | Bangko 00423 | N2-W1-51A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230286DR | 2023-09-06 12:30 | 2023-09-12 20:00 | 2023-09-29 12:00 | COMPLETE
Bangko | WFE-BNK_4 | Bangko 00429 | O-O-33B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230284DR | 2023-09-29 12:00 | 2023-10-11 11:00 | 2023-10-21 21:00 | COMPLETE
Bangko | BNK23_P07 | Bangko 00434 | O-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSM2/402/3230271DR | 2023-10-21 21:00 | 2023-10-27 08:00 | 2023-11-14 | COMPLETE
Bangko | BNK_P55A_LQR | Bangko 00436 | N2-W2-14A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220374DR | 2023-11-14 | 2023-11-28 14:00 | 2023-12-07 06:00 | COMPLETE
Balam So | LQR-TE211_BLSO_22 | Balam So 00569 | N1-W1-66C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230367DR | 2023-12-07 06:00 | 2023-12-18 05:00 | 2023-12-27 12:00 | COMPLETE
Balam So | LQR-TE014_BLSO_25 | Balam So 00570 | N1-W1-66F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230369DR | 2023-12-27 12:00 | 2023-12-30 23:00 | 2024-01-07 17:00 | COMPLETE
Balam So | LQR-TE021_BLSO_23 | Balam So 00580 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220538DR | 2024-01-07 17:00 | 2024-01-21 06:00 | 2024-02-07 10:00 | COMPLETE
Balam So | LQR-TE133_BLSO_31 | Balam So 00581 | N1-O-61B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230373DR | 2024-02-07 10:00 | 2024-02-10 16:00 | 2024-02-21 05:30 | COMPLETE
Balam So | LQR-TE023_BLSO_24 | Balam So 00582 | N1-O-61C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220330DR | 2024-02-21 05:30 | 2024-02-28 14:15 | 2024-03-07 18:00 | COMPLETE
Balam So | P_BLSO24_P06 | Balam So 00591 | N1-W1-61C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3240283DR | 2024-03-07 18:00 | 2024-03-17 09:00 | 2024-03-25 14:00 | COMPLETE
Balam So | BLSO23-P01 | Balam So 00592 | N1-W1-61D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3220596DR | 2024-03-25 14:00 | 2024-03-29 | 2024-04-07 | COMPLETE
Balam So | LQR-TE215_BLSO_45 | Balam So 00595 | N1-W1-74F | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230328DR | 2024-06-12 06:00 | 2024-06-22 13:00 | 2024-06-30 17:00 | COMPLETE
Balam So | LQR-TE214_BLSO_49 | Balam So 00596 | N1-W1-74E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSE2/402/3230325DR | 2024-06-30 17:00 | 2024-07-03 21:00 | 2024-07-10 18:00 | COMPLETE
Balam So | P_BLSO24_P20 | Balam So 00597 | N1-W1-74J | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-50.2 | SSO2/402/3240289DR | 2024-07-10 18:00 |  |  | IN_PROGRESS
Bangko | BNKO21-P06 | Bangko 00346 | S1-O-11B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210037DR | 2021-08-23 22:00 | 2021-08-23 23:00 | 2021-09-08 13:00 | COMPLETE
Bangko | BNKO21-P06 | Bangko 00346 | S1-O-11B | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210037DR | 2021-09-08 13:00 | 2021-09-08 13:00 | 2021-09-10 13:30 | COMPLETE
Seruni | SERU21-P01 | Seruni 00050 | N2-W3-56C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210159DR | 2021-09-10 13:30 | 2021-09-19 15:00 | 2021-10-02 10:00 | COMPLETE
Bangko | BNK-P25 | Bangko 00353 | N1-W1-11A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210053DR | 2021-10-02 10:00 | 2021-10-11 05:00 | 2021-10-23 01:30 | COMPLETE
Bangko | BNK-P9 | Bangko 00363 | N1-W2-45A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210074DR | 2021-10-23 01:30 | 2021-10-29 05:00 | 2021-11-10 16:30 | COMPLETE
Bangko | BNK-P20 | Bangko 00357 | O-O-85A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210048DR | 2021-11-10 16:30 | 2021-11-17 04:00 | 2021-11-29 04:00 | COMPLETE
Bangko | BNK-P15 | Bangko 00368 | O-O-63C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210043DR | 2021-11-29 04:00 | 2021-12-04 03:30 | 2021-12-15 22:00 | COMPLETE
Bangko | BNK-P18 | Bangko 00372 | O-O-64B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210046DR | 2021-12-15 22:00 | 2022-01-15 02:00 | 2022-01-26 23:00 | COMPLETE
Bangko | BNK-P16 | Bangko 00376 | O-O-74C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210044DR | 2022-01-26 23:00 | 2022-01-31 23:30 | 2022-02-12 15:00 | COMPLETE
Bangko | BNK-P23 | Bangko 00384 | N1-W2-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220059DR | 2022-02-12 15:00 | 2022-02-20 03:30 | 2022-03-04 02:30 | COMPLETE
Balam So | BLSO-P31 | Balam So 00455 | S1-O-45C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220023DR | 2022-03-04 02:30 | 2022-03-12 18:00 | 2022-03-20 12:00 | RELEASE
Balam So | BLSO-P07 | Balam So 00461 | O-O-48A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220003DR | 2022-03-20 12:00 | 2022-03-25 23:00 | 2022-04-02 13:30 | COMPLETE
Balam So | BLSO-P12 | Balam So 00465 | N1-O-76A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220013DR | 2022-04-02 13:30 | 2022-04-08 04:15 | 2022-04-16 | COMPLETE
Bangko | BNK-P19 | Bangko 00375 | O-O-86B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2210047DR | 2022-04-16 | 2022-04-23 01:00 | 2022-05-05 02:30 | COMPLETE
Bangko | BNK-X08 | Bangko 00386 | O-W1-68A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220062DR | 2022-05-05 02:30 | 2022-05-11 | 2022-05-22 21:00 | COMPLETE
Bangko | BNK-X10 | Bangko 00388 | S1-E1-57A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220064DR | 2022-05-22 21:00 | 2022-05-30 13:45 | 2022-06-10 16:00 | COMPLETE
Bangko | BNK-X11 | Bangko 00390 | S1-E2-63A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220066DR | 2022-06-10 16:00 | 2022-06-17 13:00 | 2022-07-03 14:00 | COMPLETE
Bangko | BNK-X13 | Bangko 00392 | S1-E2-63B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220076DR | 2022-07-03 14:00 | 2022-07-07 02:00 | 2022-07-20 07:00 | COMPLETE
Bangko | BNK-X12 | Bangko 00394 | S1-E2-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | GRK2/402/2220074DR | 2022-07-20 07:00 | 2022-07-25 18:00 | 2022-08-05 12:00 | COMPLETE
Bangko | BNK-X17 | Bangko 00396 | O-W1-37A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220503DR | 2022-08-05 12:00 | 2022-08-11 | 2022-08-23 02:30 | COMPLETE
Bangko | BNK-X15 | Bangko 00398 | N1-W2-68B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220517DR | 2022-08-23 02:30 | 2022-08-30 | 2022-09-11 13:00 | COMPLETE
Bangko | BNK_P45A_LQR | Bangko 00402 | N2-W2-62A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220351DR | 2022-09-11 13:00 | 2022-09-20 20:00 | 2022-10-01 02:00 | RELEASE
Bangko | BNK-X16 | Bangko 00400 | N1-W2-68C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220336DR | 2022-10-01 02:00 | 2022-10-10 15:00 | 2022-10-21 18:30 | RELEASE
Bangko | BNK-X09 | Bangko 00401 | O-O-85B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220353DR | 2022-10-21 18:30 | 2022-10-28 14:00 | 2022-11-09 | COMPLETE
Bangko | BNK_P82A_LQR | Bangko 00403 | N1-W3-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220425DR | 2022-11-09 | 2022-11-15 23:30 | 2022-11-25 14:00 | RELEASE
Bangko | BNK_P141C_LQR | Bangko 00404 | N1-W2-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220434DR | 2022-11-25 14:00 | 2022-12-01 22:30 | 2022-12-10 12:00 | RELEASE
Bangko | BNK_P270A_LQR | Bangko 00419 | N1-W3-35A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220415DR | 2022-12-10 12:00 | 2022-10-20 19:00 | 2022-12-27 18:30 | COMPLETE
Bangko | BNK_P277B_LQR | Bangko 00409 | N1-W4-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220366DR | 2022-12-27 18:30 | 2023-01-02 12:00 | 2023-01-11 18:00 | COMPLETE
Bangko | BNK_P36B_LQR | Bangko 00411 | N1-W3-73A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220419DR | 2023-01-11 18:00 | 2023-01-16 12:00 | 2023-01-25 22:00 | RELEASE
Bangko | BNK_P244A_LQR | Bangko 00414 | N1-W3-41A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220398DR | 2023-01-25 22:00 | 2023-02-02 15:00 | 2023-02-21 09:00 | RELEASE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220383DR | 2023-02-21 09:00 | 2023-02-28 02:30 | 2023-03-10 | RELEASE
Benar | P_BENA23B_P01 | Benar 00068 | N2-O-57B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3220506DR | 2023-03-10 | 2023-03-20 18:00 | 2023-03-30 02:30 | COMPLETE
Ubi | UBI-X05 | Ubi 00052 | N4-O-84C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220918DR | 2023-03-30 02:30 | 2023-04-08 18:30 | 2023-04-23 05:00 | RELEASE
Ubi | UBI-X11 | Ubi 00053 | N3-O-34A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220919DR | 2023-04-23 05:00 | 2023-05-01 02:30 | 2023-05-25 01:00 | RELEASE
Benar | P_BENA22-P03 | Benar 00071 | O-E1-32B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220844DR | 2023-05-25 01:00 | 2023-06-04 15:30 | 2023-06-26 12:00 | RELEASE
Benar | P_BENA23B_P02 | Benar 00072 | N2-O-66A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220850DR | 2023-06-26 12:00 | 2023-07-03 14:00 | 2023-07-13 15:30 | COMPLETE
Benar | P_BENA23B_P03 | Benar 00073 | N2-O-58A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SBN2/402/3220851DR | 2023-07-13 15:30 | 2023-07-19 10:30 | 2023-07-28 18:00 | COMPLETE
Ubi | UBI-X13 | Ubi 00054 | N1-W1-18A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSA2/402/3220920DR | 2023-07-28 18:00 | 2023-08-12 03:00 | 2023-08-24 08:00 | COMPLETE
Pager | PGR23-P03 | Pager 00057 | O-O-33A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230446DR | 2023-08-24 08:00 | 2023-09-07 17:30 | 2023-09-22 15:00 | COMPLETE
Pager | PGR23-P05 | Pager 00058 | O-O-33B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230448DR | 2023-09-22 15:00 | 2023-09-27 15:00 | 2023-10-13 12:00 | COMPLETE
Pager | PGR23-P01 | Pager 00059 | N1-O-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230444DR | 2023-10-13 12:00 | 2023-10-18 20:00 | 2023-11-03 01:30 | COMPLETE
Pager | PGR23-P02 | Pager 00060 | N1-O-52A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230445DR | 2023-11-03 01:30 | 2023-11-08 09:00 | 2023-11-23 05:30 | COMPLETE
Pager | PGR23-P04 | Pager 00061 | O-O-85A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230447DR | 2023-11-23 05:30 | 2023-11-29 20:00 | 2023-12-12 18:30 | COMPLETE
Pager | P_PAGE24_01 | Pager 00062 | O-O-73C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230451DR | 2023-12-12 18:30 | 2023-12-22 17:30 | 2024-02-22 16:00 | COMPLETE
Pager | PGR23-P06 | Pager 00063 | O-O-22B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230449DR | 2024-02-22 16:00 | 2024-02-28 18:30 | 2024-03-15 12:00 | COMPLETE
Pager | P_PAGE24_03 | Pager 00064 | N1-O-61A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230453DR | 2024-03-15 12:00 | 2024-03-21 09:00 | 2024-04-04 13:00 | COMPLETE
Pager | PGR23-P07 | Pager 00065 | N1-O-61B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230450DR | 2024-04-04 13:00 | 2024-04-08 10:30 | 2024-04-22 14:30 | COMPLETE
Pager | P_PAGE24_02 | Pager 00066 | N1-O-82A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | PGR2/402/3230452DR | 2024-06-21 01:00 | 2024-06-21 01:00 | 2024-07-07 21:00 | COMPLETE
Balam So | P_BLSO24_P19 | Balam So 00608 | O-O-15E | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-51.2 | SSO2/402/3240288DR | 2024-07-07 21:00 |  |  | IN_PROGRESS
Bekasap | P01_BK21 | Bekasap 00196 | O-O-84D | Complete | COM02 - Initial Completion Oil Producer | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210001DR | 2021-02-20 | 2021-08-27 19:00 | 2021-08-30 14:00 | COMPLETE
Bekasap | P01_BK21 | Bekasap 00196 | O-O-84D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210001DR | 2021-08-15 22:00 | 2021-08-15 22:00 | 2021-08-27 19:00 | COMPLETE
Pungut | Pungut P01 | Pungut 00047 | S2-E1-54B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210132DR | 2021-08-30 14:00 | 2021-09-13 16:00 | 2021-10-03 23:00 | COMPLETE
Seruni | SERU21-P07 | Seruni 00051 | N2-W3-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210160DR | 2021-10-03 23:00 | 2021-10-14 05:00 | 2021-10-26 06:00 | COMPLETE
Seruni | SRN-P2 | Seruni 00052 | N2-W3-55B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210162DR | 2021-10-26 06:00 | 2021-10-30 02:00 | 2021-11-12 10:00 | COMPLETE
Seruni | SRN-P4 | Seruni 00053 | N1-W2-41C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210164DR | 2021-11-12 10:00 | 2021-11-19 09:00 | 2021-12-03 18:00 | COMPLETE
Seruni | SRN-P1 | Seruni 00054 | N2-W3-47A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210161DR | 2021-12-03 18:00 | 2021-12-08 19:00 | 2021-12-18 13:00 | RELEASE
Seruni | SRN-P3 | Seruni 00055 | N2-W3-34A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210163DR | 2021-12-18 13:00 | 2021-12-31 16:30 | 2022-01-10 14:00 | RELEASE
Seruni | SRN-P06 | Seruni 00056 | N1-W2-41D | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220278DR | 2022-01-10 14:00 | 2022-01-20 20:00 | 2022-02-03 | COMPLETE
Seruni | SRN-P14 | Seruni 00057 | N1-W2-31B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220276DR | 2022-02-03 | 2022-02-08 12:00 | 2022-02-21 15:00 | COMPLETE
Balam So | BLSO-P13 | Balam So 00452 | N1-O-55A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220001DR | 2022-02-21 15:00 | 2022-03-02 19:00 | 2022-03-11 13:00 | COMPLETE
Balam So | BLSO-P32 | Balam So 00457 | S1-O-37C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220028DR | 2022-03-11 13:00 | 2022-03-17 23:00 | 2022-03-27 13:00 | RELEASE
Seruni | SRN-P13 | Seruni 00058 | N1-W2-31A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220277DR | 2022-03-27 13:00 | 2022-04-03 06:00 | 2022-04-18 13:00 | COMPLETE
Seruni | SRN-P05 | Seruni 00059 | N2-W3-25A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210038DR | 2022-04-18 13:00 | 2022-04-26 23:00 | 2022-05-07 | CANCELED
Ubi | UBI-X09 | Ubi 00047 | N3-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220280DR | 2022-05-07 | 2022-05-16 15:00 | 2022-06-17 16:00 | RELEASE
Ubi | UBI-X03 | Ubi 00048 | N4-O-84B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220279DR | 2022-06-17 16:00 | 2022-06-24 07:00 | 2022-07-08 11:00 | RELEASE
Ubi | UBI-X06 | Ubi 00049 | N3-O-37A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220285DR | 2022-07-08 11:00 | 2022-07-15 07:00 | 2022-07-30 16:00 | RELEASE
Ubi | UBI-X08 | Ubi 00050 | N3-O-62B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2220282DR | 2022-07-30 16:00 | 2022-08-05 08:00 | 2022-08-21 14:00 | COMPLETE
Ubi | UBI-X10 | Ubi 00051 | N2-O-24B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220512DR | 2022-08-21 14:00 | 2022-08-27 01:00 | 2022-09-09 01:00 | RELEASE
Seruni | SRN-P05_Ext | Seruni 00059-01 | N2-W3-25B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | GRK2/402/2210038DR | 2022-09-09 01:00 | 2022-09-21 02:00 | 2022-10-09 14:00 | COMPLETE
Bangko | BNK_P169A_LQR | Bangko 00417 | N2-W2-71A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220413DR | 2022-10-09 14:00 | 2022-10-18 03:00 | 2022-10-31 02:30 | RELEASE
Bangko | BNK_P63B_LQR | Bangko 00399 | N3-W3-88B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220359DR | 2022-10-31 14:00 | 2022-11-06 03:30 | 2022-11-17 | RELEASE
Bangko | BNK_P29D_LQR | Bangko 00416 | N2-W2-44 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220394DR | 2022-11-17 | 2022-10-02 03:00 | 2022-12-04 12:00 | COMPLETE
Bangko | BNK_P94E_LQR | Bangko 00406 | N1-W2-24A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220431DR | 2022-12-04 12:00 | 2022-12-11 15:00 | 2022-12-23 04:30 | RELEASE
Bangko | BNK_P112E_LQR | Bangko 00408 | O-W3-24A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220348DR | 2022-12-23 04:30 | 2022-12-31 15:00 | 2023-01-10 10:00 | COMPLETE
Bangko | BNK_P108E_LQR | Bangko 00413 | O-W2-44A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220377DR | 2023-01-10 10:00 | 2023-01-16 | 2023-01-25 05:00 | RELEASE
Bangko | BNK_P122B_LQR | Bangko 00410 | N1-W3-26B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220437DR | 2023-01-25 05:00 | 2023-02-02 08:00 | 2023-02-20 22:00 | RELEASE
Sikladi | SKL23_P05 | Sikladi 00030 | N1-O-14A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220925DR | 2023-02-20 22:00 | 2023-03-04 21:00 | 2023-03-15 19:00 | RELEASE
Sikladi | SKL23_P01 | Sikladi 00031 | O-O-46A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220921DR | 2023-03-15 19:00 | 2023-03-28 | 2023-04-11 14:00 | COMPLETE
Sikladi | SKL23_P02 | Sikladi 00032 | O-O-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220922DR | 2023-04-11 14:00 | 2023-04-15 15:00 | 2023-05-05 16:00 | COMPLETE
Sikladi | SIKL23_P06 | Sikladi 00033 | O-O-46C | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3230174DR | 2023-05-05 16:00 | 2023-05-11 02:00 | 2023-06-03 10:00 | COMPLETE
Sikladi | SKL23_P03 | Sikladi 00034 | O-O-26B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220924DR | 2023-06-03 10:00 | 2023-06-09 18:30 | 2023-07-03 | COMPLETE
Sikladi | SKL23_P04 | Sikladi 00035 | N1-O-65A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSA2/402/3220923DR | 2023-07-03 | 2023-07-10 10:00 | 2023-07-28 03:00 | RELEASE
Balam So | BLSO23-LQR-TE077 | Balam So 00542 | N1-W1-87B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230366DR | 2023-07-28 03:00 | 2023-08-09 12:00 | 2023-08-14 12:00 | COMPLETE
Balam So | BLSO23-LQR-TE065 | Balam So 00545 | N1-O-21A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230343DR | 2023-08-14 12:00 | 2023-08-20 14:30 | 2023-08-26 | COMPLETE
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230355DR | 2023-08-26 | 2023-08-31 23:30 | 2023-09-06 | COMPLETE
Balam So | BLSO23-LQR-TE043 | Balam So 00551 | N1-O-71B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230333DR | 2023-09-06 | 2023-09-11 01:00 | 2023-09-15 20:00 | COMPLETE
Balam So | BLSO23-LQR-TE046 | Balam So 00552 | O-O-73A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230351DR | 2023-09-15 20:00 | 2023-09-20 21:00 | 2023-09-25 12:00 | COMPLETE
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230350DR | 2023-09-25 12:00 | 2023-09-30 03:00 | 2023-10-04 12:00 | RELEASE
Balam So | BLSO23-LQR-TE076 | Balam So 00556 | N1-O-81A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230365DR | 2023-10-04 12:00 | 2023-10-11 12:00 | 2023-10-16 | COMPLETE
Balam So | BLSO23-LQR-TE074 | Balam So 00557 | N1-W1-26C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230335DR | 2023-10-16 | 2023-10-21 21:00 | 2023-10-26 | COMPLETE
Balam So | BLSO23-LQR-TE005 | Balam So 00561 | O-W1-35C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230342DR | 2023-10-26 | 2023-11-02 03:30 | 2023-11-06 17:00 | COMPLETE
Balam So | BLSO23-LQR-TE075 | Balam So 00563 | N1-W1-35 | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230356DR | 2023-11-06 17:00 | 2023-11-16 | 2023-11-20 07:00 | COMPLETE
Balam So | BLSO23-LQR-TE035 | Balam So 00567 | N1-W1-34B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230337DR | 2023-11-20 07:00 | 2023-12-01 10:30 | 2023-12-05 17:00 | COMPLETE
Balam Se | P_BLSE23_P11_PM | Balam Se 00035 | N1-E1-61A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230307DR | 2023-12-05 17:00 | 2023-12-17 18:00 | 2023-12-31 03:00 | COMPLETE
Balam Se | P_BLSE23_P17_PM | Balam Se 00036 | N1-E1-61B | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230308DR | 2023-12-31 03:00 | 2024-01-05 17:00 | 2024-01-18 06:30 | COMPLETE
Balam So | BLSO23-P09 | Balam So 00576 | S1-O-54A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSO2/402/3220604DR | 2024-01-18 06:30 | 2024-01-31 23:00 | 2024-02-15 16:00 | COMPLETE
Balam Se | P_BLSE23_P12_PM | Balam Se 00039 | N1-E1-61C | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230309DR | 2024-02-15 16:00 | 2024-02-24 03:00 | 2024-03-07 13:00 | COMPLETE
Balam Se | P_BLSE23_P14_PM | Balam Se 00041 | N1-E1-61D | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230310DR | 2024-03-07 13:00 | 2024-03-12 | 2024-03-26 | COMPLETE
Balam Se | P_BLSE23_P18_PM | Balam Se 00042 | N1-E1-61E | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SSE2/402/3230311DR | 2024-03-26 | 2024-03-31 15:00 | 2024-04-12 21:00 | COMPLETE
Pinang | P_PINA24_02 | Pinang 00065 | N1-W1-51 | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SPT2/402/3240823DR | 2024-06-16 10:00 | 2024-06-16 10:00 | 2024-07-06 03:00 | COMPLETE
Pinang | P_PINA24_05 | Pinang 00066 | N1-W2-46B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-52.2 | SPT2/402/3240825DR | 2024-07-06 03:00 | 2024-07-12 17:00 |  | IN_PROGRESS
Pudu | PDU23_P08 | Pudu 00022 | O-O-43A | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-53.2 | SSN2/402/3230698DR | 2024-06-27 17:00 | 2024-06-27 17:00 |  | IN_PROGRESS
Pukat | P_PUKA23_P03 | Pukat 00007 | S1-O-41A | Drill and Suspend | DRL01 - Drill Hole | Land Drilling Rig | PDSI-54.2 | SPS2/402/3240894DR | 2024-06-13 20:00 | 2024-06-13 20:00 | 2024-07-04 20:30 | COMPLETE
Pukat | P_PUKA23_P04 | Pukat 00008 | S1-O-41B | Drill and Complete | DRL01 - Drill Hole | Land Drilling Rig | PDSI-54.2 | SPS2/402/3240896DR | 2024-07-04 20:30 | 2024-07-11 21:00 | 2024-07-11 21:00 | IN_PROGRESS
Bangko | BNK-X02 | Bangko 00389 | O-O-21C | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-02 | GRK2/402/2220069DR | 2023-01-14 14:00 |  | 2023-01-14 17:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-02 | SSO2/402/3220383DR | 2023-08-13 16:00 |  | 2023-08-13 20:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-03 | SSO2/402/3220383DR | 2023-03-30 13:00 |  | 2023-03-30 17:00 | COMPLETE
Pinang | P_PINA23_P08 | Pinang 00059 | N1-W1-73B | Surface Systems Maintenance | SRF04 - Well Head Repair/ Change/ Modify | Mast Unit | PHW-03 | PNA2/402/3220823DR | 2023-07-06 14:00 |  | 2023-07-06 19:00 | COMPLETE
Pinang | P_PINA23_P09 | Pinang 00062 | N1-W2-57A | Surface Systems Maintenance | SRF04 - Well Head Repaire/ Change/ Modify | Mast Unit | PHW-03 | PNG2/402/3220837DR | 2023-08-09 13:00 |  | 2023-08-09 18:00 | COMPLETE
Balam So | BLSO23-LQR-TE044 | Balam So 00526 | O-O-64D | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSO2/402/3220588DR | 2024-02-17 14:00 | 2023-11-15 21:00 | 2024-02-22 16:00 | COMPLETE
Balam So | BLSO23-LQR-TE063 | Balam So 00525 | O-O-64E | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSE2/402/3230364DR | 2024-02-28 12:00 | 2024-02-26 20:00 | 2024-03-01 10:00 | COMPLETE
Balam So | BLSO23-LQR-TE038 | Balam So 00522 | O-O-64C | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-016 | SSO2/402/3220548DR | 2024-04-21 14:00 | 2024-05-05 05:00 | 2024-04-24 19:00 | COMPLETE
Bangko | BNK_P289B_LQR | Bangko 00420 | N1-W3-32A | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSO2/402/3220383DR | 2024-06-21 09:00 | 2024-06-10 17:00 | 2024-06-25 15:00 | IN_PROGRESS
Balam So | BLSO23-LQR-TE061 | Balam So 00548 | N1-W1-54B | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSE2/402/3230355DR | 2024-07-11 14:00 | 2024-06-12 16:00 | 2024-07-14 17:00 | SUSPENDED
Balam So | BLSO23-LQR-TE057 | Balam So 00554 | O-O-65E | Complete | COM02 - Initial Completion Oil Producer | On-Site Equipment | WCT-018 | SSE2/402/3230350DR | 2024-07-11 14:00 | 2024-05-25 10:00 | 2024-07-15 17:00 | SUSPENDED
Balam So | BLSO23-LQR-TE022 | Balam So 00535 | N1-W1-27A | Complete | COM02 - Initial Completion Oil Producer | Mast Unit | WCT-021 | SSO2/402/3220416DR | 2024-06-06 19:00 | 2024-05-20 02:00 | 2024-06-10 16:00 | COMPLETE
Minas | EXP_Mibasa-1 | Minas 02114 | 3D-74N | Complete | COM02 - Initial Completion Oil Producer | Swabbing Unit | WCT-025 | MBS2/402/3230833EX | 2024-06-21 16:30 | 2024-05-16 | 2024-06-25 16:30 | COMPLETE